Configuration Management Plan Template

Scope

This document contains instructions for the Configuration Management Plan (CMP) as required by MIL-HDBK-61A, EIA 649, and IEEE 12207.  The information contained herein is intended for compliance by the Organization to include contractors performing configuration management.  This CMP template is to be used by all project configuration managers as guidelines for documenting configuration management.

Tailorability

The CMP may be tailored to fit project-unique configuration management requirements based on the life-cycle phase, complexity, size, intended use (including joint and combined interoperability), mission criticality, and logistic support of the project’s Configuration Items (CIs).  If a section or paragraph is tailored out, the following statement shall be added directly following the heading: “This section has been tailored out.”

Revisions and approval authority

After a project’s CMP is completed under the guidelines of this template, the plan may be coordinated through the SEPG if desired, to ensure SEP compliance.  Approval authority resides with the Program Manager.  After approval, the project’s CMP becomes a configuration-controlled item.  Revisions to the CMP must be recorded in the Record Review and History page of the plan.  Minor changes may be certified by the Program Manager through electronic mail and “officially” incorporated during the next major revision.

Organization and content of the document

The required contents of how the information is to be documented in the plan is recorded in a template on the next several pages.

CONFIGURATION MANAGEMENT PLAN

for

[Project Name]

[Date of document]

[Version Number (Optional)]

Project Configuration                 Name					  Date:

Manager

Project Manager		       Name						  Date:

Lead Engineer		       Name						  Date:

Program Manager                       Name					  Date:

Table of Contents

1.0 Introduction	5

1.1 Purpose and Scope	5

1.2 Constraints	5

1.3 Key Terminology	5

1.4 Reference Documents	5

2.0 Organization	5

3.0 Configuration Management Phasing and Milestones	5

3.1 Establishment of Baselines	5

3.1.1 Functional Baseline	6

3.1.2 Allocated Baseline	6

3.1.3 Product Baseline	6

3.2 Implementation of Configuration Control	6

3.3 Implementation of Status Accounting Information	6

3.4 Establishment of Configuration Audits	6

4.0 Data Management	6

5.0 Configuration Identification	7

5.1 Identifying Configuration Items	7

5.2 Naming Convention	7

5.3 Acquiring Configuration Items	7

6.0 Interface Management	7

7.0 Configuration Control	7

7.1 Requesting a Change	7

7.2 Evaluating the Change	7

7.3 Approving or Disapproving the Change	8

7.4 Implementing the Change	8

8.0 Configuration Status Accounting	8

9.0 Configuration Audits	8

10.0 Configuration Management Library	9

11.0 Contractor Control	9

12.0 Configuration Management Resources	9

13.0 Configuration Management Metrics	9

Record Review and History Page

| Record of Reviews and Changes |  |  |  |  |
| --- | --- | --- | --- | --- |
| Change ID or CI # | Date Reviewed | Date Approved | Comment | Signature |

# Introduction

  - Purpose and Scope

The purpose and scope of this Configuration Management Plan is to define and document the configuration management procedures, processes, and activities used to control and manage the development and modifications of products supporting the project.

  - Constraints

This paragraph shall provide a concise summary of the project’s approach to configuration management, including any special conditions (such as security constraints, interoperability constraints, non-developmental items, mobile code risk categories, etc.) upon which the approach is based.

  - Key Terminology

To foster a common understanding among project personnel, this paragraph shall contain a list of key terms used throughout the CMP.  Note: Key terms must be defined in this paragraph or in an appendix attached to this plan.

  - Reference Documents

This paragraph shall list the specifications, standards, manuals and other documents, including project policy directives, referenced in the Plan by title, document number, issuing authority, revision, and when applicable, change notice, amendment number, and date of issue.

# Organization

This section describes and graphically portrays the project’s configuration management organization and its integration and relationship with other organizations and groups involved in the development and lifecycle of products under configuration management control.

a.	The relationships and integration of the project organization and functional     organization;

- Responsibility and authority for configuration management of all participating groups and organizations including their role in configuration control boards, functional review boards, and the integration of configuration management functions with other program activities such as technical reviews;

- Identification of the project’s configuration management organization and its responsibilities;

- Interfaces between the project’s configuration management organization and the contractor’s configuration management organization.  Organizational entities may consist of a customer and developer, prime contractor and subcontractor, or subgroups within an organization.

# Configuration Management Phasing and Milestones

This section shall describe the sequence of events and milestones for implementation of configuration management in phase with major project milestones and events, including as a minimum:

  - Establishment of Baselines

Once it has been formally determined that an item meets specified requirements at a specific time in its life cycle, the particular version of that item becomes its configuration baseline.  There are three types of baselines that are formally designated for a CI during its life cycle.  They are as follows:

### Functional Baseline

The Functional Baseline of a CI is established during the first phase of its life cycle at the completion of the formal meeting (i.e. CCB, management review, etc.) that’s conducted to approve the documentation.  Refer to the Baseline Establishment Procedure.

### Allocated Baseline

The Allocated Baseline of a CI is established at the completion of the System Specification Review or Preliminary Design Review.  Refer to the Baseline Establishment Procedure.

### Product Baseline

The Product Baseline is established when all the software that comprises an identified component (CSC or CI) has been successfully compiled, linked and integration tested.  Any proposed changes to the PBL after Test Readiness Review I or II must be submitted and approved on a Systems Change Request (SCR).  After software is released, a Deficiency Report (DR), CCB Action Item, Baseline/Systems Change Request (BCR/SCR), or a Requirements Document must originate changes.  Refer to the Baseline Establishment Procedure.

  - Implementation of Configuration Control

Configuration control regulates changes to the system.  For further details see the paragraph below on ‘Configuration Control’.

  - Implementation of Status Accounting Information

Configuration Status Accounting information is needed to manage the functional and physical characteristics of the CIs and may include the following: 1) a listing of the approved documents that identify and define the item’s functional and physical characteristics, 2) the status of proposed changes, deviations, and waivers to those characteristics, 3) the implementation status of approved changes, and 4) the functional and physical characteristics of all units of the CIs in the operational inventory.  See the paragraph below on ‘Configuration Status Accounting’, for further details on the status reporting procedures.

  - Establishment of Configuration Audits

Configuration audits determine to what extent the actual CI reflects the physical and functional characteristics desired by the user.  Audits may be used as management tools for establishing a baseline.  The audit team will consist of, as a minimum, the Project Configuration Manager, Project Manager, and PMO representative.  Some members of the Project Development Team may also serve as members of the audit team.  See Functional Configuration Audit Procedure and Physical Configuration Audit Procedure for details on the responsibilities of the audit team members.

# Data Management

This section shall describe the methods for meeting the configuration management technical data (data transfer, media, accessibility, security, etc) requirements of Section 9, MIL-HDBK-61A.

# Configuration Identification

Reference IEEE/EIA 12207 Paragraph 6.2.2 and MIL-HDBK-61A Section 5.  A scheme shall be established for the identification of CIs and their versions to be controlled for the project.  For each CI and its versions, the following shall be identified: the documentation that establishes the baseline, the version references, and other identification details.

  - Identifying Configuration Items

This paragraph shall list and describe the CIs to be defined and controlled.  NOTE:  This information may be maintained in a document separate from this plan.  If this is the case, that document should be referenced in this paragraph.

  - Naming Convention

This shall describe the identification system used by your project to assign unique identifiers for each CI or entity to be controlled.  Note following example:

[User defined unique identifier].  [Object type]---for example:  cmdtrans.fmb (form type)

  - Acquiring Configuration Items

This paragraph shall describe how the code, documentation, and date of identified baselines are physically controlled in the project’s configuration management libraries.

# Interface Management

This section shall describe the procedures for meeting the interface management (CIs, system, Interface Control Working Group, etc.) requirements of the project.  Reference MIL-HDBK-61A.

# Configuration Control

Reference IEEE/EIA 12207.2 Paragraph 6.2.3, MIL-HDBK-61A, Section 6.  The following shall be performed:  identification and recording of change requests; analysis and evaluation of the changes; approval or disapproval of the request; and implementation, verification and release of the modified software item.  An audit trail shall exist, whereby each modification, the reason for the modification, and authorization of the modification can be traced.  Control and audit of all accesses to the controlled CIs that handle safety or security critical functions shall be performed.

  - Requesting a Change

This paragraph shall describe the procedures that have been established for requesting changes to baseline CIs for the project.  Established reporting forms may be used to request a change.  As a minimum, the information necessary for proposing a change shall contain the following:

- Date of initiation

- Originator of request

- Scope

- Subject

- Identification of requested item, service or response

- Detailed description of requested item, service or response, including suspense date

- Justifications

  - Evaluating the Change

This paragraph shall specify type of analysis conducted to determine the impact of the proposed change and the review procedures necessary to accomplish the analysis.  Reference MIL-HDBK-61A Section 6 and EIA 649 paragraph 5.3.1.2.  Potential threats and vulnerabilities regarding the management of any mobile code technologies that have an impact on the operability or functionality of the system must be identified and described in this paragraph.  Reference DODI 8500.2 and DODI 8552.01.

  - Approving or Disapproving the Change

This paragraph shall describe the functions of configuration management boards (i.e. Configuration Control Board (CCB) or Functional Review Board (FRB)) and the level of authority for approving a proposed change.  A CCB may be an individual or a group.  NOTE:  The procedures established for approval or disapproval of changes not requiring a CCB or FRB (i.e. the Project Manager approves Class II, etc.) must also be documented in this area.

  - Implementing the Change

This paragraph shall describe how an approved change request is implemented into an existing baselined CI, to include information addressing how all applicable mobile code software will be implemented with the change.  The minimum information necessary for completing a change shall contain the following:

a. The associated change requests

b. Names and versions of the affected items

c. The identifier of the new version

d. Verification date and responsible party

e. Installation date and responsible party

# Configuration Status Accounting

This section shall describe the management records and status reports that show the status and history of controlled items including software baseline shall be prepared.  Status reports should include the number of changes for a project, latest software item versions, release identifiers, the number of releases, and comparisons of releases.  Reference IEEE/EIA 12207.2, paragraph 6.2.4, EIA 649 paragraph 5.4, MIL-HDBK-61A Section 7.

# Configuration Audits

Configuration auditing verifies that the software product is built according to the requirements, standards, or contractual agreement.  Auditing also verifies that all software products have been produced, correctly identified, and that all change requests have been resolved.  A configuration audit ensures that the configuration management practices and procedures are rigorously followed.  The integrity of the baselines must be assessed.  The completeness and correctness of the software baseline library contents need to be verified.  The accuracy of the implementation of the changes to the baselines also should be verified to ensure that the changes were implemented as intended.  Reference MIL-HDBK-61A, section 8, EIA 649 paragraph 5.5.2.  NOTE:  The information listed below must be defined prior to conducting an audit:

a. Objective of audit or review

b. CIs to be audited or reviewed

c. Audit or review schedule of events

d. Procedures for conducting the audit or review

e. Participants involved

f. Necessary documentation required to be reviewed or to support the audit or review

g. Method of identifying discrepancies and reporting corrective actions

h. Approval criteria and specific actions required

# Configuration Management Library

This section shall describe the number and types of configuration management libraries, from physical to automated, that will control and maintain the various types of software products associated with software development.

# Contractor Control

This section shall describe the methods used by the government to ensure the contractor’s compliance with configuration management (identification, change control, status accounting, audit, etc.) requirements.

# Configuration Management Resources

This section shall describe the configuration management tools, techniques, equipment, personnel and necessary skills, and training required for implementing a sound project configuration management discipline.

# Configuration Management Metrics

This section shall describe the type of metrics to be collected at the project level, frequency of collection, and reporting requirements.