# project management plan

# TEMPLATE

TM-PP-01 V2.0

May 24, 2005

Systems Engineering Process Office, Code 20203

Space and Naval Warfare Systems Center

53560 Hull Street

San Diego CA 92152-5001

Approved for public release; distribution is unlimited.

Preface

This template provides the format and content of a Project Management Plan (PMP) for a mid-sized project (e.g., 5 to 20 staff members).  Typically, larger projects will receive explicit direction from the sponsor on planning documentation requirements.  Smaller projects may use a scaled-down version of this template.  The template is considered flexible enough that it may be used for any type of project.

This document is part of a trilogy of sample documents and templates intended to support the guidance provided by the SSC San Diego Project Management Guide (PMG).  Figure A provides an abstract of the PMG’s project management functions of Initiation, Planning, Control, Execution, and Close Out.  As depicted in Figure A, the Planning Function includes the development of plans to facilitate both the Control Function and the Execution Function.

Figure A.  Project Management Guide Functional Overview

Three documents available from the Space and Naval Warfare (SPAWAR) Systems Center (SSC) San Diego Process Asset Library (PAL) Web site at http://sepo.spawar.navy.mil/ are recommended for the implementation of the concepts presented in the PMG.  While these documents are not the only means or document selections that can facilitate this process, they are considered a ‘Best Practice’ and can be tailored during the Planning Function to guide the Control Function and Execution Function.  This trilogy of documents includes those listed below:

Trilogy Part 1.  Project Management Plan (PMP) Template, TM-PP-01 (this document).  Control function planning requires a defined Management Solution, documented in a format such as the IEEE Standard for Software Management Plans, IEEE Std 1058-1998.  The PMP addresses such issues as budget, budget control, schedule, schedule control, staffing, risk management, configuration management, quality assurance, and project tracking measurements.

Trilogy Part 2.  Product Engineering and Qualification (PE&Q) Process, PR-TS-01.  Planning for the Execution function results in documented engineering and qualification processes needed to implement a project’s work product(s).  The PE&Q Process represents an example of the level of detail needed for these processes.  The PE&Q Process represents one method of defining an engineering process.  Other process definition methods could include, but are not limited to, data flow diagrams, Entry-Task-Verification &Validation-Exit (ETVX) diagrams, Integrated Computer Aided Manufacturing Definition (IDEF) 0 or IDEF 3 diagrams for process flow, etc.

Trilogy Part 3.  Project Build Plan Template, TM-PP-02.  Planning for the functional content of the project’s work product should result in a document as typified by the Project Build Plan Template.  This document defines the product content in terms of functional requirements to be delivered, the acceptance criteria, fielding direction, and user training needs.  This document could serve as a contract between the acquirer and the supplier for any given deliverable increment of the product.  Other build plan methodologies could include, but are not limited to, use of the MIL-STD 498 Data Item Description (DID) for Software Version Description (SVD), or detailed project plans itemizing the product content.

These three documents are an integral part of the SSC San Diego-approved life cycle strategies as defined in A Description of the SSC San Diego Standard Process Assets (SPA). These documents are available on the SSC San Diego PAL Web site along with the SPA itself.

SSC San Diego has assigned the responsibility for this document to the Systems Engineering Process Office (SEPO).  SEPO welcomes and solicits feedback from users of this document so that future revisions of this document will reflect improvements, based on organizational experience and lessons learned.  Questions or comments regarding this document may be communicated to SEPO via the Document Change Request form located on the next page or submitted online via the SSC San Diego PAL.  Updates to this document are performed in accordance with the SEPO Configuration Management Procedure.

DOCUMENT CHANGE REQUEST (DCR)

| Document Title: Project Management Plan Template | Tracking Number: |
| --- | --- |
| Name of Submitting Organization: |
| Organization Contact: | Phone: |
| Mailing Address: |
| DCR Description: | Date: |
| Change Location: (use section #, figure #, table #, etc.) |
| Proposed change: |
| Rational for Change: |
| Note: For the Systems Engineering Process Office (SEPO) to take appropriate action on a change request, please provide a clear description of the recommended change along with supporting rationale. Send to: Commanding Officer, Space and Naval Warfare Systems Center, Code 20203, 53560 Hull Street, San Diego, CA 92152-5001 Fax : (619) 553-6249 Email : sepo@spawar.navy.mil Submit online: http://sepo.spawar.navy.mil/ DCR Form 11/2004 |

RECORD OF CHANGES

*A - ADDED  M - MODIFIED  D – DELETED

| VERSION NUMBER | DATE | NUMBER OF FIGURE, TABLE OR PARAGRAPH | A* M D | TITLE OR BRIEF DESCRIPTION | CHANGE REQUEST NUMBER |
| --- | --- | --- | --- | --- | --- |
| 1.0 | 12/16/03 |  |  | Original. This document replaces the document of the same name with a configuration number of TM-SPP-09. Minor corrections to references and several configuration numbers have been made in this version | PP-0002 |
| 2.0 | 5/24/05 | Throughout | A M D | Updated per Project Management Council Peer Review |  |
| 2.0 | 5/24/05 | Throughout | A | Added information about using the DAR Process | PP-0004 |
| 2.0 | 5/24/05 | Throughout | A | Multiple changes from DCR | PP-0007 |
| 2.0 | 5/24/05 | Section 5.4 | A | Expand information on Risk Management | PP-0008 |

DOCUMENT CONVENTIONS

The outline of this Project Management Plan (PMP) has been tailored from the Institute of Electrical and Electronics Engineers (IEEE) Standard for Software Project Management Plans, IEEE Std 1058-1998.  While the title implies guidance for software projects, the content, scope, and flexibility of the IEEE Standard facilitates application to a variety of projects that are typical of the scope found at SSC San Diego (i.e., systems, software, integration services, R&D, etc.).  It is intended that the template and its content be tailored to define a project's management, technical, and supporting processes in the context of Standard for Information Technology - Software Life Cycle Processes, IEEE/Electronic Industries Association (EIA) 12207 Series; Systems Engineering – System Life Cycle Processes, International Organization for Standardization (ISO)/International Electrotechnical Commission (IEC) 15288; or the Processes for Engineering a System, Electronic Industries Alliance (EIA) Standard 632.

Standard conventions are used within this document to direct the reader to specific sections of the text.  These sections provide instructions and explanations and require users to substitute their own project-specific information for the generic information provided or to “fill in the blank.”  The conventions used in this document are shown below.

[[text]]	Global changes.  Items that appear in regular text and are surrounded by double brackets represent changes that can be made globally throughout the document.

Italics	Individual changes.  Items that appear in bold italics represent items that need to be changed in that location only.  The bold italics are not meant to appear in the completed version of the document.

Italics	Instructions and explanations.  Each section of the template has been annotated with a guidance box, derived from the IEEE 1058-1998 standard, to assist the reader in drafting the content.  For example:

IEEE Std 1058-1998 Guidance

The guidance box provides instructions and explanations from the IEEE 1058-1998 standard, in italics, as required to assist the user in drafting their own information.

Watermark.	To further assist in drafting the required information, the sections contain a sample of a hypothetical project.  A watermark has been placed diagonally across the page to indicate that the text is an example of the type of information that should appear in each section.

The samples have been constructed such that if extracted from the template with their associated paragraph number they would create a good first draft of a PMP.  The template samples are written as a project management plan for a hypothetical project, the Red/Black Controller (RBC) Project.  Combining the IEEE standard derived guidance with sample content has created a template in the form of an annotated version of a PMP.

Users should first review the generic processes contained in the PMP Template samples to ensure an understanding of scope, management processes, technical processes, relationships, and responsibilities for the positions within the model organization.  It is important to understand that the sample organization and processes do not fit all projects but serve as a representative example, requiring tailoring to meet project specific needs.

It is recommended that the Section 4 organizational diagrams and Table 4-1, addressing roles and responsibilities, be printed and kept readily available for reference as one reads the individual samples associated with the guidance information.

Tailoring should follow the directions contained in the SPA document available from the SSC San Diego PAL.

The PMP Template contains engineering process definitions and references to other key templates for disciplines such as configuration management and quality assurance.  These templates, available from the SSC San Diego PAL, comprise a suite of process descriptions that can be packaged in a multitude of formats.

The PMP Template is intended to be tailored at the Department level to serve each Department’s business domain prior to its deployment to individual projects.

The PMP begins on the next page with a PMP title and approval page.  Delete this Document Conventions page and all preceding pages in the final version of your PMP.  Remember to update the header to reflect the appropriate document configuration identifier for your project’s PMP.

This page intentionally left blank.

# project management plan

# for the

# [[red/Black controller project]]

# [[document configuration identifier]]

# [[DATE]]

Place project logo here

[[Project Name, Code]]

Space and Naval Warfare Systems Center

53560 Hull Street

San Diego CA 92152-5001

Approved for public release; distribution is unlimited.

project management plan

for the

[[red/Black controller project]]

[[document configuration identifier]]

[[DATE]]

PMP Approvals:

_____________________________	____________

[[RBC]] Project Manager	Date

_____________________________	____________

Division Head	Date

_____________________________	____________

Program Manager	Date

[[SYSCOM Communications Security Office]]

Preface

This Project Management Plan (PMP) is intended to provide guidance on the management of the [[Red/Black Controller (RBC) Project]].

The plan has been tailored from the Space and Naval Warfare (SPAWAR) Systems Center (SSC) San Diego Project Management Plan Template, TM-PP-01.  The template conforms to the Institute of Electrical and Electronics Engineers (IEEE) Standard for Software Project Management Plans, IEEE Std 1058-1998, for format and content.  The template and its standard were selected as they are flexible enough to be applied to any type of project.  The management, technical, and supporting processes comply with the guidance provided by Standard for Information Technology - Software Life Cycle Processes, IEEE/Electronic Industries Association (EIA) 12207 Series; Systems Engineering – System Life Cycle Processes, International Organization for Standardization (ISO)/International Electrotechnical Commission (IEC) 15288; or the Processes for Engineering a System, Electronic Industries Alliance (EIA) Standard 632; and the SSC San Diego Systems/Software Engineering Management Policy.

The [[RBC]] Project Manager assumes responsibility for this document and updates it as required to meet the needs of the [[Systems Command Communications Security Office]].  Updates to this document are performed in accordance with the [[RBC]] Configuration Management Process, [[RBC CM process document configuration identifier]].

RECORD OF CHANGES

*A - ADDED  M - MODIFIED  D – DELETED

| VERSION NUMBER | DATE | NUMBER OF FIGURE, TABLE OR PARAGRAPH | A* M D | TITLE OR BRIEF DESCRIPTION | CHANGE REQUEST NUMBER |
| --- | --- | --- | --- | --- | --- |

Table of Contents

Section	Page

SECTION 1.  OVERVIEW	1-1

1.1	Project Summary	1-1

1.1.1	Purpose, Scope, and Objectives	1-2

1.1.2	Assumptions and Constraints	1-2

1.1.3	Project Deliverables	1-2

1.1.4	Master Schedule and Budget Summary	1-3

1.2	Evolution of the Plan	1-4

1.3	Document Structure	1-4

SECTION 2.  REFERENCES	2-1

2.1	Standards and Documents	2-1

2.2	Deviations and Waivers	2-2

SECTION 3.  DEFINITIONS	3-1

SECTION 4.  PROJECT ORGANIZATION	4-1

4.1	External Interfaces	4-1

4.2	Internal Structure	4-3

4.2.1	The Project Manager	4-3

4.3	Project Roles and Responsibilities	4-4

SECTION 5.  MANAGEment PROCESS	5-1

5.1	Start-up	5-1

5.1.1	Estimation	5-1

5.1.2	Staffing	5-1

5.1.3	Resource Acquisition	5-2

5.1.4	Staff Training	5-2

5.2	Work Planning	5-2

5.2.1	Work Activities	5-2

5.2.2	Schedule Allocation	5-3

5.2.3	Resource Allocation	5-3

5.2.4	Budget Allocation	5-5

5.3	Project Controls	5-6

5.3.1	Requirements Control	5-7

5.3.2	Schedule Control	5-7

5.3.3	Budget Control	5-8

5.3.4	Quality Control	5-10

5.3.5	Project Reporting and Communication	5-10

5.3.6	Metrics Collection	5-11

5.4	Risk Management	5-11

5.5	Project Closeout	5-12

SECTION 6.  TECHNICAL PROCESS	6-1

6.1	Process Model	6-1

6.2	Methods, Tools and Techniques	6-2

6.3	Project Infrastructure	6-2

6.4	Product Acceptance	6-2

SECTION 7.  SUPPORTING PROCESSES	7-1

7.1	Configuration Management	7-1

7.2	Independent Verification and Validation	7-1

7.3	Documentation	7-1

7.4	Quality Assurance	7-3

7.5	Reviews and Audits	7-3

7.6	Problem Resolution	7-3

7.6.1	TRB Membership	7-5

7.6.2	TRB Chairperson	7-5

7.7	Contractor Management	7-5

7.7.1	Contracting Process	7-6

7.7.2	Contractor Performance Monitoring	7-6

7.8	Process Improvement	7-6

7.8.1	Systems/Software Process Improvement Lead	7-6

7.8.2	Systems Engineering Process Group	7-7

SECTION 8.  Additional Plans	8-1

8.1	Logistics Engineering	8-1

8.1.1	System Performance	8-2

8.1.2	System Availability	8-2

8.1.3	Process Efficiency	8-2

8.1.4	Technical Effectiveness	8-2

8.1.5	System Effectiveness	8-2

8.1.6	System Ownership Cost	8-2

Appendix A.  RBC Master Schedule (Microsoft Project)	Appendices-2

Appendix B.  RBC Facilities Plan	APPENDICES-3

Appendix C.  RBC Project Training Plan	APPENDICES-4

Appendix D.  RBC Measurement Plan	APPENDICES-5

Appendix E.  RBC Product Engineering and Qualification Process	APPENDICES-6

Appendix F.  RBC Quality Assurance Plan	APPENDICES-7

Appendix G.  RBC Configuration Management Plan	APPENDICES-8

List of Figures

Figure	Page

Figure 1-1.  RBC System Overview	1-1

Figure 1-2.  Master Build Schedule	1-3

Figure 4-1.  RBC Project External Organizational Interfaces	4-1

Figure 4-2.  RBC Project Internal Organizational Structure	4-3

Figure 5-1.  RBC Project Schedule Allocations	5-4

Figure 6-1.  RBC Project Life Cycle Strategy	6-1

Figure 8-1.  Components of System Operational Effectiveness	8-1

List of Tables

Table	Page

TABLE 1-1.  RBC Program Budget	1-3

TABLE 4-1.  Programmatic Roles and Responsibilies	4-2

TABLE 4-2.  Project Roles and Responsibilities	4-4

TABLE 5-1.  Staff Resources by Development Phase	5-4

TABLE 5-2.  RBC System Build Budget Allocation	5-5

TABLE 5-3.  Management Control System Elements	5-6

TABLE 7-1.  RBC Project Documentation	7-2

This page intentionally left blank.

# SECTION 1.  OVERVIEW

## 1.1	Project Summary

IEEE Std 1058-1998 Guidance

The IEEE Std 1058-1998 provides no specific guidance on Project Summary (Subclause1.1).  This section may be tailored as needed to provide additional subsections in which a project may be more fully described.  For example, 1.1 Project Summary, 1.1.1 System Overview, 1.1.2 Purpose, Scope, and Objectives, etc.  The following is an example of the recommended content.

The Red/Black Controller (RBC) system provides encryption/decryption services for numerous applications as part of communications systems, subsystems, and networks.  The RBC system can be applied at either the subscriber level to provide isolation between users of the network at different clearance levels or differing need-to-know requirements, or at the link level to provide encryption/decryption of all network control information and secondary encryption/decryption of all user data.  The RBC system does not operate in a stand-alone setting, but as a component in an overall Command, Control, Communications, Computers, and Intelligence (C4I) system.

The RBC system consists of two interfacing hardware configuration items embedded in the host C4I system.  Figure 1-1 is an overview of the RBC system and its hosted Computer Software Configuration Items (CSCIs).

Figure 1-1.  RBC System Overview

The CSCIs consist of the Red Control CSCI (RCC) and Black Control CSCI (BCC) residing in RED and BLACK processor components of the host C4I system.  The purpose of the BCC is to handle the BLACK data and BLACK control interfaces, handle the RCC interface, perform BLACK bypass data filtering and control, and conduct self test.  The purpose of the RCC is to handle the RED control interfaces, handle the BCC interface, control the Cryptographic Module, perform security management, perform Alarm/Alert processing, perform RED bypass data filtering and control, and conduct self test.

### 1.1.1	Purpose, Scope, and Objectives

IEEE Std 1058-1998 Guidance

(Subclause 1.1.1) Purpose, scope, and objectives

This subclause shall define the purpose, scope, and objectives of the project.  This shall include a brief statement of the business or system needs to be satisfied by the project, with a concise summary of the project objectives, the products to be delivered to satisfy those objectives, and the methods by which satisfaction will be determined.  The project statement of purpose shall describe the relationship of this project to other projects, and, as appropriate, how this project will be integrated with other projects or ongoing work processes.

The RBC Project involves the evolutionary development of the RBC system, a multipurpose cryptographic system hosted in a desktop configuration.  The scope of the project consists of both the hardware and software components delivered as an integrated system to sites specified by the Systems Command (SYSCOM) Communications Security Office.  RBC system provides the requisite communications security for systems and equipment implementing a wireless communication network.

### 1.1.2	Assumptions and Constraints

IEEE Std 1058-1998 Guidance

(Subclause 1.1.2) Assumptions and constraints

This subclause shall describe the assumptions on which the project is based and imposed constraints on project factors such as the schedule, budget, resources, components to be reused, acquirer components to be incorporated, technology to be employed, and product interfaces to other products.

The RBC project will tailor a suite of standard work processes from the Space and Naval Warfare (SPAWAR) Systems Center (SSC) San Diego organization standard processes as described in A Description of the SSC San Diego Standard Process Assets (SPA), reference (a) and available on the SSC San Diego Process Asset Library (PAL) at http://sepo.spawar.navy.mil.  This Project Management Plan (PMP) will state the general plans for the application of SSC San Diego policies, and processes for the RBC project.  Plans, policies, and processes described herein apply to the RBC project at SSC San Diego, and its supporting contractors.

### 1.1.3	Project Deliverables

IEEE Std 1058-1998 Guidance

(Subclause 1.1.3) Project deliverables

This subclause shall list the work products that will be delivered to the acquirer, the delivery dates, delivery locations, and quantities required to satisfy the terms of the project agreement.  In addition, this subclause shall specify the delivery media and any special instructions for packaging and handling.  The list of project deliverables may be incorporated into the document directly or by reference to an external document such as a Contract Data Requirements List (CDRL) or a Product Parts List (PPL).

The deliverables for each increment of the RBC system will be documented in build plans.  The build plan for each increment is tailored from the Project Build Plan Template, reference (b), and serves as a contract between the SYSCOM Communications Security Office and the RBC project on the content and acceptance criteria for each build of the RBC system.

### 1.1.4	Master Schedule and Budget Summary

IEEE Std 1058-1998 Guidance

(Subclause 1.1.4) Schedule and budget summary

This subclause shall provide a summary of the schedule and budget for the  project.  The level of detail should be restricted to an itemization of the major work activities and supporting processes as, for example, those depicted by the top level of the work breakdown structure.

The SYSCOM Communications Security Office has established a Master Build Schedule as depicted in Figure 1-2.  Fiscal year budget allocations are contained in Table 1-1.  The supporting Work Breakdown Structure (WBS), cost, schedule, and staffing requirements for the each increment of the Master Build Schedule are contained in Section 5.2 and Appendix A.

Figure 1-2.  Master Build Schedule

TABLE 1-1.  RBC Program Budget

| Fiscal Year | 1st QTR | 2nd QTR | 3rd QTR | 4th QTR |
| --- | --- | --- | --- | --- |
| 2002 |  |  | $0.50M | $0.50M |
| 2003 | $0.65M | $0.80M | $0.80M | $0.80M |
| 2004 | $0.80M | $0.80M | $0.80M | $0.80M |
| 2005 | $1.20M | $1.20M | $1.20M | $1.20M |
| 2006 | $1.00M | $1.00M | $1.00M | $1.00M |
| 2007 | $0.70M | $0.70M |  |  |

## 1.2	Evolution of the Plan

IEEE Std 1058-1998 Guidance

(Subclause 1.2) Evolution of the Plan

This subclause shall specify the plans for producing both scheduled and unscheduled updates to this planning document.  Methods of disseminating the updates shall be specified.  This subclause shall also specify the mechanisms used to place the initial version under configuration management and to control subsequent changes to the planning document.

The initiation, planning, control, and execution of the RBC project will follow the guidance of the SSC San Diego Project Management Guide, reference (c).  This PMP, implementing the guidance of reference (c), has been tailored in format and content from the Institute of Electrical and Electronics Engineers (IEEE) Standard for Software Project Management Plans, IEEE Standard1058-1998, reference (d).  Additional guidance is drawn from the Standard for Information Technology - Software Life Cycle Processes, IEEE/Electronic Industries Association (EIA) 12207 Series, reference (e); Systems Engineering – System Life Cycle Processes, International Organization for Standardization (ISO)/International Electrotechnical Commission (IEC) 15288, reference (f); and Processes for Engineering a System, Electronic Industries Alliance (EIA) Standard 632, reference (g).  To ensure application of the Systems/Software Engineering Management policy defined in reference (h), the PMP is maintained in accordance with reference (a), and through the tailoring of the Project Management Plan Template, reference (i).

The purpose of this PMP is to provide a documented plan for the management and control of the organizational, developmental, and supporting processes necessary to the successful implementation of the RBC Project.  To that end the PMP is considered to be a living document.  As such it is subject to revision based on programmatic events as typified by a sudden changes in project or product requirements, the encounter of risk events, or unexpected deviation from the planned course of action.  Revisions to the plan will follow reference (a) and the RBC Configuration Management Plan, Appendix G.

## 1.3	Document Structure

General Guidance

This section has been added to the template to help provide the reader of the final planning document an understanding of the structure and content of the document without having to reference the IEEE Std 1058-1998.

This plan is organized as follows:

- Section 1, Project Overview.  This section provides an overview of the scope and objectives of the project, the project’s assumptions and constraints, reference to the project deliverables, schedule and budget, and a description of the evolution of the plan.

- Section 2, References.  This section provides a list of all documents, policies, templates, processes, and other sources of information referenced in the plan.

- Section 3, Definitions.  This section contains the abbreviations and acronyms required to properly understand this planning document.

- Section 4, Project Organization.  This section identifies interfaces to organizational entities external to the project, the project’s internal organizational structure, and defines roles and responsibilities for the project.

- Section 5, Management Process.  This section describes the planning, measurement, tracking, reporting, risk control mechanisms needed to provide management control over the technical processes and product quality, and appropriate project initiation and closeout procedures.

- Section 6, Technical Process.  This section describes the technical solution in terms of a process model and implementation methods, tools, and techniques to be used to develop the various work products, plans for establishing and maintaining the project infrastructure, and the product acceptance.

- Section 7, Supporting Processes.  This section describes processes that are employed to facilitate and control the technical processes and the state of the product.  These include, but are not limited to, configuration management, verification and validation, documentation, quality assurance, reviews and audits, problem resolution, and contractor management, and methods to ensure continuous process improvement.

- Section 8, Additional Plans.  This section addresses the logistic support strategy to be applied to increase the system’s operational effectiveness.

- Appendix A.  RBC Master Schedule (Microsoft Project)

- Appendix B.  RBC Facilities Plan

- Appendix C.  RBC Project Training Plan

- Appendix D.  RBC Measurement Plan

- Appendix E.  RBC Product Engineering and Qualification Process

- Appendix F.  RBC Quality Assurance Plan

- Appendix G.  RBC Configuration Management Plan

This page intentionally left blank.

# SECTION 2.  REFERENCES

IEEE Std 1058-1998 Guidance

(Clause 2) References

This clause shall provide a complete list of all documents and other sources of information referenced in the document.  Each document should be identified by title, report number, date, author, path/name for electronic access, and publishing organization.  Other sources of information, such as electronic files, shall be identified using unique identifiers such as date and version number.  Any deviations from referenced standards or policies shall be identified and justifications shall be provided.

## 2.1	Standards and Documents

The standards and documents listed below are referenced in this document:

- A Description of the SSC San Diego Standard Process Assets (SPA), PR-OPD-35, SSC San Diego

- Project Build Plan Template, TM-PP-02, SSC San Diego

- SSC San Diego Project Management Guide, PR-OPD-29, SSC San Diego

- Institute of Electrical and Electronics Engineers (IEEE) Standard for Software Project Management Plans, IEEE Standard 1058-1998, IEEE, December 1998

- Standard for Information Technology - Software Life Cycle Processes, IEEE/Electronic Industries Association (EIA) 12207 Series, IEEE/ EIA, March 1998

- Systems Engineering – System Life Cycle Processes, International Organization for Standardization (ISO)/International Electrotechnical Commission (IEC) 15288, ISO/IEC 15288:2002(E), Nov 2002

- Processes for Engineering a System, Electronic Industries Alliance (EIA) Standard 632, ANSI/EIA-632-1998, January 1999

- Systems/Software Engineering Management Policy, DC-OPD-09, SSC San Diego

- Project Management Plan Template, TM-PP-01, SSC San Diego

- Incremental Life Cycle Schedule Template, TM-SPP-06, SSC San Diego

- SSC San Diego Training Program Process, PR-OT-01, SSC San Diego

- Department/Project Training Plan Template, TM-TP-01, SSC San Diego

- Measurement and Analysis Process (Expert Mode), PRX-MA-01, SSC San Diego

- Software Measurement Plan Template, TM-SPTO-03, SSC San Diego

- Requirements Management Guidebook, Naval Air Systems Command, September 1998

- Risk Management Process, PR-SPP-04, SSC San Diego

- Product Engineering and Qualification Process, PR-TS-01, SSC San Diego

- Software Test Planning and Management Guide, PR-SPE-03, SSC San Diego

- Configuration Management Process, PR-CM-01, SSC San Diego

- Configuration Management Plan Template, TM-CM-01, SSC San Diego

- Quality Assurance Process, PR-PPQA-01, SSC San Diego

- Quality Assurance Plan Template, TM-PPQA-01, SSC San Diego

- Integrated Software Management/Software Product Engineering/Inter-group Coordination Implementation Guide, PR-ISM-02, SSC San Diego

- Contractor Acquisition and Performance Monitoring Process, PR-SAM-01, SSC San Diego

- Decision Analysis and Resolution Process (Expert Mode), PRX-DAR-01, SSC San Diego

- Designing and Assessing Supportability in DoD Weapon Systems – A Guide to Increased Reliability and Reduced Logistics Footprint, Office of the Secretary of Defense (OSD), May 2003

## 2.2	Deviations and Waivers

Deviations and/or waivers from reference (h), or the project’s documented standard processes or procedures will be defined in the individual build plans as necessary and approved by agreement between the project manager and the program manager.

# SECTION 3.  DEFINITIONS

IEEE Std 1058-1998 Guidance

(Clause 3)  Definitions

This clause shall define, or provide references to, documents containing the definition of all terms and acronyms required to properly understand this planning document.

The abbreviations and acronyms used throughout this document are listed below:

ACWP	Actual Cost of Work Performed

AD	Architectural Design

BCC	Black Controller CSCI

BCWP	Budgeted Cost of Work Performed

BCWS	Budgeted Cost of Work Scheduled

CDRL	Contract Data Requirements List

CM	Configuration Management

COR	Contracting Officer's Representative

CSCI	Computer Software Configuration Item

CT	Code and Unit Test

C4I	Command, Control, Communications, Computers, and Intelligence

DBDD	DataBase Design Description

DCR	Document Change Request

DD	Detailed Design

DID	Data Item Description

DoN	Department of the Navy

EIA	Electronic Industries Association or Alliance

HWCI	Hardware Configuration Item

IEEE	Institute of Electronics and Electrical Engineers

IPR	In-Process Review

IR	Information Repository

IRS	Interface Requirements Specification

IT	Integration Test

IV&V	Independent Verification and Validation

LCCB	Local Configuration Control Board

MCS	Management Control System

MENS	Mission Element Needs Statement

MIL-STD	Military Standard

OPNAV	Office of the Chief of Naval Operations

OPTEVFOR	Operational Test and Evaluation Force

PAL	Process Asset Library

P/CR	Problem/Change Report

PE&Q	Product Engineering and Qualification

PM 	Project Manager

PMP	Project Management Plan

PPL	Product Parts List

PRP	Procurement Requirements Package

QA	Quality Assurance

QT	Qualification Test

RBC	Red/Black Controller

RCC	Red Controller CSCI

RA	Requirements Analysis

RD	Requirements Definition

RM	Requirements Management

SCCB	System Configuration Control Board

SCM	Software Configuration Management

SCR	System Change Request

SDD	Software Design Description

SDF	Software Development File

SDL	Software Development Library

SEN	Software Engineering Notebook

SEPG	Systems Engineering Process Group

SEPO	Systems Engineering Process Office

SMP	Software Measurement Plan

SOE	System Operational Effectiveness

SOW	Statement of Work

SPA	Software Process Assets document

SPAWAR	Space and Naval Warfare

SPI	Systems Process Improvement

SPP	Software Project Planning

SPTO	Software Project Tracking and Oversight

SQA	Software Quality Assurance

SQT	System Qualification Test

SRS	Software Requirements Specification

SSC	SPAWAR Systems Center

STD	Software Test Description

STP	Software Test Plan

SYSCOM	Systems Command

T&E	Test and Evaluation

TRB	Technical Review Board

VPO	Virtual Project Office

WBS	Work Breakdown Structure

# SECTION 4.  PROJECT ORGANIZATION

## 4.1	External Interfaces

IEEE Std 1058-1998 Guidance

(Subclause 4.1) External interfaces

This subclause shall describe the organizational boundaries between the project and external entities.  This should include, but is not limited to, the following: the parent organization, the acquiring organization, subcontracted organizations, and other organizational entities that interact with the project.  Representations such as organizational charts and diagrams may be used to depict the project’s external interfaces.

External organizational interfaces and the chain-of-command for the RBC Project are defined in Figure 4-1. Organizational entities in italics are located within the SSC San Diego complex.

Figure 4-1.  RBC Project External Organizational Interfaces

The responsibilities of the organizational entities and key positions shown in Figure 4-1 are defined in Table 4-1.

TABLE 4-1.  Programmatic Roles and Responsibilies

| POSITION | ROLES/RESPONSIBILITIES |
| --- | --- |
| Sponsor | Office of the Chief of Naval Operations (OPNAV)-level organization providing Mission Element Need Statement (MENS) and Department of the Navy (DoN) budget. |
| Systems Command (SYSCOM) Communications Security Office | SYSCOM-level organization tasked by OPNAV to perform system acquisition to meet the MENS for secure communication systems. |
| Program Manager | SYSCOM-level manager within the Communications Security Office assigned responsibility to direct total RBC system acquisition (hardware/software). |
| System Configuration Control Board (SCCB) | SYSCOM-level board responsible for the RBC system configuration (hardware/software). |
| Operational Test and Evaluation Force (OPTEVFOR) | OPTEVFOR is the Navy's sole independent agency for operational test and evaluation. OPTEVFOR is responsible to OPNAV for the evaluation of a system's ability to meet the MENS. |
| Independent Verification and Validation (IV&V) Organization | Program-level organization charged with the responsibility of providing resources and management for IV&V functions. Organized such that they report to the Program Manager through a chain of command separate from SSC San Diego’s. |
| SSC San Diego Senior Management | A senior manager (i.e., Executive Director, Department Head, or possibly a Division Head) providing infrastructure resources (e.g., facilities, admin, contracting, supply) to support an internal entity such as a development/maintenance organization for the RBC Project. |
| System Test Organization | Organizational entity charged with system-level acceptance testing. Reports directly to the SYSCOM Communications Security Office. |
| System Test Manager | Office within the System Test Organization charged with responsibility for RBC system testing. Answers directly to the Program Manager. |
| RBC Project | SSC San Diego organizational entity managing a defined group of activities with the responsibility to meet one or more specific system objectives tasked by the Program Manager. The project has its own funding, accounting, and schedules. |
| RBC Project Manager | An SSC San Diego ‘manager’ responsible to the Program Manager and to SSC San Diego Senior Management for specific tasked RBC project objectives. |
| Systems Engineering Process Office (SEPO) | SSC San Diego’s organization responsible for facilitating systems and software engineering process improvement. |
| Department Systems Engineering Process Group (SEPG) | Professional staff providing Systems/Software Process Improvement (SPI) leadership to the SSC San Diego Department to which the RBC project is assigned. |
| Department SPI Agent | Representative from the SSC San Diego department to which the RBC project is assigned. The agent is responsible for co-ordination with SEPO for process improvement. |

## 4.2	Internal Structure

IEEE Std 1058-1998 Guidance

(Subclause 4.2) Internal structure

This subclause shall describe the internal structure of the project organization to include the interfaces among the units of the development team.  In addition, the organizational interfaces between the project and organizational entities that provide supporting processes, such as configuration management, quality assurance, and verification and validation, shall be specified in this subclause.  Graphical devices such as organizational charts or diagrams should be used to depict the lines of authority, responsibility, and communication within the project.

The RBC Project organizational structure internal to SSC San Diego is defined in Figure 4-2.

Figure 4-2.  RBC Project Internal Organizational Structure

### 4.2.1	The Project Manager

The RBC Project Manager (PM) has full authority and is responsible and accountable for all aspects of the projects assigned by the SYSCOM Communications Security Office.

4.2.1.1  Scope of Authority.  The RBC PM represents SSC San Diego on all issues within the RBC organization, including contractors, and subcontractors.  The RBC PM’s authority extends from initial planning though all aspects of the performance including technical direction of project personnel.  The RBC PM has full authority over the technical managers and direct access to SSC San Diego senior management to acquire and commit the necessary resources to meet the requirements of any or all work assigned.  The RBC PM exercises complete and final authority over contract activities in accordance with SSC San Diego policies and procedures.  The RBC PM also has full authority over the contractors and implements this authority via formal contractual documents maintained by the SSC San Diego’s contract administrator and the respective Contracting Officer’s Representative (COR).

4.2.1.2  Scope of Responsibility.  The RBC PM is accountable to the SYSCOM Communications Security Office, for the conduct of the assigned projects including contractor efforts.  The PM is the SYSCOM Communications Security Office’s Point-of-Contact for all issues related to the RBC system.  The RBC PM directs the Administrative Office staff in the performance of assigned responsibilities.

4.2.1.3  Internal Responsibilities.  The RBC PM is responsible for all technical, quality, cost and schedule aspects of the tasks assigned in the current SYSCOM Communications Security Office Statement of Work (SOW).  The RBC PM will establish and approve a schedule showing major activities needed to establish full RBC system capability in accordance with Figure 1-2.   General responsibilities are listed below:

- Approve all cost and schedule-related planning documents.

- Approve all organizational work and WBS.

- Control or delegate control of all organizational resources.

- Establish organizational budgets.

- Establish organizational policies.

- Appoint and evaluate all technical managers.

- Monitor and report all project performance including the approval of monthly progress reports and cost summary reports.

- Evaluate trade-offs prior to major decisions and approve any deviations to approved plans.

- Assist group managers in choosing alternative courses of action to resolve problems.

- Identify project issues requiring formally documented decision analysis and resolution,

- Monitor and assure that all corrective actions are completed in the specified time.

- Assume the chair for the Local Configuration Control Board (LCCB)

4.2.1.4  External Responsibilities.  The RBC PM is the principal point of contact for maintaining liaison with the SYSCOM Communications Security Office, coordinating and supporting meetings, conducting program reviews, supporting the COR, approving all deliverables and managing all subcontractor activity.  The RBC PM attends all program meetings and assures the attendance of the required key personnel.  The RBC PM reviews and approves all deliverable work products at critical in-process junctures as well as at completion.

## 4.3	Project Roles and Responsibilities

IEEE Std 1058-1998 Guidance

(Subclause 4.3) Roles and responsibilities

This subclause shall identify and state the nature of each major work activity and supporting process and identify the organizational units that are responsible for those processes and activities.  A matrix of work activities and supporting processes vs. organizational units may be used to depict project roles and responsibilities.

The RBC project roles and responsibilities, including, but not limited to, the positions shown in Figure 4-2, are defined in Table 4-2.

TABLE 4-2.  Project Roles and Responsibilities

| POSITION | ROLES/RESPONSIBILITIES |
| --- | --- |
| RBC Project Manager | An SSC San Diego ‘manager’ responsible to the Program Manager for specific tasked system objectives. For the RBC project, the Project Manager acts as the LCCB chairperson and the Risk Manager. As Risk Manager, the PM coordinates risk identification, assessments, contingency planning, and the maintenance of the risk database. |
| Local Configuration Control Board (LCCB) | Project Manager’s project-level configuration control board controlling the configurations. Interfaces with and is subordinate to the SCCB. The Project Manager serves as the LCCB Chair. |
| Project SPI Lead | Project member who facilitates the project’s process improvement effort, collecting measurements and reporting status of the effort to the Project Manager and the Dept SPI Agent. |
| Administrative Office | The Project Manager’s administrative and financial support staff whose responsibilities include budget tracking, purchasing, and various contract items. |
| Contracting Officer’s Representative (COR) | Office responsible for compliance of RBC contracts to SSC San Diego and DoN acquisition regulations. Performs contract oversight. |
| Technical Managers | Collective name for the Project Manager’s technical supervisory team comprised of the Development Manager, T&E Manager, CM Manager, and QA Manager. |
| Technical Review Board (TRB) | A working group chartered to resolve both programmatic and technical issues and to submit recommendations to the Project Manager. |
| Development Manager | An organizational technical manager responsible for product development, who reports to the Project Manager. |
| Development Group | Collective name of the engineering staff responsible for RBC product development. |
| Requirements Team | Staff responsible for the management of the RBC requirements database. |
| Design Team | Staff responsible for the RBC architecture and design. |
| Implementation Team | Staff responsible for code, and/or reuse component selection, and unit test. |
| Test and Evaluation (T&E) Manager | An organizational technical manager, responsible for CSCI and Integration T&E, who reports to the Project Manager . |
| T&E Group | Collective name of the engineering staff responsible for CSCI integration and testing. |
| CSCI Test Team | Engineering staff responsible for internal CSCI Testing. |
| Integration Test Team | Engineering staff responsible for internal CSCI/Hardware Configuration Item (HWCI) Testing. |
| Delivery Team | Engineering staff responsible for on-site deliveries, training, and testing. |
| Configuration Management (CM) Manager | An organizational technical manager responsible for CM, who reports to the Project Manager. |
| CM Group | Collective name of the engineering staff responsible for CM functions. |
| Librarian | Member of engineering staff who is keeper of document and program baselines (check in/out) |
| Quality Assurance (QA) Manager | An organizational technical manager, responsible for QA functions, that reports to the Project Manager. |
| QA Group | Collective name of the engineering staff responsible for QA functions. |

This page intentionally left blank.

# SECTION 5.  MANAGEment PROCESS

## 5.1	Start-up

IEEE Std 1058-1998 Guidance

(Subclause 5.1) Project start-up plan

This subclause shall specify the estimation plan, staffing plan, resource acquisition plan, and training plan.  Depending on the size and scope of the project, these plans may be incorporated directly or by reference to other plans.

A SYSCOM Communications Security Office Task containing a build-specific SOW and funding information initiates project tasking for each incremental build of the RBC system at SSC San Diego.

### 5.1.1	Estimation

IEEE Std 1058-1998 Guidance

(Subclause 5.1.1) Estimation plan

This subclause shall specify the cost and schedule for conducting the project as well as methods, tools, and techniques used to estimate project cost, schedule, resource requirements, and associated confidence levels.  In addition, the basis of estimation shall be specified to include techniques such as analogy, rule of thumb, or local history and the sources of data.  This subclause shall also specify the methods, tools, and techniques that will be used to periodically re-estimate the cost, schedule, and resources needed to complete the project.  Re-estimation may be done on a monthly basis and/or periodically as necessary.

To develop RBC system build schedules, estimates are developed by using the Management Control System (MCS) cost-estimating tool cited in Section 5.3.  The Incremental Life Cycle Schedule Template, reference (j), is analyzed and tailored based on the estimate results.  The staffing requirements for each task are abstracted from the macro estimate and partitioned to the detailed entries of the Master Schedule, Appendix A.  Start and duration times, together with prerequisite and other timing data, are extracted from the estimate and input to the Microsoft Project plan to generate schedules.  The resulting schedules are then analyzed for reasonableness to ensure that they fit into a compliant overall schedule.  Results that are determined to be non-compliant are revised and then input back into the estimating process.

### 5.1.2	Staffing

IEEE Std 1058-1998 Guidance

(Subclause 5.1.2) Staffing plan

This subclause shall specify the number of staff required by skill level, the project phases in which the numbers of personnel and types of skills are needed, the source of personnel and the duration of need.  Resource Gantt charts, resource histograms, spreadsheets, and tables may be used to depict the staffing plan by skill level, by project phase, and by aggregations of skill levels and project phases.

Staffing for the RBC project will be comprised of a mix of the civil service personnel currently in place and contractor personnel acquired through an open competition for a support contract.  Overall staffing requirements and their allocation are defined paragraph 5.2.3.

### 5.1.3	Resource Acquisition

IEEE Std 1058-1998 Guidance

(Subclause 5.1.3) Resource acquisition plan

This subclause shall specify the plan for acquiring the resources in addition to personnel needed to successfully complete the project.  The resource acquisition plan should include a description of the resource acquisition process, including assignment of responsibility for all aspects of resource acquisition.  The plan should include, but not be limited to, acquisition plans for equipment, computer hardware and software, training, service contracts, transportation, facilities, and administrative and janitorial services.  The plan should specify the points in the project schedule when the various acquisition activities will be required.  Constraints on acquiring the necessary resources shall be specified.

Non-staff resource requirements and the means of acquisition are defined in the RBC Facilities Plan, Appendix B.

### 5.1.4	Staff Training

IEEE Std 1058-1998 Guidance

(Subclause 5.1.4) Project staff training plan

This subclause shall specify the training needed to ensure that necessary skill levels in sufficient numbers are available to successfully conduct the  project.  The training schedule shall include the types of training to be provided, numbers of personnel to be trained, entry and exit criteria for training, and the training method (e.g.,  lectures, consultations, mentoring, or computer-assisted training).  The training plan should include training as needed in both technical and managerial skills.

Personnel assigned to the RBC project are required to complete, or waive, technical training to enable them to carry out their assignments proficiently.  In addition, personnel newly assigned to the organization are required to familiarize themselves with both the project and the common processes used to support the RBC project.  The RBC Project Training Plan, Appendix C, was developed in accordance with the SSC San Diego Training Program Process, reference (k).  The process establishes the requirement for a Department/Project Training Plan.  The Department/Project Training Plan Template, reference (l), was tailored to develop Appendix C.

## 5.2	Work Planning

IEEE Std 1058-1998 Guidance

(Subclause 5.2) Work plan

This clause shall specify the work activities, schedule, resources, and budget details for the project.

The following paragraphs provide a working management plan for the acquisition of the RBC system.

### 5.2.1	Work Activities

IEEE Std 1058-1998 Guidance

(Subclause 5.2.1) Work activities

This subclause shall specify the various work activities to be performed in the project.  A work breakdown structure shall be used to depict the work activities and the relationships among work activities.  Work activities should be decomposed to a level that exposes all project risk factors and allows accurate estimate of resource requirements and schedule duration for each work activity.  Work packages should be used to specify, for each work activity, factors such as the necessary resources, estimated duration, work products to be produced, acceptance criteria for the work products, and predecessor and successor work activities.  The level of decomposition for different work activities in the work breakdown structure may be different depending on factors such as the quality of the requirements, familiarity of the work, and novelty of the technology to be used.

The WBS for the RBC Project is contained in Appendix A.  The WBS identifies the needed tasks, resource allocations, and cost estimates in a Microsoft Project format that was tailored from reference (j).  The individual builds have their own supporting Microsoft Project plans that provide roll-up data to the master Microsoft Project plan in Appendix A.  The build plans will be tailored from reference (b).  Issues requiring formally documented decision analysis and resolution are entered as discrete WBS tasks to ensure tracking.  Events requiring formally documented decision analysis include decisions on architectural design trade-offs, supplier selection, resolution of high risk issues, commercial off-the-shelf product selection, support tool selection, and make-or-buy decisions.   The project manager specifies the decision analysis and resolution events.

### 5.2.2	Schedule Allocation

IEEE Std 1058-1998 Guidance

(Subclause 5.2.2) Schedule allocation

This subclause shall provide scheduling relationships among work activities in a manner that depicts the time-sequencing constraints and illustrates opportunities for concurrent work activities.  Any constraints on scheduling of particular work activities caused by factors external to the project shall be indicated in the work activity schedule.  The schedule should include frequent milestones that can be assessed for achievement using objective indicators to assess the scope and quality of work products completed at those milestones.  Techniques for depicting schedule relationships may include milestone charts, activity lists, activity Gantt charts, activity networks, critical path networks, and PERT.

Figure 5-1 allocates development activities within the individual builds identified in Figure 1-2.  Each build will be addressed in more detail in the build plan identifying the individual build’s requirements, schedule, resources, and acceptance criteria.  The development activities included in Figure 5-1 are Requirements Analysis (RA), Architectural Design (AD), Detailed Design (DD), Code and Unit Test (CT), Integration Test (IT), and Qualification Test (QT).

Note that RA and AD are conducted during a common schedule phase.

### 5.2.3	Resource Allocation

IEEE Std 1058-1998 Guidance

(Subclause 5.2.3) Resource allocation

This subclause shall provide a detailed itemization of the resources allocated to each major work activity in the project work breakdown structure.  Resources shall include the numbers and required skill levels of personnel for each work activity.  Resource allocation may include, as appropriate, personnel by skill level and factors such as computing resources, tools, special testing and simulation facilities, and administrative support.  A separate line item should be provided for each type of resource for each work activity.  A summary of resource requirements for the various work activities should be collected from the work packages of the work breakdown structure and presented in tabular form.

Required staffing allocations by development phase are defined in Table 5-1.  The table provides guidance for staff allocations for the overall project.  Facilities resources, including floor space, lab configuration, hardware, and tool requirements are defined in the RBC Facilities Plan, Appendix B.

Figure 5-1.  RBC Project Schedule Allocations

TABLE 5-1.  Staff Resources by Development Phase

| Labor Category | RA & AD | DD | CT | IT & QT |
| --- | --- | --- | --- | --- |
| Project Manager | 1 | 1 | 1 | 1 |
| Systems Engineer | 1 | 1 | 1 | 1 |
| Hardware Engineer | 1 | 1 | 1 | 1 |
| Software Engineer | 5 | 7 | 7 | 5 |
| CM Specialist | 2 | 2 | 2 | 2 |
| QA Specialist | 1 | 1 | 1 | 1 |
| Senior Test Engineer | 1 | 1 | 1 | 1 |
| Test Engineer | 2 | 2 | 2 | 2 |
| Facilities Administrator | 1 | 1 | 1 | 1 |
| Hardware installation specialist | 1 | 1 | 1 | 1 |
| Subtotals | 16 | 18 | 18 | 16 |

### 5.2.4	Budget Allocation

IEEE Std 1058-1998 Guidance

(Subclause 5.2.4) Budget allocation

This subclause shall provide a detailed breakdown of necessary resource budgets for each of the major work activities in the work breakdown structure.  The activity budget shall include the estimated cost for activity personnel and may include, as appropriate, costs for factors such as travel, meetings, computing resources, tools, special testing and simulation facilities, and administrative support.  A separate line item shall be provided for each type of resource in each activity budget.  The work activity budget may be developed using a spreadsheet and presented in tabular form.

Table 5-2 presents the RBC project budget and allocates the funding to the individual builds and their development activities.

TABLE 5-2.  RBC System Build Budget Allocation

| Build | Phase | Budget (K$) |  |
| --- | --- | --- | --- |
| Build 01 |  |  |  |
|  | RA | $ 552 |  |
|  | AD | $ 2,016 |  |
|  | DD | $ 737 |  |
|  | CT | $ 799 |  |
|  | IT and QT | $ 1,106 |  |
|  | Total | $ 5,210 | $ 5,210 |
| Build 02 |  |  |  |
|  | RA | $ 300 |  |
|  | AD | $ 209 |  |
|  | DD | $ 1,432 |  |
|  | CT | $ 1,551 |  |
|  | IT and QT | $ 2,148 |  |
|  | Total | $ 5,640 | $ 5,640 |
| Build 03 |  |  |  |
|  | RA | $ 300 |  |
|  | AD | $ 233 |  |
|  | DD | $ 1,601 |  |
|  | CT | $ 1,734 |  |
|  | IT and QT | $ 2,401 |  |
|  | Total | $ 6,269 | $ 6,269 |
|  |  | Project Total | $17,119 |

## 5.3	Project Controls

IEEE Std 1058-1998 Guidance

(Subclause 5.3) Control plan

This subclause shall specify the metrics, reporting mechanisms, and control procedures necessary to measure, report, and control the product requirements, the project schedule, budget, and resources, and the quality of work processes and work products.  All elements of the control plan should be consistent with the organization’s standards, policies, and procedures for project control as well as with any contractual agreements for project control.

The SYSCOM Communications Security Office provides direction to SSC San Diego through formally established Plans Of Action and Milestones, memoranda, and SYSCOM Communications Security Office Tasks.  The SSC San Diego RBC Project organization provides current status to the SYSCOM Communications Security Office through the reviews, audits, reports, and working interchanges established for the program.  The key factors that contribute to the SSC San Diego RBC Project management are the processes of planning, scheduling, performance measurement, risk mitigation, variance analysis, and corrective action.  Under the direction of the PM, the technical managers develop detailed plans based on established work assignments for specific projects.  The MCS tools are used to document and track the work against major program milestones and provide work performance measurement against costs incurred.  To ensure the necessary level of tracking and oversight and the application of reference (h), the RBC Measurement Plan (SMP), Appendix D, was developed in accordance with the Measurement and Analysis Process (Expert Mode), reference (m), and through the tailoring of the Software Measurement Plan Template, reference (n).  The RBC SMP includes periodic reviews, monthly status reports, and audits.  Periodic reviews are conducted to assess the risks, to initiate risk analysis, and to establish risk mitigation methods.  Quality Assurance's (QA) function is to ensure that these transactions are fully recorded and traceable though the project life.  Deviations from the baseline cost and schedule data are subjected to variance analysis.  Corrective action items are documented for each significant variance.  Corrective action items are established, logged, and tracked until successfully resolved.  Directives are issued through the formal planning, scheduling, and communications media.

The MCS tools, supported by the WBS, permit cost, schedule, performance and quality to be reviewed at any level.  Table 5-3 identifies the primary tools that support program management and are part of the MCS.

TABLE 5-3.  Management Control System Elements

| Tool | Description | Production Control | Resource Mgmt | Cost Mgmt | Schedule Mgmt |
| --- | --- | --- | --- | --- | --- |
| COSTAR | Cost Estimating |  | x | x | x |
| Microsoft Project | Plans/Tracking |  | x | x | x |
| Microsoft Excel | Plans/Tracking |  | x | x | x |
| Microsoft Powerpoint | Documentation | x | x | x | x |
| Microsoft Word | Documentation | x | x | x | x |
| Microsoft Access | P/CR and SCR Tracking | x |  |  |  |
| Microsoft Outlook | E-Mail | x | x | x | x |
| Requisite Pro | Requirements Mgmt | x |  |  |  |
| Risk Radar | Risk Tracking | x | x | x | x |

### 5.3.1	Requirements Control

IEEE Std 1058-1998 Guidance

(Subclause 5.3.1) Requirements control plan

This subclause shall specify the control mechanisms for measuring, reporting, and controlling changes to the product requirements.  This subclause shall also specify the mechanisms to be used in assessing the impact of requirements changes on product scope and quality, and the impacts of requirements changes on project schedule, budget, resources, and risk factors.  Configuration management mechanisms shall include change control procedures and a change control board.  Techniques that may be used for requirements control include traceability, prototyping and modeling, impact analysis, and reviews.

The Requirements Team is responsible for the RBC project requirement’s process.  The Requirements Team will develop a Requirements Management (RM) process based on database technology.  The team will establish the overall schema for the requirements database and for providing informal training, as required.  To ensure application of reference (h), the requirements management process will apply guidance from the Requirements Management Guidebook, reference (o).  The Requirements Team will enter requirements data into the database, and will produce requirements traceability matrices.  RA and subsequent Requirements Definition (RD) is performed in accordance with the requirements process described in the RBC Product Engineering and Qualification (PE&Q) Process, Appendix E to this document.  The allocation and baselining of requirements to individual builds is the responsibility of the LCCB.

Each technical manager will ensure the integrity of the requirements data entered and that requirement bi-directional traceability matrices are built for each major document (such as Software Requirements Specification (SRS), Interface Requirements Specification (IRS), Software Design Description (SDD), and for the test specifications including the Software Test Plan (STP), the Software Test Descriptions (STD), etc.).  As traceability matrices are produced, the Requirements Team will be able to determine whether all requirements for each phase of each build have been met.

### 5.3.2	Schedule Control

IEEE Std 1058-1998 Guidance

(Subclause 5.3.2) Schedule control plan

This subclause shall specify the control mechanisms to be used to measure the progress of work completed at the major and minor project milestones, to compare actual progress to planned progress, and to implement corrective action when actual progress does not conform to planned progress.  The schedule control plan shall specify the methods and tools that will be used to measure and control schedule progress.  Achievement of schedule milestones should be assessed using objective criteria to measure the scope and quality of work products completed at each milestone.

The following paragraphs define the management approach for schedule control of the RBC Project.

5.3.2.1  Schedule Tracking.  Progress is charted on a monthly basis.  Schedule performance data is generated at the task level and compared to the proposed schedule.  Reports are generated that provide data on performance-to-date and projected future performance.  In addition, deviations of both current and future milestones from proposed milestone dates are flagged.  The actual start dates, completion dates, task completion percentages based on earned value algorithms, and actual dollar amounts expended on each task are entered into the Microsoft Project plan for each product component and the project overall.

5.3.2.2  Schedule Performance Reports.  Schedule status information is measured against the required schedule dates, and reports on performance-to-date and projected future milestone dates are made.  Deviations of "to-date" and "future-milestone-dates" from "required-dates" are flagged.  Using MS Project for each product component, the Administrative Office generates variance analysis reports by comparing Actual Cost of Work Performed (ACWP), Budgeted Cost of Work Scheduled (BCWS), Budgeted Cost of Work Performed (BCWP), and Estimate at Completion.

5.3.2.3  Schedule Reviews.  QA reports and Configuration Management (CM) status accounting reports are reviewed in relationship with the schedule performance reports at multiple detail levels and timing intervals to provide management early visibility into potential schedule problems and/or schedule risks.

At each review level, schedule problems and/or risks are identified.  If an actual problem (schedule variance) occurs, a problem resolution analysis is made to include: problem severity, schedule impact (domino effect), possible resolutions, and risk associated with each alternative.

Depending upon the reviewer's authority level and the nature of the required corrective action, the reviewer either directs corrective action or recommends corrective action to a higher authority level.  This process applies to all contractor activities as well.

5.3.2.4  Progress Variance Monitoring.  Actual progress can differ from the planned progress for many reasons.  The technical managers have the responsibility to identify schedule deviation causes and trends at the task level and correct the deviations.  Deviations that are beyond a technical manager’s capabilities to resolve are brought to the PM’s attention.

5.3.2.5  Progress Variance Resolution.  Once a schedule variance is identified and quantified, management has several options from which to choose for deviation resolution.  Depending on the cause of the deviation, the action may be resource reallocation, rescheduling the task or set of tasks, or correcting a performance problem.

5.3.2.6  Follow-Up on Corrective Action.  The MCS tools are used to both identify the initial schedule deviation and to analyze the corrective action results.  Corrective action items are closely monitored to ensure that they are effectively recovering the schedule variance before milestones or the master schedule are jeopardized.

### 5.3.3	Budget Control

IEEE Std 1058-1998 Guidance

(Subclause 5.3.3) Budget control plan

This subclause shall specify the control mechanisms to be used to measure the cost of work completed, compare planned cost to budgeted cost, and implement corrective action when actual cost does not conform to budgeted cost.  The budget control plan shall specify the intervals at which cost reporting will be done and the methods and tools that will be used to manage the budget.  The budget plan should include frequent milestones that can be assessed for achievement using objective indicators to assess the scope and quality of work products completed at those milestones.  A mechanism such as earned value tracking should be used to report the budget and schedule plan, schedule progress, and the cost of work completed.

The following paragraphs define the management approach for budget control of the RBC Project.

5.3.3.1  Cost Management.  To ensure that the PM has the control necessary to accomplish the project objectives, the Administrative Office is assigned total budget tracking responsibility.  The PM delegates specific cost management duties to his Administrative Office staff while retaining review and approval authority for all cost-related efforts.

The primary building block within the methodology is the WBS as detailed in the project’s Microsoft Project Plan as derived from the organization’s standard Microsoft Project plan template, reference (j), or the Enterprise Resource Planning WBS Template.  The cost estimating tool of the MCS is used for the cost estimating process while Microsoft Project is used for tracking the project costs.

Once a valid cost baseline is established, detailed schedules are utilized to provide visibility and to be the basis for establishing the cost of work performed.  This determination is supplied monthly to establish measurement points for cost and schedule adherence.  To ensure immediate and appropriate attention, cost and schedule variances are automatically triggered for review in the integrated review process.

5.3.3.2  Methods to Ensure Cost Adherence.  Management of costs and risks is a focal point of the cost adherence plan.  A comprehensive set of processes, tools, and practices is coupled with contingency planning to ensure that costs and risks are closely monitored and controlled.

5.3.3.3  Cost Control.  Cost management methodology utilizes the MCS tools to track and measure the cost of work being performed.  Deviations are highlighted for immediate management attention.  Group  managers employ input in the form of cost and completion percentages via monthly management reports to develop a BCWP.  This is a measure of budget adherence that is used to determine where management attention must be focused.

5.3.3.4  Contractor Cost Control.  Cost management practices for contractors include formal methods for monitoring and controlling contractor cost performance and minimizing risk.  Specific contractor tasks are identified and are detailed in the appropriate Microsoft Project plan.  Enforced flow-down of technical, schedule, and contractual requirements is incorporated into individual statements of work in each delivery order.  Contract management has been given the dual responsibility of ensuring that 1) lines of communication remain open for the exchange of information and 2) negotiated agreements are not compromised.

The RBC Project uses a review and reporting system that requires contractor evaluation and is consistent with contracting requirements.  A monthly contractor’s status report including any variances in cost, schedule, or technical performance will be included in the monthly program reviews.  The same problem identification and resolution procedures used by the CM Group are extended to the subcontractor, to ensure management visibility and to guarantee that proper and prompt attention is given to risk management and reduction on a program-wide basis.

The technical managers manage the contractor costs directly.  They are chartered with the responsibility of monitoring contractor costs and schedules for adherence to budget.  They will report directly to the PM and the COR, thus ensuring that the PM will have immediate insight into all contractor cost control.

5.3.3.5  Cost Variance Measurement.  The MCS is the vehicle for tracking cost variances.  At the start of a project, or a baseline revision, WBS levels are entered into a Microsoft Project plan and baselined to form the framework for cost-variance measurement.

Milestones are monitored, and noted variances reviewed to determine program impact and establish corrective action items.  Corrective action items are tracked to completion.  Out-of-tolerance variances are assessed to the responsible technical manager and reviewed with the PM.  Internal cost and schedule reviews are held for the duration of the effort.  Reviews assess cost trends and analyze cost and schedule variances, with variances determined by comparing elements of BCWP against ACWP and BCWS.  If a variance reaches a predetermined threshold, as defined in the risk management database, it is brought to the immediate attention of the responsible technical manager for assessment and formulation of corrective action.  Threshold limits are set by the PM and documented in the related risk management database entries and adjusted, as appropriate, based on trend analysis and risk identification.  Variances, either positive or negative, are automatically triggered and raised for analysis.

5.3.3.6  Cost Variance Corrective Action.  Periodically, the PM conducts a formal program review to communicate costs, schedule, and status.  Variances are graphed and utilized to describe specific cost variances (positive or negative) that are greater than PM’s established thresholds for the task-to-date.  For each variance, the PM either approves the recommended corrective action or directs that further analysis/planning is to be done and reported on within a week.  In this manner, all cost variances are immediately acted upon before they are allowed to become significant.

Once a variance has been identified and quantified, the PM has a number of options from which he or she may choose to correct the problem.

In all cases, the PM maintains total control over the resolution of the problem.  If either the problem or the corrective action taken constitutes a program risk, the risk is quantified, minimized as much as possible, and added to the risk management database along with its contingency actions.

Since it is possible that some cost problems cannot be rectified from within the SSC San Diego RBC Project resources, the PM may also elect to draw upon the significant resources of other SSC San Diego or sponsor organizations.

### 5.3.4	Quality Control

IEEE Std 1058-1998 Guidance

(Subclause 5.3.4) Quality control plan

This subclause shall specify the mechanisms to be used to measure and control the quality of the work processes and the resulting work products.  Quality control mechanisms may include quality assurance of work processes, verification and validation, joint reviews, audits, and process assessment.

The QA Group under the direction of the QA Manager provides the PM with the assurance that all quality and production control requirements are being accomplished.  The QA Manager also provides oversight for the conduct of audits (e.g., Functional Configuration Audit/Physical Configuration Audit) and reviews to assure that all performance and contractual requirements are met and integrated into the deliverable baseline.  In performing these duties, the QA Manager monitors adherence to all applicable policies, processes, procedures, and plans through the delegation of responsibilities to the QA Group.  QA will be performed in accordance with the RBC Quality Assurance Plan in Appendix F.

### 5.3.5	Project Reporting and Communication

IEEE Std 1058-1998 Guidance

(Subclause 5.3.5) Reporting plan

This subclause shall specify the reporting mechanisms, report formats, and information flows to be used in communicating the status of requirements, schedule, budget, quality, and other desired or required status metrics within the project and to entities external to the project.  The methods, tools, and techniques of communication shall be specified in this subclause.  The frequency and detail of communications related to project measurement and control shall be consistent with the project scope, criticality, risk, and visibility.

The following paragraphs define the management plan for ensuring the broadest communication of needed information for project coordination.

5.3.5.1  Electronic Media.  RBC project personnel will make appropriate and considerable use of e-mail and the RBC Virtual Project Office (VPO) site to assist in distribution and review of documents, memoranda, presentations, schedules, action items, and requests for information.  The VPO is for “internal” use, and is distinct from the RBC Information Repository.

5.3.5.2  Meetings.  RBC project meetings will typically be multi-site meetings linked via telephone and Internet.  Conference call capabilities will be provided to allow audio participation, and Internet data link capabilities will be provided to allow visual presentations.

Net Meeting software will allow any participant to control visual presentations visible to all meeting sites using the underlying Internet links.  The RBC will use the RBC VPO site for presentation material to permit presentation review before and after the meeting.  Meeting minutes will be recorded, and action items listed and tracked to completion.

5.3.5.3  Information Repository.  The RBC Information Repository (IR) maintained at SSC San Diego provides a single secure location for reference documents, test reports, a reuse library, and related documentation.  It is the formal location for delivery of the RBC products to the end user.

5.3.5.4  Internal Reviews.  The RBC project holds In-Progress Reviews (IPRs) at least every third month for the purpose of monitoring internal progress towards milestones, reviewing problems encountered, presenting proposed resolutions, presenting near-term plans, reviewing risks and mitigation plans, and presenting a financial review using Earned Value data from Appendix A.

5.3.5.5  Status Reporting.  The RBC project provides monthly progress reports to the Program Manager summarizing work completed, a financial report, issues, meetings and conferences attended, and upcoming calendar events.

### 5.3.6	Metrics Collection

IEEE Std 1058-1998 Guidance

(Subclause 5.3.6) Metrics collection plan

This subclause shall specify the methods, tools, and techniques to be used in collecting and retaining project metrics.  The metrics collection plan shall specify the metrics to be collected, the frequency of collection, and the methods to be used in validating, analyzing, and reporting the metrics.

To ensure application of reference (h), Appendix D was developed in accordance with reference (m), and through the tailoring of the reference (n).

The RBC SMP outlines standard measurements to be collected by task areas within the RBC project.  Measurement requirements specific to each build will be defined in the applicable Project Build Plan and will roll up as overall project’s measurements for analysis.

## 5.4	Risk Management

IEEE Std 1058-1998 Guidance

(Subclause 5.4) Risk management plan

This subclause shall specify the risk management plan for identifying, analyzing, and prioritizing project risk factors.  This subclause shall also describe the procedures for contingency planning, and the methods to be used in tracking the various risk factors, evaluating changes in the levels of risk factors, and the responses to those changes.

Risk factors that should be considered include risks in the acquirer-supplier relationship, contractual risks, technological risks, risks caused by the size and complexity of the product, risks in the development and target environments, risks in personnel acquisition, skill levels and retention, risks to schedule and budget, and risks in achieving acquirer acceptance of the product.

To ensure application of reference (h), the risk management approach for the RBC project follows the guidance of the Risk Management Process, reference (p).  The strategy is to develop a risk management database to support a continuous risk assessment process following the guidance of reference (p).  The initial taxonomy of risk to be addressed is contained in Appendix A to reference (p).  The RBC project uses the Risk Radar tool for recording risks, their analysis, mitigation and contingency actions.  The database is placed under CM.  The RBC PM assumes the collateral duty as the Risk Manager for the project.  The RBC PM, in the role of Risk Manager, maintains the RBC Risk database, analyzes risk-related measurements, reviews individual database entries as needed at weekly status meetings with the technical managers, and holds a review of the database on quarterly schedule with the sponsor and other senior management as defined in Appendix A.

## 5.5	Project Closeout

IEEE Std 1058-1998 Guidance

(Subclause 5.5) Project closeout plan

This subclause shall contain the plans necessary to ensure orderly closeout of the project.  Items in the closeout plan should include a staff reassignment plan, a plan for archiving project materials, a plan for postmortem debriefings of project personnel, and preparation of a final report to include lessons learned and analysis of project objectives achieved.

At the direction of the SYSCOM Communications Security Office a transition plan with the format and content to be defined by the SYSCOM Communications Security Office, will be developed to manage and control transition of the RBC system to the designated Life Cycle Support Activity.

# SECTION 6.  TECHNICAL PROCESS

## 6.1	Process Model

IEEE Std 1058-1998 Guidance

(Subclause 6.1) Process model

This subclause shall define the relationships among major project work activities and supporting processes by specifying the flow of information and work products among activities and functions, the timing of work products to be generated, reviews to be conducted, major milestones to be achieved, baselines to be established, project deliverables to be completed, and required approvals that span the duration of the project.  The process model for the project shall include project initiation and project termination activities.  To describe the process model, a combination of graphical and textual notations may be used.  Any tailoring of an organization’s standard process model for a project shall be indicated in this subclause.

The Incremental Life Cycle Strategy of reference (e) is being tailored to the acquisition of the RBC system.  Figure 6-1 presents the fundamental process model employed by the RBC project to develop the RBC system.

Figure 6-1.  RBC Project Life Cycle Strategy

The flow of information and work products through the Development Process Activities is detailed in Appendix E.  The activities of the Supporting Processes and Organizational Processes are as defined in this PMP.

## 6.2	Methods, Tools and Techniques

IEEE Std 1058-1998 Guidance

(Subclause 6.2) Methods, tools, and techniques

This subclause shall specify the development methodologies, programming languages and other notations, and the tools and techniques to be used to specify, design, build, test, integrate, document, deliver, modify and maintain the project deliverable and non-deliverable work products.  In addition, the technical standards, policies, and procedures governing development and/or modification of the work products shall be specified.

The allocation of functional requirements for each build will be negotiated with the SYSCOM Communications Security Office’s System Configuration Control Board (SCCB) and documented in a Project Build Plan for each increment.  The Project Build Plan will also include build-specific acceptance criteria and installation/user training requirements.  To ensure application of reference (h), Appendix E was developed by tailoring the organization's Product Engineering and Qualification Process, reference (q), and applying the guidance of the Software Test Planning and Management Guide, reference (r).

Evidence of results of development activities will be deposited in Software Development Files (SDFs) and Software Engineering Notebooks (SENs).  The SDF and SEN contents and responsibility for their maintenance is described in the RBC Configuration Management Plan, Appendix G.  These artifacts, along with pertinent project data will be deposited and maintained in a Software Development Library (SDL) and made available to support management reviews, metrics calculations, quality audits, product evaluations, and preparation of product deliverables.  The SDL is a key component of the IR.

## 6.3	Project Infrastructure

IEEE Std 1058-1998 Guidance

(Subclause 6.3) Infrastructure plan

This subclause shall specify the plan for establishing and maintaining the development environment (hardware, operating system, network, and software), and the policies, procedures, standards, and facilities required to conduct the project.  These resources may include workstations, local area networks,  tools for analysis, design, implementation, testing, and project management, desks, office space, and provisions for physical security, administrative personnel, and janitorial services.

Appendix B specifies the plan for establishing and maintaining the development and test environments.  The resources addressed include the office and lab space, included workstations, local area networks, hardware/software tools, provisions for physical security, facilities management processes, and equipment maintenance contract data.

## 6.4	Product Acceptance

IEEE Std 1058-1998 Guidance

(Subclause 6.4) Product acceptance plan

This subclause shall specify the plan for acquirer acceptance of the deliverable work products generated by the project.  Objective criteria for determining acceptability of the deliverable work products shall be specified in this plan and a formal agreement of the acceptance criteria shall be signed by representatives of the development organization and the acquiring organization.  Any technical processes, methods, or tools required for product acceptance shall be specified in the product acceptance plan.  Methods such as testing, demonstration, analysis, and inspection should be specified in this plan.

The System Qualification Testing (SQT) is the SYSCOM Communications Security Office’s approved and witnessed series of tests that demonstrate compliance with the system-level requirements.  The SQT is the acceptance mechanism for the developer’s compliance with the terms of tasking by the SYSCOM Communications Security Office.

RBC SQT consists of complementary and progressive test phases.  A single SQT Test Plan will be generated by the System Test Organization, under the direction of a System Test Manager, to address the planning for all levels of SQT.  A Test Description will be generated for each product component, documenting the test procedures to be run to verify each requirement for that component.  A cross-reference matrix will be provided, using the project-wide requirements traceability database, to document the test or tests that satisfy each requirement.  A system-level Test Report will be generated for each product component, documenting the results of each product component test.  The System Test Organization is responsible for generating the appropriate test documentation.

This page intentionally left blank.

# SECTION 7.  SUPPORTING PROCESSES

## 7.1	Configuration Management

IEEE Std 1058-1998 Guidance

(Subclause 7.1) Configuration management plan

This subclause shall contain the configuration management plan for the  project, to include the methods that will be used to provide configuration identification, control, status accounting, evaluation, and release management.  In addition, this subclause shall specify the processes of configuration management to include procedures for initial baselining of work products, logging and analysis of change requests, change control board procedures, tracking of changes in progress, and procedures for notifying concerned parties when baselines are first established or later changed.  The configuration management process should be supported by one or more automated configuration management tools.

Appendix G was developed in accordance with the Configuration Management (CM) Process, reference (s).  The process establishes the requirement for a CM Plan that implements reference (h).  The CM Plan Template, reference (t), was tailored to develop Appendix G.

## 7.2	Independent Verification and Validation

IEEE Std 1058-1998 Guidance

(Subclause 7.2) Verification and validation plan

This subclause shall contain the verification and validation plan for the project to include scope, tools, techniques, and responsibilities for the verification and validation work activities.  The organizational relationships and degrees of independence between development activities and verification and validation activities shall be specified.  Verification planning should result in specification of techniques such as traceability, milestone reviews, progress reviews, peer reviews, prototyping, simulation, and modeling.  Validation planning should result in specification of techniques such as testing, demonstration, analysis, and inspection. Automated tools to be used in verification and validation should be specified.

For the RBC example, this section has been tailored to address the relationship between the RBC project and the sponsor’s Independent Verification and Validation Agent.  The RBC project processes supporting verification and validation activities as addressed in the IEEE Std 1058-1998 would be contained in Appendix E.

Processes for the Independent Verification and Validation (IV&V) of the RBC system are the responsibility of the IV&V agent illustrated in Figure 4-1.  The RBC PM is responsible for the conduct of supporting analysis and resolution as required by the IV&V organization and/or the sponsor in response to issues raised by the IV&V agent.

## 7.3	Documentation

IEEE Std 1058-1998 Guidance

(Subclause 7.3) Documentation plan

This subclause shall contain the documentation plan for the project, to include plans for generating non-deliverable and deliverable work products.  Organizational entities responsible for providing input information, generating, and reviewing the various documents shall be specified in the documentation plan.  The documentation plan should include a list of documents to be prepared, the controlling template or standard for each document, who will prepare it, who will review it, due dates for review copy and initial baseline version, and a distribution list for review copies and baseline versions.

Defining the documentation requirements in terms of associated standards, size, and the required reviews is important to both planning and clarifying the acquisition process.  Documentation is a key deliverable for the RBC system.  Table 7-1 defines the RBC project’s documentation plan.  The format standards listed in Table 7-1 are available on the SSC San Diego PAL at http://sepo.spawar.navy.mil/.  Documents related to the Development Process Activities of Figure 6-1 are referenced in the Appendix E.

TABLE 7-1.  RBC Project Documentation

| Document Type | Format Standard | Estimated Page Count | Peer Review Type |
| --- | --- | --- | --- |
| Project Management Plan | PMP Template | 50 | Formal Inspection |
| Configuration Management Plan | SCM Plan Template | 50 | Formal Inspection |
| Quality Assurance Plan | SQA Plan Template | 40 | Formal Inspection |
| Master Schedule (Microsoft Project) | MS Project Incremental Life Cycle Schedule Template | 10 | Technical Review |
| Measurement Plan | SMP Template | 25 | Formal Inspection |
| Facilities Plan | Project Defined | 40 | Formal Inspection |
| Training Plan | Training Plan Template | 15 | Technical Review |
| Product Engineering and Qualification Process | PE&Q Process Template | 35 | Formal Inspection |
| Build Plan (3 required – one per increment) | Project Build Plan Template | 15 | Technical Review |
| Software Requirements Specifications | MIL-STD-498 SRS Data Item Description (DID) | 80 | Formal Inspection |
| Interface Requirements Specifications | MIL-STD-498 IRS DID | 70 | Formal Inspection |
| Requirements Traceability Matrix | Project Defined | 20 | Technical Review |
| Database Design Description (DBDD) | MIL-STD-498 DBDD DID | 20 | Technical Review |
| Software Design Description | MIL-STD-498 SDD DID | 120 | Technical Review |
| Software Development Folders with code and unit tests (2 required – one per CSCI) | Project Defined | 100 | Walkthrough |
| Software Test Plan | MIL-STD-498 STP DID | 20 | Formal Inspection |
| Software Test Descriptions (2 required – one per CSCI) | MIL-STD-498 STD DID | 60 | Technical Review |
| Software Test Procedures (2 Sets – one per STD) | Project Defined | 150 | Walkthrough |
| Integration Test Plan | Project Defined | 10 | Walkthrough |

## 7.4	Quality Assurance

IEEE Std 1058-1998 Guidance

(Subclause 7.4) Quality assurance plan

This subclause shall provide the plans for assuring that the project fulfills its commitments to the process and the product as specified in the requirements specification, the document, supporting plans, and any standards, procedures, or guidelines to which the process or the product must adhere.  Quality assurance procedures may include analysis, inspections, reviews, audits, and assessments.  The quality assurance plan should indicate the relationships among the quality assurance, verification and validation, review, audit, configuration management, system engineering, and assessment processes.

Appendix F was developed in accordance with the Quality Assurance (QA) Process, reference (u).  The process establishes the requirement for a QA Plan that implements reference (h).  The QA Plan Template, reference (v), was tailored to develop Appendix F.

## 7.5	Reviews and Audits

IEEE Std 1058-1998 Guidance

(Subclause 7.5) Reviews and audits plan

This subclause shall specify the schedule, resources, and methods and procedures to be used in conducting project reviews and audits.  The plan should specify plans for joint acquirer-supplier reviews, management progress reviews, developer peer reviews, quality assurance audits, and acquirer-conducted reviews and audits.  The plan should list the external agencies that approve or regulate any product of the project.

Audits will be performed in accordance with Appendix F, on a schedule defined in Appendix A.  In addition, the PM shall plan and participate in management reviews at locations and dates approved by the SYSCOM Communications Security Office.  Persons with authority to make cost and schedule decisions attend the reviews.  The reviews are scheduled quarterly in Appendix A for the RBC project.  The reviews are to keep SYSCOM Communications Security Office informed about project status, directions being taken, technical agreements reached, and overall status of evolving system products.  Activities would include, but not necessarily be limited to, those listed below:

- Resolve issues that could not be resolved at IPRs.

- Arrive at agreed-upon mitigation strategies for near- and long-term risks that could not be resolved at IPRs.

- Identify and resolve management-level issues and risks not raised at IPRs.

- Obtain commitments and acquirer approvals needed for timely accomplishment of the project.

## 7.6	Problem Resolution

IEEE Std 1058-1998 Guidance

(Subclause 7.6) Problem resolution plan

This subclause shall specify the resources, methods, tools, techniques, and procedures to be used in reporting, analyzing, prioritizing, and processing problem reports generated during the project.  The problem resolution plan should indicate the roles of development, configuration management, the change control board, and verification and validation in problem resolution work activities.  Effort devoted to problem reporting, analysis, and resolution should be separately reported so that rework can be tracked and process improvement accomplished.

The RBC project will use the processes for storing, tracking, and directing correction of Problem/Change Reports (P/CRs) and System Change Requests (SCRs) as defined in Appendix G.  In addition, the PM will direct that an Action Item database be maintained to track issues raised at all planning, coordination, and joint management reviews to ensure timely action and closure.  When necessary, issues will be escalated up the chain-of-command, using the process described in Appendix A of the Integrated Software Management/Software Product Engineering/Inter-group Coordination Guide, reference (w).

To support the resolution of critical issues that may impact the operational readiness of the system, the RBC project will have an active Technical Review Board (TRB).  The TRB, chaired by the PM or an appointed technical manager, is responsible for addressing the key project issues that impact the system’s ability to meet specified requirements.  The TRB will assist, as directed, in ensuring that planning, development, and acquisition of computer resources comply with established Navy policy, procedures, plans and standards.  The TRB also provides technical support to the SCCB.  Given below is a set of candidate issues that might be addressed, at the direction of the project manager, by the TRB during the life of the RBC project:

- Operational concept review to resolve open issues regarding the operational concept for the system.

- System/subsystem requirements reviews, or formally documented decision analysis, to resolve open issues regarding the specified requirements for a system or subsystem.

- System/subsystem design reviews, or formally documented decision analysis, to resolve open issues regarding one or more of the following:

  - The system or subsystem-wide design decisions.

  - The architectural design of a system or subsystem.

- System requirements reviews, or formally documented decision analysis, to resolve open issues regarding the specified requirements for a HWCI or CSCI.

- Software design reviews, or formally documented decision analysis, to resolve open issues regarding one or more of the following:

  - The HWCI/CSCI-wide design decisions.

  - The architectural design of a HWCI/CSCI.

  - The detailed design of a HWCI/CSCI or portion thereof (such as a database).

- Test readiness reviews to resolve open issues regarding one or more of the following:

  - The status of the test environment.

  - The test cases and test procedures to be used for product qualification testing or System Qualification Testing.

  - The status of the hardware and software to be tested.

- Test results reviews to resolve open issues regarding the results of product qualification testing or system qualification testing.

- System usability reviews to resolve open issues regarding one or more of the following:

  - The readiness of the system for installation at user sites.

  - The user and operator manuals.

  - The system version descriptions.

  - The status of installation preparations and activities.

- System supportability reviews to resolve open issues regarding one or more of the following:

  - The readiness of the system for transition to the support agency.

  - The system product specifications.

  - The system support manuals.

  - The system version descriptions.

  - The status of transition preparations and activities, including transition of the system development environment, if applicable.

- Critical requirement reviews,  or formally documented decision analysis,  to resolve open issues regarding the handling of critical requirements, such as those for safety, security, and privacy.

### 7.6.1	TRB Membership

The Development Group, CM, QA, and the Test and Evaluation Group shall be responsible for providing a representative to the TRB.  The representative’s responsibilities are listed below:

- Attend all TRB meetings.

- Provide draft issue papers, as tasked to the member, at a specified period prior to the TRB meeting where it will be discussed.

- Update, release, and control technical memoranda reflecting the TRB decisions to the group the member represents.

### 7.6.2	TRB Chairperson

The PM may serve as the TRB Chairperson, although the task may be delegated to a technical manager.  In that case, the TRB Chairperson shall be accountable to the PM to report problems as they are encountered by the TRB.  The Chairperson’s responsibilities are listed below:

- Schedule meetings.

- Provide the meeting space and administrative support.

- Distribute issue documentation to be addressed at the upcoming TRB.

- Conduct the TRB meetings.

- Record, track, and update action items.

- Ensure the minutes of the TRB meetings are recorded and distributed.

- Ensure that decisions are distributed within the time frame agreed to by the affected participants.

## 7.7	Contractor Management

IEEE Std 1058-1998 Guidance

(Subclause 7.7) Subcontractor management plans

This subclause shall contain plans for selecting and managing any subcontractors that may contribute work products to the project.  The criteria for selecting subcontractors shall be specified and the management plan for each subcontract shall be generated using a tailored version of this standard.  Tailored plans should include the items necessary to ensure successful completion of each subcontract.  In particular, requirements management, monitoring of technical progress, schedule and budget control, product acceptance criteria, and risk management procedures shall be included in each subcontractor plan.  Additional topics should be added as needed to ensure successful completion of the subcontract.  A reference to the official subcontract and prime contractor/subcontractor points of contact shall be specified.

Contractor resources needed by the RBC project are identified in the planning (or plan revision) process.  Elements of the WBS typically become contract requirements.  During the planning process, an informal survey of existing contracts is done to see if an existing contract may be used to meet the contract requirements, including schedule and budget requirements.

The acquisition and monitoring of required contractor support is done in accordance with the Contractor Acquisition and Performance Monitoring Process, reference (x).  The process establishes the requirement for contractor management activities implementing reference (h).

A COR will be named to oversee the contract and track contractor process and contract status.  The COR may be outside of the RBC organization; however, they must be technically conversant with RBC system development issues.  The COR will hold periodic technical reviews with the contractor, and periodic status reviews with the contractor’s management.  The reviews are for the benefit of the SYSCOM Communications Security Office, providing visibility into contract performance, and also for SSC San Diego, providing visibility into contractor capability and suitability. Contract activity measurements will be defined in the contract SOW, will complement RBC project measurements, and will be reported to the RBC PM’s designated representative.  Contractor planning documentation will be reviewed and approved by the RBC project government technical staff.  The COR will also ensure compliance with SSC acquisition regulations.

### 7.7.1	Contracting Process

The RBC project will follow the guidance of reference (x).  Briefly, a Procurement Requirements Package (PRP) will be published for proposed new contracts.  A contract SOW is written.  For existing or new indefinite delivery contracts, Delivery Orders, PRPs and SOWs will be written in accordance with the overall contract PRP or SOW.  Proposals are collected and evaluated by the COR depending upon requirements satisfaction (cost and schedule), contract type, and contractor capability.  An award will be made employing a formally documented decision analysis and resolution process such as the Decision Analysis and Resolution Process (Expert Mode), reference (y).  The COR will administer the contract, and monitor and track contractor performance, including measurement collection, correspondence, funding, and deliverable.  The COR will make this information available to the PM in a timely manner.

### 7.7.2	Contractor Performance Monitoring

The RBC PM is responsible for the management of contractor performance.  The PM delegates contractor monitoring on a technical basis to the technical managers, and on a financial basis to the RBC PM’s Administrative Office.  Issues raised at contractor reviews are either resolved during the review, assigned to a technical manager, or escalated up the chain-of-command in accordance with Appendix A of reference (w).

## 7.8	Process Improvement

IEEE Std 1058-1998 Guidance

(Subclause 7.8) Process improvement plan

This subclause shall include plans for periodically assessing the project, determining areas for improvement, and implementing improvement plans.  The process improvement plan should be closely related to the problem resolution plan; for example, root cause analysis of recurring problems may lead to simple process improvements that can significantly reduce rework during the remainder of the project. Implementation of improvement plans should be examined to identify those processes that can be improved without serious disruptions to an ongoing project and to identify those processes that can best be improved by process improvement initiatives at the organizational level.

The following paragraphs provide data on the RBC project’s efforts for continuing process improvement.

### 7.8.1	Systems/Software Process Improvement Lead

The RBC Systems/Software Process Improvement (SPI) Lead, assigned by the PM, will evaluate RBC practices and make recommendations regarding government and industry best practices in key management and development areas, and interface with the Department Systems Engineering Process Group (SEPG) and SSC San Diego Systems Engineering Process Office (SEPO).

### 7.8.2	Systems Engineering Process Group

Each Department at SSC San Diego maintains an SEPG that is responsible to the Department Head for the development and maintenance of applied system engineering processes.  The SEPG provides a forum for discussion of systems engineering processes and applicable best practices, and promotes the gathering and dissemination of information on those processes.

The SEPG shall analyze the measurement data collected and assess the effectiveness and value of the organization’s processes.  This is done to ensure that the processes are being adapted properly and to identify those processes that need improvement.  The SEPG will interface with SEPO to perform and/or acquire any required training necessary to implement process improvement within the organization.  The SEPG interfaces with SEPO to exchange knowledge on system engineering processes and process improvement on a center-wide basis.  The relationship between SEPO, the Department SEPG, and the RBC SPI Lead is seen in Figure 4-1.  SSC San Diego establishes overall systems engineering policy and guidance, while the SEPG assures sound application of that policy and guidance within the department.  The RBC project SPI Lead serves as the communication interface between the project and the Department’s SEPG for all issues related to process improvement for the RBC project.

This page intentionally left blank.

# SECTION 8.  Additional Plans

IEEE Std 1058-1998 Guidance

(Clause 8) Additional plans

This clause shall contain additional plans, or activities, required to satisfy product requirements and contractual terms.

Additional plans for a particular project may include plans for assuring that safety, privacy, and security requirements for the product are met, special facilities or equipment, product installation plans, user training plans, integration plans, data conversion plans, system transition plans, product maintenance plans, logistic engineering approach, or product support plans.

General Guidance

In this template this section is used to describe the logistics engineering, and its objectives, inherent in the RBC project.

## 8.1	Logistics Engineering

The RBC project performs logistics engineering as an integral part of the development and life cycle support effort.  The objective of the integrated logistics engineering activities is to achieve the maximum level of System Operational Effectiveness (SOE) following the guidance of Designing and Assessing Supportability in DoD Weapon Systems – A Guide to Increased Reliability and Reduced Logistics Footprint, reference (z).

A system’s operational effectiveness derives from a number of component factors that can be described in a hierarchical model, as shown in Figure 8-1.

Figure 8-1.  Components of System Operational Effectiveness

### 8.1.1	System Performance

System performance is realized through designed-in system capabilities and functions. The term capability refers to the various desired performance attributes of the system, such as maximum data rates and message capacity.  The term functions refer to the desired mission capabilities and mission scenarios that the system must be capable of executing in an operational environment.  For the RBC system, these characteristics are determined during requirements analysis.

### 8.1.2	System Availability

The components that contribute to system availability include the systems reliability, maintainability, supportability and sustainment.   Supportability and sustainment are essential components of SOE.  For the RBC system, these characteristics are determined during requirements analysis and the adjudication of the requirements with the determination of a cost effective component architecture.  For example, during the cyclic activities of requirements analysis and architectural design, decisions on ‘buy-or-build’ for an architectural component will weigh reliability, maintainability, and supportability as key decision criteria and may cause reconciliation with capability and/or functional requirements.

### 8.1.3	Process Efficiency

Process efficiency reflects how well the system can be operated and maintained, and to what degree the logistics infrastructure and footprint can be reduced to provide a cost effective, deployable, and operationally effective system.  For the RBC system, these issues are both a part of the RBC project’s continuous process improvement efforts and for the end system, they are addressed during the adjudication of requirements and the architectural design processes defined in Appendix E.

### 8.1.4	Technical Effectiveness

Technical effectiveness reflects the inherent balance between system performance and system availability. These two aspects of the system are designed-in.   The PM ensures the processes for designing and assessing supportability are not only applied during the product development framework, but throughout the entire life cycle.  Supportability assessments, coordinated with systems engineering, are intended to identify redesign opportunities for fielded systems that would enhance overall operational effectiveness.  For the RBC project, the continuous improvement of technical effectiveness is inherent in the revision planning for each build of the system and in the efforts for continuous process improvement.

### 8.1.5	System Effectiveness

System effectiveness reflects the balance achieved between the technical effectiveness and the process efficiency of the system. In this context, process efficiency constitutes the system operational, maintenance, and logistics processes.  System effectiveness reflects the real mission capability delivered to the field.  The RBC PM is ultimately responsible for the resulting system effectiveness.

### 8.1.6	System Ownership Cost

The final piece in the overall SOE model pertains to cost effectiveness.  The over-riding objective is to maximize the system effectiveness from the perspective of the end-user.   However, given a resource-constrained environment trade-offs are inevitable among performance, availability, process efficiency, and cost. The PM must address these issues using the SOE model and negotiate the consequences of balancing consideration of performance, cost, schedule, system availability, and process efficiency with the sponsor for each individual RBC build and its content.

APPENDICES

IEEE Std 1058-1998 Guidance

Annexes may be included, either directly or by reference to other documents, to provide supporting details that could detract from the document if included in the body.

General Guidance

###### In this template, the following appendices are used for reference purposes only.  It should not be assumed that the referenced RBC documents exists as an example.

# Appendix A.  RBC Master Schedule (Microsoft Project)

Guidance

The objective of the RBC Master Schedule is to provide management with the task map and tracking tool needed to guide the RBC Project in the performance of its mission.

The RBC Master Schedule’s Microsoft Project representation of the WBS would be tailored from the templates available from the SSC San Diego Process Asset Library (PAL) in the “SW-CMM Archive”.  Draft Microsoft Project templates are found under the “Process Assets by SW-CMM KPA”, “Software Project Planning (SPP)” in the “Tools” section.  These templates can be tailored up or down to meet specific project needs.

# Appendix B.  RBC Facilities Plan

Guidance

The objective of the RBC Facilities Plan is to document the environmental needs of the RBC project.   These needs include space, equipments, security, safety, support tools, and the staff necessary to maintain and operate an environment needed for project operations.

The facilities requirements for projects vary broadly, often with several projects sharing both facilities and computer resources.   There currently are no templates available from the SSC San Diego PAL to assist in developing a facilities plan.  However, recommended issues to address in a Facilities Plan would include, but not be limited to, the following list:

1.  Facility Objectives/General Description

2.  Facility Locations (i.e., Building Locations)

3.  Facility Diagrams

a.  Floor Plans (i.e., lab, work cubicles)

b.  Environmental Requirements i.e. Heating, Lighting

4.  Facilities Equipment Requirements

a.  Equipment Lists (i.e., work stations, development, test)

b.  Equipment Interface Diagrams

c.  Space Equipment Layouts

d.  Inspections and Records Requirements

5.  Facilities Software Requirements

a.  Software by Development/Test Host Equipment

b.  Software by Workstation

6.  Facilities Operating Personnel Requirements

7.  Facilities Operating Personnel Training Requirements

8.  Security Measures

a.  Internal

b.  External

9.  Safety Measures

10.  Maintenance Requirements (i.e., spaces, per equipment)

11.  Facilities Performance Measurements

# Appendix C.  RBC Project Training Plan

Guidance

The objective of the RBC Project Training Plan is to develop the skills and knowledge of the RBC project staff so they can perform their roles effectively and efficiently.

The RBC Project Training Plan would be tailored from the Department/Project Training Plan Template available from the SSC San Diego Process Asset Library (PAL).  The template is located in the “Process Assets by CMMI PA” sub-page under the “Organizational Training” PA in the “Plans” section.  The template can be tailored up or down to meet specific project needs.

# Appendix D.  RBC Measurement Plan

Guidance

The objective of the RBC Measurement Plan is to develop and present the data needed to support RBC project management information needs necessary to ensure objective decision-making.

The RBC Measurement Plan would be tailored from the Software Measurement Plan Template available from the SSC San Diego Process Asset Library (PAL) in the “SW-CMM Archive”.  This template can be found under the ”Process Assets by SW-CMM KPA”, “Software Project Tracking and Oversight (SPTO)” KPA in the “Tools” section.  The template can be tailored up or down to meet specific project needs.

# Appendix E.  RBC Product Engineering and Qualification Process

Guidance

The objective of the RBC Product Engineering and Qualification (PE&Q) Process is to document the processes comprising a technical solution for development, maintenance, test, and product qualification.

The RBC PE&Q Process would be tailored from the Product Engineering and Qualification Process available from the SSC San Diego Process Asset Library (PAL).  The process is located in the “Process Assets by CMMI PA” sub-page under the “Technical Solution” PA in the “Process” section.  The PE&Q Process can be tailored up or down to meet specific project needs.

# Appendix F.  RBC Quality Assurance Plan

Guidance

The objective of the RBC Quality Assurance Plan is to provide staff and management with objective insights into processes and associated work products, ensuring their conformance to documented requirements.

The RBC Quality Assurance Plan would be tailored from the Quality Assurance Plan Template available from the SSC San Diego Process Asset Library (PAL).  The process is located in the “Process Assets by CMMI PA” sub-page under the “Process and Product Quality Assurance (PPQA)” PA in the “Plans” section.  The template can be tailored up or down to meet specific project needs.

# Appendix G.  RBC Configuration Management Plan

Guidance

The objective of the RBC Configuration Management Plan is to establish and maintain the integrity of RBC work products using configuration identification, configuration control, configuration status accounting, and configuration audits.

The RBC Configuration Management Plan would be tailored from the Configuration Management Plan Template available from the SSC San Diego Process Asset Library (PAL).  The template is located in the “Process Assets by CMMI PA” sub-page under the “Configuration Management (CM)” PA in the “Plans” section.  The template can be tailored up or down to meet specific project needs.

DOCUMENT CHANGE REQUEST (DCR)

| Document Title: [[RBC]] Project Management Plan | Tracking Number: |
| --- | --- |
| Name of Submitting Organization: |
| Organization Contact: | Phone: |
| Mailing Address: |
| DCR Description: | Date: |
| Change Location: (use section #, figure #, table #, etc.) |
| Proposed change: |
| Rationale for Change: |
| Note: For the indicate appropriate authority to take appropriate action on a change request, please provide a clear description of the recommended change along with supporting rationale. Send to: Commanding Officer, Space and Naval Warfare Systems Center, Code [[2xx]], 53560 Hull Street, San Diego, CA 92152-5001 Fax to: indicate appropriate fax number Email to: indicate appropriate email Submit online: indicate appropriate URL DCR Form 2/2005 |