United States Department of Transportation

Federal Aviation Administration

Earned Value Management

GUIDE

August 2005

TABLE OF CONTENTS

SECTION I FAA EARNED VALUE MANAGEMENT PROGRAM	3

Introduction	3

Program Description	4

Roles and Responsibilities	4

SECTION 2 EARNED VALUE MANAGEMENT IMPLEMENTATION ON FAA PROGRAMS	7

Earned Value Management for FAA Programs	7

Basic Features of Earned Value Management	8

Process for Implementing EVMS	9

ANSI/EIA-748 Standard Guidelines for EVMS	9

Tailoring the EVMS	10

SECTION 3 EARNED VALUE MANAGEMENT IMPLEMENTATION ON FAA CONTRACTS	11

Earned Value Management for FAA Contracts	11

Tailoring the EVMS	12

Pre-Contract Award Activities	12

Post Contract Award Activities	15

SECTION 4 FAA EARNED VALUE MANAGEMENT SYSTEMS CERTIFICATION APPROACH	17

Certification Approach and Scope	17

FAA Programs EVMS Certification Process	17

FAA Contractors EVMS Certification Process	18

Earned Value Management System Surveillance	19

APPENDIX 1 -- EARNED VALUE MANAGEMENT REFERENCES	20

# SECTION I
FAA EARNED VALUE MANAGEMENT PROGRAM

Introduction

The effective application of Earned Value Management (EVM) in support of integrated program management provides both the FAA and its contractors with timely, accurate, and integrated cost, schedule and technical performance information, for both the total capital investment program and individual supporting contracts.  EVM continuously measures the quantity and value of work completed and enables the forecasting of reliable estimates of future performance.  The approach has proven to be an effective management tool for programs with performance risk or high interest to management.

The three aspects of earned value referenced in this Guide are defined as follows:

- Earned Value Management (EVM) is a methodology that integrates a program’s (or contract’s) work scope, schedule, and resources with risk management, thereby providing government and contractor managers with objective visibility into progress on their programs and the ability to manage effectively. By reliably identifying trends and problems early, EVM helps program managers effectively plan, control, and manage programs so they can take corrective action and re-plan the work, if necessary.  Systematic implementation of EVM throughout the organization facilitates comparison of program performance, enabling managers to make better-informed decisions.

- Earned Value Management System (EVMS) is the integrated set of processes, applications and practice that follow the guidelines in American National Standard ANSI/EIA-748, “Earned Value Management Systems.”  The ANSI/EIA-748 guidelines describe the attributes of an effectively integrated cost, schedule, and technical performance management system.

- Earned Value (EV) is the amount or volume of work completed to date, also referred to as the budgeted cost for work actually accomplished or performed.  When compared to the planned value for the work and its actual cost, earned value provides objective measures of schedule and cost performance.

The FAA EVM Guide provides specific implementation guidance to program managers and contracting officers in support of the policy established in the Acquisition Management System (AMS) for EVM systems use on FAA programs and contracts.  Additionally, the Guide provides FAA program managers, contracting officers, executives, executive committees, and review boards with a further understanding of the application of EVM concepts in support of program management practices in FAA that will contribute to improved program performance.

Program Description

The FAA’s EVM program provides for the effective and consistent implementation of earned value program management across FAA’s capital investment portfolio, including programs supporting the National Airspace System (NAS), agency-wide information technology programs, and other major investment programs such as safety-related programs.  The following key components of the EVM program are addressed in this Guide:

- EVM Implementation on FAA Programs;

- EVM Implementation on FAA Contracts; and

- EVM Certification and Surveillance Processes

Section 2.0 provides guidance on which programs are required by policy to use EVM, describes its basic features, and discusses implementation on FAA investment programs.  Section 3.0 provides guidance on which contracts are required by policy to use EVM and discusses how it is implemented contractually, pre-award and post-award activities that support the process of placing EVM on a contract.

Additionally, the EVM program includes support processes for program managers in the areas of EVM training, Exhibit 300 – Project Funding Plan (Section 1.H) Reporting, Exhibit 300 – Project Funding Plan (Section 1.H) Preparation, and EVMS program assessments and transition plans that will be addressed in future releases of this Guide.

Reporting EVM Performance Data to Department of Transportation.  For FAA major systems or capital investments, the Office of Management and Budget (OMB) tracks and ultimately approves baseline changes through the budgeting process and the President’s Management Agenda “green” level of performance.   OMB requires the FAA to show that major capital investment programs have less than a 10% variance from cost, schedule, and performance goals.  Program managers must submit quarterly cumulative EVM data and variance analyses (and corrective action plans if necessary) through the FAA Chief Information Officer (AIO) to the Department of Transportation Chief Information Officer (S-80).

EVM Applications.  The FAA’s EVM program uses applications to analyze and report EVM performance data (EVM analysis tools).  Program managers may likewise use this type of EVM application to analyze and report program performance, as well as applications used to manage programs and produce EVM data (EVM “engines”).  A number of commercially available applications produce, receive, analyze, and report data and should be used by program managers to efficiently manage EVM data.  FAA has not yet selected either a standard EVM engine or a standard analysis tool, but may do so in the future.  Program offices should contact the EVM Focal Point to discuss their options.

Roles and Responsibilities

The Acquisition Executive and the Chief Information Officer are jointly responsible for the FAA EVM program and its consistent application across the capital investment portfolio, including the individual supporting contracts.  Correspondingly, the primary roles and responsibilities for the EVM program are assigned to the Acquisition Planning and Policy Division (ATO-A), and the Office of the Chief Information Officer (AIO), Value Management Office.  However, the program manager and contracting officer have the most critical roles and will be described first.

To meet the EVM responsibilities listed in policy, the program manager:

- Prepares the investment program for an EVMS certification review, if required, in accordance with Section 4.0, FAA Certification Approach;

- Ensures the program management team is adequately trained in program management and earned value management techniques;

- Incorporates contract performance reports into the program performance information consistently using the Program Work Breakdown Structure;

- Ensures timely preparation and update of the OMB Exhibit 300 annually; and

- Estimates cost and schedule at completion based on performance to date, and when required, initiates a request for re-baselining in accordance with FAA policy.

To meet the EVM responsibilities listed in policy, the contracting officer:

- Advises the team preparing the Screening Information Request on the proper use of contract clauses and supporting documentation for EVM;

- Formally receives, delivers comments, and accepts EVM-related deliverables; and

- Coordinates with the FAA EVM Executive Agent (EVM Focal Point) to ensure that contractor EVM systems are certified when required.

.

The EVM Focal Point and the Value Management Office work closely together to ensure the EVM program is applied consistently across the FAA.

To meet EVM responsibilities listed in policy, the EVM Focal Point:

- Develops policy and guidance for EVM in support of the AMS;

- Consults with teams on EVM issues during source selection;

- Advises and assists programs with Integrated Baseline Reviews;

- Maintains information about acceptance of contractors’ EVMS

- Coordinates EVMS reviews;

- Manages the EVM training program and curriculum; and

- Serves as a subject-matter expert when reviewing and commenting on the Exhibit 300, Project Investment and Funding Plan (Section 1.H) during the annual preparation process for investment programs.

To meet the EVM responsibilities listed in policy, the Value Management Office:

- Coordinates and manages the preparation of agency Exhibit 300s, including the Project Investment and Funding Plan (Section 1.H), which describes the programs’ Performance Based Management System (EVMS), the program baseline, schedule and cost performance, variance analysis, and corrective action plans, when required; and

- Assists in the development of policy and guidance for EVM in support of the AMS.

# SECTION 2
EARNED VALUE MANAGEMENT IMPLEMENTATION ON FAA PROGRAMS

Earned Value Management for FAA Programs

The OMB and AMS policies require development, modernization, and enhancement programs to use EVM based on the guidelines in the American National Standard ANSI/EIA-748.  FAA programs apply EVM methodologies to the total program effort, including both government and contractor work, to better manage complex, high-risk, high-cost, or high-visibility efforts.  While development, modernization, and enhancement programs primarily occur during solution implementation, the work, as approved, may start during final investment analysis and may continue during in-service management.

FAA programs may utilize multiple sources to accomplish the work of the program and commonly assign work to the following performing organizations that must be included in the EVMS:

Government Organizations.  Government organizations and personnel (Full-Time Equivalents – FTEs), while commonly used to perform program management and oversight, may also perform engineering, testing, deployment, and logistics support functions.  All work and program activities performed by government personnel are assigned using the program Work Breakdown Structure (WBS) and are managed using EVM.  FAA programs required to use EVM must include resources for all government DME effort included in the JRC-approved program baseline.

Major Contractors.  Major contractors commonly are employed in the areas of design, engineering, development, deployment, and support functions.  All work and program activities performed by major contractors are assigned using the program WBS and are managed using EVM.  FAA programs required to use EVM must include resources for all major contractor effort included in the JRC-approved program baseline.  (See Section 3.0)

Support Contractors.  Support contractors commonly perform support roles in one or more areas of program management, engineering, configuration management, test, and logistics.  All work and program activities performed by support contractors are assigned using the Program WBS and are managed using EVM.  FAA programs required to use EVM must include resources for all support contractor effort included in the JRC-approved program baseline.  (See Section 3.0)

Investment programs organize work using the FAA Standard WBS that follows the AMS lifecycle.  The use of EVMS during the planning phases (WBS 1.0 and 2.0) is considered a best practice when the work involves prototyping or testing.  EVMS is required by AMS policy when the FAA approving authority at the final investment decision approves the program baseline and when a program commences development work prior to the final investment decision.  EVM is used during the solution development phase (WBS 3.0), solution implementation phase (WBS 4.0), and in service management phase activities (WBS 5.0), commonly funded by Facilities and Equipment (F&E) funds, including the NAS “Hand-Off” activities, in order to promote the integrity of the performance measurement baseline.  The primary consideration in deciding to use EVM is the nature of the work.  The decision should not be arbitrarily based on program phase or funding source.

Operational and steady-state programs or useful segments funded by Operations and Maintenance (O&M) funds are not required to use EVM, but may do so when the nature of the work lends itself to earned value performance measurement.  These programs perform an annual operational analysis to confirm that realized benefits outweigh costs and that they continue to support agency goals and user needs.

Basic Features of Earned Value Management

EVM methodology periodically (normally monthly, but more frequently when necessary) measures achievement objectively against established goals in a performance baseline plan, helping projects stay on course.  It assists in the identification of potential cost and schedule problems early, before they become unmanageable or unrecoverable, and enables estimates of final program cost and schedule.  Appendix 1, EVM References, provides multiple sources for the definition and formulas of standard EVM performance measures.

EVM requires the fundamental program management principles of planning, organizing, measuring, and controlling to be implemented systematically to produce a product or service.  To apply EVM effectively, program managers:

- Plan all work to completion;

- Break down the work into manageable product-oriented components and assign them to a responsible organization;

- Integrate cost, schedule, and performance objectives into a baseline plan against which progress is measured;

- Record actual costs;

- Objectively measure performance against the baseline plan;

- Analyze variances, forecast impacts, and base estimates at completion on actual performance to date;

- Control and document changes to the performance measurement baseline; and

- Use earned value information in the organization’s management processes.

Process for Implementing EVMS

The generic steps for establishing an EVMS are outlined below.  In addition, FAA’s EVM Training Program and Appendix 1, EVM References provide more detailed descriptions of implementation.

- Establish a management control system that meets the guidelines in ANSI/EIA-748;

- Create an integrated performance measurement baseline (resource-loaded schedule of work to be performed at the lowest level required for performance measurement);

- Establish a work authorization system that assigns responsibility for and controls changes to the performance measurement baseline;

- Earn value for planned budgets as work is completed;

- Provide status against the baseline plan and identify significant schedule and cost variances;

- Analyze variances for early warning signs and take corrective action as necessary; and

- Estimate final cost and schedule outcomes

ANSI/EIA-748 Standard Guidelines for EVMS

ANSI/EIA-748 contains guidelines for establishing and applying an integrated management system for cost, schedule, and technical performance.  The Standard contains 32 guidelines, grouped into five major categories:

- Organization;

- Planning, Scheduling, and Budgeting;

- Accounting Considerations;

- Analysis and Management Reports; and

- Revisions and Data Maintenance

Due to variations in organizations, products, and working relationships, it is impossible to prescribe a universal system for cost and schedule control.  Therefore, the guidelines in ANSI/EIA-748 do not describe a system.  Instead, they state the qualities and operational considerations of an integrated management system without mandating detailed system characteristics.  In designing and implementing an EVMS, the primary objective of the FAA or contractor should be effective management and control.  FAA and contractor organizations have flexibility under this guideline approach to develop an EVMS most suited to their management needs.

The guidelines do not address all FAA needs for day-to-day or week-to-week internal control, such as status reports, reviews, and communications.  These internal controls are characteristics of good management and should be used with EVM to provide insight and information necessary to make informed decisions.  The NDIA Intent Guide for Earned Value Management Systems provides additional insight into the 32 guidelines and describes the typical attributes and objective evidence that support compliance with a given guideline.

Tailoring the EVMS

The program manager, assisted by functional experts such as systems engineers, cost performance specialists, and financial analysts, assesses the program’s anticipated size, complexity, risk, criticality, type of contract, and other factors to select the performance management methodology and reporting best suited for effective management control.  The program manager, considering all risk factors, tailors EVMS requirements to the program.  For example, full compliance with the ANSI/EIA-748 guidelines, with no tailoring, would provide necessary insight into progress on a high-risk program involving a critical, complex integration effort.

Alternatively, appropriate tailoring of EVMS requirements could provide sufficient visibility into performance for a lower-risk program.  Once the program manager characterizes the overall nature of the program, EVMS requirements are tailored to ensure an appropriate level of performance measurement and control.  Examples of ways an EVMS may be tailored include:

| Nature of Program | ANSI/EIA Guidelines | Performance Reports | EVMS Validation | Performance Measurement Baseline | Earning Performance |
| --- | --- | --- | --- | --- | --- |
| Lower Risk (E.g., off the shelf, low- risk schedule, fixed-price contract) | Core principles | Other reports – streamlined | None | Self assessed | Logical means at higher level |
|  | Tailored compliance | Contract Performance Report - tailored (delete formats) | TBD | Integrated Baseline Review | Control account level |
| Higher Risk (E.g., complex integration; Leading-edge technology, risk-sharing contract) | Full compliance | Contract Performance Report (all formats) | Government involved | Integrated Baseline Review | Control account level |

EVM is not required for programs or projects lasting less than one year, but may be used when an existing EVMS can provide reliable information soon after initiation and the program manager has ready access to the information.  Although EVM may not be required, it is important that appropriate scheduling, risk, and requirements management practices be applied for effective monitoring and control.

# SECTION 3
EARNED VALUE MANAGEMENT IMPLEMENTATION ON FAA CONTRACTS

Earned Value Management for FAA Contracts

Investment programs or capital investments determined to be “major programs” with an Exhibit 300 reporting requirement to OMB, are required by AMS policy to use an EVMS to manage all development, modernization, and enhancement work, including the work assigned to all contractors, http://fast.faa.gov/.  This applies to all contract types and contract sizes.  The implementation approach is consistent with the acquisition strategy of the program and is based on an assessment of the cost, schedule, and performance risk associated with the work.  A Contract Performance Report (CPR) and Integrated Master Schedule (IMS) are obtained whenever EVMS compliance is required on a contract.  These reports may be tailored in accordance with their respective Data Item Descriptions (DID) and the specific risks and requirements of the contract.  Integrated Baseline Reviews (IBR) are performed to ensure planning is adequate.  The EVMS used by each contractor must meet the guidelines in ANSI/EIA-748 and be certified in accordance with the process outlined in Section 4.

Investment programs not designated as “major systems” and as a result having no Exhibit 300 reporting requirement to OMB and solely responsible to the JRC or a Line of Business Investment Review Board also follow the policy in AMS in determining the application of EVMS and associated reporting of development, modernization, or enhancement work assigned to contractors.

Major Contracts and Subcontracts.  When a program awards a contract greater than $10M for development, modernization, and enhancement work, the contract is managed by an EVMS.  A CPR and IMS are obtained whenever EVMS compliance is required on a contract.  These reports may be tailored in accordance with their respective DIDs and the specific risks and requirements of the contract.  IBRs are performed to ensure planning is adequate.  The EVMS used by each contractor must meet the guidelines in ANSI/EIA-748 and be certified in accordance with the process outlined in Section 4.

Small Contracts and Subcontracts.  When a program awards a contract less than $10M for development, modernization, and enhancement work, the contract may be managed using an EVMS following the optional policy guidelines outlined in AMS.  A CPR and IMS are optional requirements on the contract.  These reports may be tailored in accordance with their respective DIDs and the specific risks and requirements of the contract.  IBRs may be performed to ensure planning is adequate.  The EVMS, if required, should follow the guidelines of ANSI/EIA-748, and a certification of the EVMS may be required in accordance with Section 4.

Tailoring the EVMS

The selection of contract type is a decision made independent of EVM considerations.  The decision should be based on the nature of the work and anticipated risk.  Any contract that provides for risk sharing (cost type or fixed-price incentive) should include appropriate EVM application and reporting requirements.  Decisions on contract type should not be made to avoid placing EVM on the contract; conversely, EVM should not be applied when it is not appropriate; for example, when buying commercial items based on competitively determined market prices.

Pre-Contract Award Activities

Performance Reports.  The program manager uses contractor performance information derived from the EVMS along with other management information, including technical and schedule-related deliverables to inform the decision-making process throughout the program lifecycle.  Establishing the basis for program metrics and reporting prior to contract award are critical success factors.  Based on a realistic assessment of what can and will be needed, the program manager determines which contract type is best suited based on anticipated risk and what performance reporting, appropriately tailored, is required.  The screening information request and resulting contract are written to reflect the type of report and reporting level needed for effective program control.  Performance reporting options, tailored as needed, are:

- Contract Performance Report (CPR) – Full Reporting.  This is used for high-risk, complex, large programs, when the government shares significant risk or when management interest requires assurance that contractor and subcontractor’s cost and schedule management control systems are adequate.  All five formats of the CPR should be required, with specific reporting levels identified;

- Contract Performance Report - Tailored.  This is intended for less complex programs with lower risk where the contractor assumes a greater share of the risk.  Formats 2 and 4 of the CPR are often not required and the reporting level may be higher in the contract WBS; and

- Other authorized reports - any other performance reports that the program manager believes appropriate and necessary.

Data Item Descriptions.  Performance reports contain the data the program manager needs to manage the contract consistent with contract requirements for the CPR.  When a CPR is required, the DI-MGT- 81466 DID is included in the screening information request as a guide for obtaining the CPR and tailoring report requirements to appropriate information.  DIDs are available on-line in the Statement of Work Generator in FAST or from the DoD EVM website under EVM Policy and Guidance.

Contract Clauses.  For contracts requiring full compliance with the EVMS Standard and the submission of a CPR, the screening information request includes both AMS provision 1.13-1, “Notice of Earned Value Management System Requirements” and contract clause 1.13-2, “Earned Value Management Systems.”

Contract Work Breakdown Structure.  A preliminary contract work breakdown structure (CWBS) is prepared by the program manager and included in the screening information request.  The program manager ensures the CWBS is consistent and compatible with the Program WBS to facilitate incorporation of contractor performance information into program performance reports.  The CWBS should not specify an excessive number of lower-level elements because it may impinge on the contractor’s normal method of operations or result in excessive reporting requirements.  When determining the level for reporting, the program manager should extend the CWBS only to the level that allows visibility into those high-cost, high-risk, or specific areas critical to the success of the program.  The statement of work (SOW) requires the contractor to extend the CWBS to meaningful management or product-oriented lower levels that reflect the way it does business, and to prepare and deliver a CWBS Index and Dictionary.  The contractor should have complete flexibility in extending the CWBS to capture all high-cost and high-risk elements.  The reporting of progress, performance, and engineering evaluations, as well as financial data and variance analysis, are based on the CWBS.  However, any extension proposed by the contractor needs to be traceable directly to the CWBS prepared by the program manager, unless an alternative has been agreed to.

Network Schedule. To ensure the management control system is integrated, the program manager defines requirements in the SOW for a network logic schedule showing the sequence of events and critical path for program milestones or deliverables.

Statement of Work(SOW). The contract SOW reflects the requirement for an EVMS.  The SOW should require the contractor to use appropriately tailored-earned value information as a basis for preparing the CPR and to integrate and present cost, schedule, and technical performance information with risk-management reporting at regularly scheduled program status reviews.  Specific SIR and contract clauses are available as part of the FAST procurement guidance.  Examples of SOW language for EVMS, CWBS, and network schedule are as follows; these examples or the more detailed standard FAA clauses should be modified to fit particular program requirements.

Earned Value Management System (EVMS)

The Contractor must utilize an EVMS for planning, controlling, and integrating project scope, schedule, and resources.  The Contractor must provide documentation that their EVMS is certified.  If the Contractor proposes to use an EVMS or similar system that is not certified, the Contractor must submit a comprehensive plan to develop and implement a certified EVMS.

Contract Work Breakdown Structure (CWBS)

The Contractor must extend the CWBS specified in the contract to a level sufficient to identify all high-cost or high-risk elements and any elements of special interest to management.  If the Contractor uses an existing CWBS, the Contractor must ensure the CWBS is consistent with the FAA Standard Work Breakdown Structure at http://fast.faa.gov/wbs/index.htm.  If the Contractor develops a new CWBS, the Contractor must ensure the CWBS is reconcilable with the FAA Standard Work Breakdown Structure (i.e., information can be summarized directly from the contractor’s CWBS extension to the FAA Standard WBS).  The CWBS must be extended to the necessary level of detail to support development of a logical and efficient sequence of tasks designed to accomplish the effort described in the Contract.

Network Logic Schedule (NLS)

The Contractor must establish a NLS that describes the sequence of events needed to accomplish the requirements of this contract and that reflects CWBS elements.  The Contractor must ensure the NLS portrays an integrated schedule plan to meet the milestones and delivery requirements of this contract.  The NLS must identify the program’s critical path.  The NLS is to be constructed using a software tool compatible with standard scheduling software.  The Contractor must submit the NLS at the post-award conference and an updated version monthly in program status reviews.

Proposal Evaluation.  As part of proposal submission, offerors provide information describing their system for planning, controlling, integrating, and reporting performance.  Their proposed EVMS is subject to validation, which may include self-evaluation with government review, third-party accreditation, or self-evaluation with independent organizational review.  Offerors provide evidence that the EVMS has been reviewed and independently validated.  If the EVMS has not been validated, offerors provide a plan for doing so.  In some situations it may be beneficial to the proposal evaluation process to conduct an Integrated Baseline Review (IBR) for each offeror before contract award if time and resources permit.  Guidance on the IBR process is provided in the NDIA Program Managers' Guide to the Integrated Baseline Review Process.

Contract Award.  The awarded contract includes SOW tasks instructing the contractor to provide integrated earned value-based cost and schedule reporting.  It also requires the contractor to extend the negotiated CWBS and use it as a basis for planning, budgeting, and reporting.  The applicable CPR clause and corresponding DID are also included in the contract.  If applicable, there may also be contractual agreements on subcontractor performance reporting.  EVM-related activities and outputs ending at contract award are summarized below:

| Activity | Output |
| --- | --- |
| Determine management system and reporting requirements | Reporting: - CPR - full guidelines, all formats - CPR - tailored - Other performance reports |
| Prepare screening information request | SIR includes: - CDRL/DID - CPR, or other report - SOW language - CWBS - Clauses |
| Evaluate offeror’s proposals | Evaluation addresses: - Contractor’s description of its EVMS - Potential pre-award IBR - Proposed CWBS changes |
| Negotiate contract and select offeror | Negotiation finalizes: - CDRL/DID tailoring - Proposed CWBS changes, if any - Contractor EVMS management procedures |
| Award contract | Final contract includes: - CDRL/DID - SOW language - CWBS - Clauses |

DoD’s Earned Value Management Implementation Guide contains additional guidance for developing contractual requirements.

Post Contract Award Activities

If not conducted prior to contract award, the program manager conducts a comprehensive IBR of the program baseline for major contracts within 90 to 180 days of contract award or program baseline establishment.  An IBR conducted after award uses earned-value plans and data reported by the contractor, ensures the data are analyzed and coordinated among program personnel, and if applicable ensures follow-up surveillance of the contractor’s EVMS.

Integrated Baseline Review.  An IBR evaluates the contractor’s implementation of the performance measurement baseline.  An IBR is intended to ensure the government and contractor mutually understand program scope, schedule, resources, inherent risk, and management approach, and to ensure early and adequate planning.  The IBR identifies risk items that naturally become part of the risk management plan.  The IBR is a continuous part of the government and contractor program management process.  When the contract requires a CPR or tailored CPR, the program manager normally conducts an IBR within 6 months of contract award.  An updated IBR is also conducted after award of significant contract options or contract modifications.  Guidance on the IBR process is provided in the NDIA Program Managers' Guide to the Integrated Baseline Review Process.

Analyze Data.  Functional specialists on the program, such as software or systems engineers, are designated as control account managers, with responsibility for reviewing reported cost, schedule, and technical progress related to their functional area.  Cross-fertilization of this information improves program decision-making by integrating cost, schedule, and technical considerations, and assures the program of the consistency of reported information from various sources.  The contractor delivers the first CPR or other performance report shortly after contract award.  The program manager and functional specialists immediately review the data.  Thresholds are established for detailed analysis of cost and schedule variances.  The analysis examines the causes for variances, identifies corrective actions, and assesses impact on the overall program.  Cost and schedule variances are charted and compared against other data that may be available such as progress reports, technical interchange meeting minutes, etc.  It is also important for cost and schedule status information reported in performance reports to be discussed along with technical status at regularly scheduled meetings and program reviews with the contractor.

Address Variances.  The Performance Measurement Baseline (PMB) is the agreed to plan for executing the program.  Variances from the plan are expected to occur because the PMB and actual execution normally differ.  Variance analysis provides information on:

- Cause and effect - How and why did the variance happen?

- Consequence - What is the effect of the variance on this work package, control account, and WBS element and on other work packages, controls accounts and WBS elements?

- Correction - Is it possible to recover?  What is the recovery plan?  Do other tasks require management attention to mitigate the effect of the variance?  If it is not possible to recover and get back on plan, what must be done to replan the effort?

Analysis of variances begins at the control account level and continues upward through the WBS and program team until all effects are accounted for and mitigated.  Detailed analysis should be performed for all significant variances.

Links to Risk Management.  Throughout execution of the contract, the program manager ensures the results of EVM analysis and metrics are linked to the risk management plan.  Risk mitigation plans are included in the EVM plan to track and manage risk mitigation actions.

# SECTION 4
FAA EARNED VALUE MANAGEMENT SYSTEMS CERTIFICATION APPROACH

Certification Approach and Scope

FAA programs required by policy, http://fast.faa.gov/, to use an EVMS and required to be certified as meeting the guidelines of ANSI/EIA-748 are assessed and validated by the EVM Focal Point.  The validation is reviewed by the Value Management Office (AIO) and submitted to the appropriate FAA approving authority (?? we need to specify the approving authority) for certification.  After a program has received an EVMS certification, the EVM Focal Point initiates EVM surveillance to ensure the program continues to meet the guidelines of ANSI/EIA-748.

FAA contractors required by policy to use EVMS and required to be certified as meeting the guidelines of ANSI/EIA-748 are validated by the contracting officer, with the assistance of the EVM Focal Point.  The EVM Focal Point determines whether a contractor requires an EVMS certification review or if an existing certification and EVM surveillance process are acceptable.  The FAA EVM Focal Point establishes agreements with other government agencies to recognize contractor EVM certifications and surveillance reports.

FAA Programs EVMS Certification Process

The EVM Focal Point conducts EVMS Validation Reviews on programs prior to the final investment decision or as requested.  The assessment includes a review of program documentation and interviews with program management and key personnel.  The assessment includes a review of procedures and practices on the use of earned value data by the program team.  The review focuses on three main areas concerning use of earned value data:

- Program planning of schedule and cost; including their integration and baseline control with the technical scope as defined in the Program WBS;

- Program performance data analysis and reporting; including the usefulness and effectiveness to the program team to manage schedule and cost; and the

- Availability of timely program performance data used by the program team to anticipate and mitigate program risks.

The program EVM review includes data for government effort, major contractors, and support contractors.

Program management EVM processes are assessed to determine if they meet the intent of ANSI/EIA-748.  The bases for the assessment are ANSI/EIA-748 guidelines and the National Defense Industrial Association (NDIA) Program Management Systems Committee (PMSC) EVMS Standard Intent Guide.  The assessment uses a Red/Yellow/Green rating system to assess EVM implementation for each guideline.  The scale for determining EVM compliance for each guideline is as follows:

Green = The program has implemented the intent of the ANSI/EIA-748 guideline.

Yellow = Partially compliant and the program team is obtaining useful program performance data to anticipate and mitigate program risks.  The program has an acceptable action plan.

Red = The program has not implemented the intent of the ANSI/EIA-748 guideline.

The ANSI/EIA-748 guidelines are summarized into five sub-groups that include related guidelines within each sub-group.  The guideline groupings are similar to those used by the Defense Contract Management Agency (DCMA).

FAA Contractors EVMS Certification Process

The FAA conducts EVMS validation reviews of contractors to verify they have implemented EVMS as required by the contract and ANSI/EIA-748.  The FAA uses the DoD EVM Implementation Guide (EVMIG), Section 3, System Validation and Maintenance for contractor EVMS certification.

The EVMIG defines the process for conducting an EVM validation review and obtaining acceptance by the Executive Agent.  The FAA EVM Focal Point is the Executive Agent for accepting a certification of an EVMS that complies with FAA’s implementation of ANSI/EIA-748.  The EVMIG recognizes validation reviews by government teams, contractor self-validation, and third-party certifications.  FAA also recognizes EVM certifications accepted by DCMA.

The validation review consists of a capability analysis to verify the system meets ANSI/EIA-748 and a review of its use on programs to verify it is being used as designed.  Upon completion of the review by the EVM Focal Point and correction of non-compliant areas, as required, the contracting officer issues an FAA Letter of System Acceptance stating that the contractor’s EVMS meets the guidelines of ANSI/EIA-748.

When a contractor has a contract with the FAA and employs an EVMS that has been formally accepted by another FAA contracting officer as compliant with FAA’s implementation of ANSI/EIA-748, the EVM Focal Point may (but is not required to) recognize the system as compliant for other programs.  Though the system may be deemed compliant, the EVM Focal Point and the program manager jointly verify and demonstrate to the JRC that the system is being used properly and effectively.  This may be accomplished in many ways and depends on program characteristics, past EVM performance of the contractor, JRC direction, and ATO-A surveillance reports.  FAA’s acceptance of the system for other programs depends on the outcome of the EVM surveillance process.  Because management systems are dynamic due to personnel and other changes, surveillance plays a key role in ensuring the continued integrity of the system.  Without an effective surveillance policy and process, the FAA may not unconditionally accept the system.

Earned Value Management System Surveillance

The EVM Focal Point conducts program-level surveillance to ensure continued compliance of the approved EVM system.  In consultation with the contracting officer, the EVM Focal Point conducts a contractor EVM system surveillance program to ensure the continued integrity of contractor EVM Systems.  While achieving certification is a significant event, maintaining the system is equally critical.  Without an effective surveillance process in place, industry experience indicates the EVM System will deteriorate rapidly over time.  The surveillance process is also critical for extending EVM systems across multiple programs.

FAA recognizes and accepts DCMA contractor surveillance agreements.  The EVMIG defines the process for conducting contractor EVM surveillance.  Receipt of DCMA EVM contractor surveillance reports is acceptable to satisfy contractor EVM surveillance requirements.  Some contractors with an EVM requirement may not be under DCMA EVM surveillance.  The EVM Focal Point provides surveillance for these contractors in coordination with the contracting officer.

The FAA assesses the results of the surveillance program to determine if additional action is necessary once certification has been achieved.   The FAA adapts the industry surveillance approach in the National Defense Industrial Association, Program Management Systems Subcommittee, Surveillance Guide as the preferred resource for its surveillance program.

# APPENDIX 1 -- EARNED VALUE MANAGEMENT REFERENCES

FAA guidance on EVM adapts information from various sources, and is not designed as a comprehensive description of EVM activities or practices.  Detailed information on EVM implementation is included in the below references, many of which are available on-line:

ANSI/EIA-748-1998-A – Earned Value Management Systems

Defense Contract Management Agency (DCMA) website:  http://www.dcma.mil/

Defense Acquisition University (DAU) Acquisition Community Connection:  http://acc.dau.mil/

DoD Earned Value Management Implementation Guide:  http://acq.osd.mil/pm

National Defense Industrial Association (NDIA) Program Management Systems Committee (PMSC) Intent Guide for Earned Value Management Systems:  http://www.ndia.org or http://acc.dau.mil

NDIA PMSC Program Managers' Guide to the Integrated Baseline Review Process: http://www.ndia.org or http://acc.dau.mil

NDIA PMSC Surveillance Guide:  http://www.ndia.org or http://acc.dau.mil

PMI College of Performance Management website:  http://www.pmi-cpm.org/

Project Management Institute’s (PMI) Guide to the Project Management Body of Knowledge (PMBOK®)