NAVAL AIR SYSTEMS COMMAND

###### NAVAIR RISK ASSESSMENT HANDBOOK

Do not cite this document on contract.

DISTRIBUTION STATEMENT: Approved for public release; distribution is unlimited.

Acknowledgements

Project Sponsor

William Balderson, AIR 1.0, Deputy Commander for Acquisition and Operations

Technical Writers

Hank Hinkle, AIR-4.1C Policy and Standards Office

Donna Snead, AIR 4.2.7 Division Manager

Robert Wilhelm, ARINC

Robert Larrabee, ARINC

Dina Bullock, ARINC

Contributors

Mike Friedman, AIR 1.0, Acquisition Management BPR Team Leader

Joan Johnson, AIR 4.1.1, Software Center of Excellence

Ray Terry, 4.1.10, System Safety

# PREFACE

This Guide supports the Business Process Re-Engineering (BPR) initiatives particularly in the Acquisition Management arena, and Acquisition Reform Initiatives mandated by the Department of Defense.  As such, it is intended for use in the development of a risk assessment strategy.  This is the initial release of this guide, which will continue to be improved as the BPR effort dictates.

The Acquisition Management Process is a key component of the Naval Aviation Systems Team’s integrated core processes which translates customer requirements into products that meet cost, schedule and technical expectations.  The process is founded on the premise that it is owned by a well-educated and trained acquisition work force, encourages self-motivation and innovation, and adapts to changing environments.  It is characterized by greater insight through disciplined risk management, decreased oversight, partnerships with industry to leverage commercial best practices, and fully integrated, modern information technology.

Beneficial comments (recommendations, additions, deletions) and any pertinent data which may be of use in improving this document should be addressed to: Department of the Navy; Commander; Attn: Hank Hinkle, AIR 4.1C, Suite 2140, Bldg.2185; Naval Air Systems Command Headquarters; 22347 Cedar Point Rd, Unit 6; Patuxent River, Maryland; 20670-1161 or via e-mail hinklehj@navair.navy.mil.

Table of Contents

PREFACE	3

Chapter 1: Introduction	6

1.0 History	6

1.1 Scope	6

1.2 Understanding this guide	7

1.3 Definitions	8

1.4 Applicable Documents	9

Chapter 2: Risk Assessment Process Overview	10

2.0 Risk Assessment Process Introduction	10

2.1 Planning	11

2.2 Integrated Product Team (IPT) Training	13

2.3 Risk Assessment	14

2.4 Risk Reporting	17

Chapter 3: Technical Risk Assessment	19

3.0 Technical Risk Assessment Introduction	19

3.1 Identify High Level Technical Thresholds	20

3.2 Analogy Review	21

3.3 Bottoms Up Work Breakdown Structure (WBS)/Statement of Work (SOW) Review	21

3.4 Critical Technical Processes Review	24

3.5 Additional Risk Factors	26

3.6 Develop Technical Risk List	27

3.7 Technical Risk Likelihood/Consequence Screening	27

3.8 Determine Risk Mitigation Alternatives	29

Chapter 4: Schedule Risk Assessment Process	31

4.0 Schedule Risk Assessment Introduction	31

4.1 Identify High Level Schedule Requirements	32

4.2 Analogy Review	32

4.3 Apply Technical Assessment Results	33

4.4 Risk Readiness for New Technology/Commercial of the Self (COTS)	33

4.5 Document Schedule Risk	34

Chapter 5: Cost Risk Assessment Process	35

5.0 Cost Risk Introduction	35

5.1 Define Scope and Purpose	36

5.2 Identify and Gather Data	36

5.3 Determine Potential Cost Risk Methodologies	37

5.4 Analyze Data	38

5.5 Accomplish Cost Risk Estimate and Crosschecks	39

5.6 Review Estimate with Risk and Present	40

5.7 Document Cost Risk Estimate and Integrate with TA and SA	40

Chapter 6: Risk Reporting	42

6.0 Risk Reporting Introduction	42

6.1 Static Risk Reporting	43

6.2 Dynamic Risk Reporting	45

6.3 Program Risk Mitigation Waterfall Chart	47

Appendix A	A-1

Appendix B	B-1

Appendix C	C-1

Appendix D	D-1

Appendix E	E-1

# Chapter 1: Introduction

## 1.0 History

Risk assessments have been performed within the Naval Air Systems Command for generations.  Review of the events associated with these assessments indicates that most, if not all, of the assessments were performed differently. This concern along with other cost savings initiatives have spurred the development of a standardized risk identification, risk evaluation, and risk reporting process by the Acquisition Management Business Process Re-engineering Group.

In order for the risk assessment process to work, it must become formal, systematic, and applied in a disciplined manner within the organization: in other words, institutionalized. That is not to say that all programs should require extensive formal risk assessments. It does mean that to obtain the maximum benefit from risk assessment, it must become a fully systematic process. There have been, historically, many different interpretations of risk assessment techniques/methodologies. The intent of this guide is to lay the groundwork for institutionalizing a standardized approach to risk assessment within the Naval Air Systems Command.

## 1.1 Scope

The DOD/SECNAV 5000 series, in general, require program managers to establish a risk management program, provide continuous risk management, and determine how risks have changed. These requirements constitute a program consisting of risk assessment, risk monitoring, risk documentation, risk planning and ultimately risk handling.  This guide addresses only the risk assessment portions of these program requirements. Since there are different types of risks associated with acquisition programs, it is also important to note that this guide addresses "acquisition" and "program" risk assessment and does not address risk identification and evaluation techniques associated with "Operational Safety".  Operational Safety risk identification and evaluation is handled exclusively by AIR-4.1.10. This document does not preclude or infer program management actions but focuses only on risk assessment methodologies and practices as they relate to an overall risk management program.   Program management offices are charged with the responsibility of making decisions associated with risk mitigation execution. This guide will provide some guidance in this area. Since risk management is a continuous process, the process outlined in this guide should be performed periodically (planned intervals), and continuously (on going activity).  In support of continuous risk management, this method serves as a program risk baselining tool and should be performed:

- to support Milestone decisions

- to support system requirements reviews (SRRs), preliminary design reviews (PDRs), critical design reviews (CDRs), operational test readiness reviews (OTRRs)

- to support proposal evaluations

- to support budget reviews

- to rebaseline risk status when a risk has been realized

- to rebaseline risk status when requirements change

- for events determined by the team

This process does not preclude independent risk assessment activities, but addresses a process that could be followed if the program manager deems such an approach appropriate.  In reality the approach selected should be based on the program managers resource availability and risk management plan.

## 1.2 Understanding this guide

Acquisition risk is approached in this handbook from a holistic viewpoint. It is addressed as a single entity, consisting of different facets (cost-schedule-technical).  Within the context of this process, technical issues are the primary source of risk with the subsequent impacts to schedule and cost addressed as part of an integrated process.  Although the cost and schedule impact to technical aspects is addressed, risk associated with baseline cost and schedule are also addressed within this guide.  The guide consists of a risk assessment technique that was developed from an evaluation of a number of existing and prior program efforts.  The guide is a tailored sequence that will facilitate a specific program risk assessment.  The sequence is a step process with information from one step facilitating or supporting subsequent steps. The guide is formatted to provide the step sequence with each steps’ input, action description and expected output identified in sub-paragraphs. The level and type of documentation for each input is what changes from program to program and phase to phase. Specific program documentation is cited to support the process, but the process is flexible enough to support the program’s existing level of documentation.

This risk assessment approach provides a basis for the project manager’s risk management program with traceability to program requirements to support a standard reporting mechanism.  Risk is the probability or likelihood that a program requirement (cost-schedule-technical) or goal will not be met as a result of some identified causal factor.  All risks are traceable to a program requirement or goal.  Goals are included within the risk assessment process because programmatically, if effort and funding is expended to achieve a goal then the risk associated with it must be identified and managed.  The consequence of not meeting a requirement or goal is determined by the team independent of the causal factor and is based on the specifics of the project. In other words, the consequence severity of a given event has no relationship to the probability of event occurrence.  The risk assessment process initiates with technical risk identification associated with program requirements and subsequent consequence screening based on the requirements.  Likelihood screening for technical factors will then be integrated with cost and schedule data to result in an integrated program risk assessment.  Examples of reporting techniques are given to support static and dynamic risk representations as well as mitigation status presentation.

In order to adequately assess risk, it is paramount that the risk identification team understand that a realized risk is no longer a risk, it is a problem or issue.  As such it should be dealt with outside the risk management methodology.  However, a well-executed risk assessment should have anticipated the problem and the resolution path or appropriate cost-schedule-technical tradeoffs to solve the problem would have been pro-actively developed beforehand.

## 1.3 Definitions

Risk Management:

“ Proactive management technique that identifies critical processes and methodology for controlling their risk to the program”, (Top Eleven Ways to Manage Technical Risk, OASN (RD&A), 1998).

“Risk Management conducted primarily by assessing contractor critical design, test and production processes; and Earned Value Management System (EVMS) Cost Performance Index/Schedule Performance Index (CPI/SPI) performance to plan against industry best practices and metrics; and programmatic requirements, with the degree of variance determining level of risk”, (Naval Aviation Critical Process Assessment Tool).

Risk Planning:

"The process of developing and documenting an organized, comprehensive, and interactive strategy and methods for identifying and tracking risk areas, developing risk handling plans, performing continuous risk assessments to determine how risks have changed, and assigning adequate resources". (Risk Management Guide for DoD Acquisition, 6 May 1999).

Risk Assessment:

"The process of identifying and analyzing program areas and critical technical process risks to increase the likelihood of meeting cost, schedule, and performance objectives". (Risk Management Guide for DoD Acquisition, 6 May 1999).

Risk Identification:

"The process of examining the program areas and each critical technical process to identify and document the associated risk". (Risk Management Guide for DoD Acquisition, 6 May 1999).

Risk Analysis:

"The process of examining each identified risk area or process to refine the description of the risk, isolate the cause, and determine the effects.  It includes risk rating and prioritization in which risk events are depicted in terms of their probability of occurrence, severity of consequence (or impacts), and relationship to other risk areas or processes". (Risk Management Guide for DoD Acquisition, 6 May 1999).

Risk Mitigation:

“A plan to eliminate or reduce an identified risk when the risk can not be accepted.” (Continuous Risk Management, Software Engineering Institute)

Risk:

“The possibility of suffering loss” (Webster’s dictionary, and Continuous Risk Management, Software Engineering Institute)

“Difference between actual performance of a process and the known best practice for performing that process “,  (Top Eleven Ways to Manage Technical Risk, OASN (RD&A), 1998).

For our purposes, Risk is the potential loss to critical requirements (cost, schedule, or technical).

Likelihood (of a risk’s occurrence):

Quantitative measure of a risk’s potential occurrence.

Consequence (of a risk’s occurrence):

Severity of a risk’s occurrence, if realized.

Problem:

A realized risk (not synonymous with risk itself, and managed differently).

## 1.4 Applicable Documents

This section lists items that were utilized in the development of this guide.

Mandatory Documents

DoD D 5000.1- The Defense Acquisition System

DoD 5000.2-R - Mandatory Procedure for major Defense Acquisition Programs (MDAPS) and Major Automated Information System (MAIS) Acquisition Programs

SECNAVINST 5000.2B - Implementation of Mandatory Procedures for Major & Non-Major Defense Acquisition Program Programs & Major & Non-Major Information Technology Acquisition Programs

Guidance Documents

DoD Directive 5000.4 Cost Analysis Guidance Procedures

Risk Management Guide for DOD Acquisition, DSMC of May 1999

Continuous Risk Management Guidebook, CMU-SEI, 1996

NAVSO P-3686 Top Eleven Ways to Manage Technical Risk, OASN (RD&A), 1998

NAVSO P-6071, Best Practices

DoD 4245.7-M Transition from Development to Production

AIR 4.1 Design Review Handbook, August 2000

Chief of Naval Engineering “Interoperability and Interface Risk ID Questions”

Systems Engineering Formal Review Process Manual

Transition from Development to Production Template (Willowby Template)

F-18  “Product” Risk Consequence evaluation Criteria

R & M Process Assessment (AMRMT)

Software Development Capability Evaluation (S/W Process Assessment)

EIA-632

Naval Aviation Critical Process Assessment Tool (NACPAT)

# Chapter 2: Risk Assessment Process Overview

## 2.0 Risk Assessment Process Introduction

The risk assessment process described in this document can be performed with facilitation or can be implemented by the IPT using these guidelines. The overall function of risk management is the responsibility of the Program Manager and the IPT leader as assigned. The risk assessment process, encompassing risk identification and analysis, simply provides a solid base for executing a pro-active and continuous risk management program. This process also provides a basis for standard reporting of program risks. Internal team management, tracking, monitoring, and team reporting are all under the auspices of the cognizant Program Manager. As such, the process involves the Program Manager and product teams to ensure the efforts support the goals and processes of the product management team.

The risk process can be performed at any time during the acquisition program. The process is the same as presented in the overview below but the level of detail and focus changes with the phase of the program. As a result, this process sequence will always be used. The Process Assessment Tools, such as the DoD 4245.7-M "Transition From Development To Production ", NAVSO P-3686 "Top Eleven Ways To Manage Risk", NAVSO P-6071 "Best Practices", Naval Aviation Critical Process Assessment Tool (NACPAT), and additional factors used to conduct the technical assessment, will change with the acquisition phase and availability of more detailed documentation. What is crucial to all phases is the adequacy of the WBS available for evaluation by the team. A comprehensive description of the utility of the WBS in risk identification and analysis is provided in chapter 3 of this handbook. The process overview is presented graphically in Figure 1.

Figure 1 –Risk Assessment Process Overview

## 2.1 Planning

### 2.1.1 Planning, Inputs:

Risk assessment planning is initiated subsequent to a request for risk assessment from a Program Executive Officer (PEO), Program Manager, Air (PMA), IPT Lead, AIR-4.0B, etc.  The request then results in a scheduled meeting between the risk assessment coordinator and the PMA/IPT Lead.

### 2.1.2 Planning, Description:

Risk Assessment planning is required to identify/acquire program documentation, identify team membership, and assure that the risk assessment coordinator will address program requirements and concerns.  The risk assessment coordinator will conduct an initial interview with the program manager. During this meeting the coordinator will present an overview of this process, explaining the function of the coordinator and the expected interactions for successful execution of the assessment. The program manager and coordinator will determine program processes that are critical for successful execution of the program.  The coordinator can provide a list of process assessment tools such as the DoD 4245.7-M "Transition from Development to Production", NAVSO P-6071 "Best Practices", NACPAT, and NAVSO P-3686 "Top Eleven Ways to Manage Technical Risk" for review by the program manager.	The coordinator will require the following information during the initial meeting to permit planning of the assessment effort:

- Program Brief (If coordinator was not already part of the program)– to provide understanding of the acquisition approach.

- Programmatic and Technical requirements document – to determine the traceability aspects and level of detail available for evaluation. Documentation will vary based on the type and level of program. The types of documentation are:

- Operational Requirements Documents (ORD’s)

- Acquisition Program Baseline Agreement (APBA)

- Specifications

- Contracts

- WBS (Integrated Master Plan and/or schedule)

Note: The requirements embedded within this documentation form the basis for assessment of risks as well as reporting of program level risk

- Current risk assessment/management process-Contractor and/or government organizational processes that exist including current risk assessment results

- Initial thoughts on critical processes associated with the product under development

- IPT risk assessment point of contact-single POC for risk assessment interactions

- Risk assessment team membership-contractor and government personnel and roles assigned for risk assessment process

- Preliminary risk assessment schedule-what are the Program Manager’s or team’s requirements to complete the effort (support a milestone, personnel availability, etc.)

- Location where risk assessment will be performed (contractors facility, Patuxent River, etc.)

- Funding issues associated with manpower or travel to support the risk assessment effort

- If the program involves software development, the SEI CMM certification level of the developing agency (SEI level of the software development unit)

- Agreement on level of risks (high, medium, or low) which will require determination of risk mitigation alternatives (tailor appendix A to aid the program manager)

- If an independent assessment is to be performed, a memorandum of understanding (MOU) should be developed which outlines reporting and risk assessment exit criteria requirements

- Agreement on an agenda for the formal risk assessment  (See appendix B)

This process element ensures the approach and expected results will satisfy the program managers requirements and will assess the adequacy of the program documentation to support risk identification. The documentation reviewed will be discussed with the Program Manager to determine the scope of the risk assessment and limitations which will be encountered based on risk assessment team personnel as well as limitations in the available documentation.

The risk coordinator should develop a risk assessment plan (RAP) which addresses the planning elements of the formal assessment.  A generic RAP is included in appendix C.  The RAP is not a substitute for a program risk management plan, but it does represent the plan for the activity associated with the formal risk assessment. The RAP should address the criteria for the program phase or incremental design milestone the program is working toward.  For design reviews, the criteria should be derived from the AIR-4.1 Design Review Handbook.  For milestone reviews the review should address the milestone entrance and exit criteria developed based on DOD 5000 compliance.

This process should be executed in coordination with the AIR-3.0 integrated logistics assessment (ILA) whenever possible.  This coordination effort will eliminate duplicative activities and lesson the burden on the program team.

### 2.1.3 Planning, Outputs:

The Program Manager interview should result in a basic understanding of the process by the Program Manager.  The interview will provide valuable program information to the risk assessment expert/facilitator that assists in developing a basic understanding of the program, program constraints, Program Manger expectations, and documentation required for review as input into the next risk assessment process element.  A tentative list of critical processes associated with the product under development will also be supplied.  Specific outputs follow:

- Preliminary risk assessment based on the level of documentation provided. Requirement for additional documentation.

- Utilization of existing risk processes. How the assessment effort will feed existing tracking and monitoring tools or methods. How existing assessment methods will be utilized as additional factors.

- Recommendations of additional personnel (if necessary) based on the risk assessment team staffing provided.

- Plan of Action and Milestones (POA&M) for risk assessment execution.

- List of critical processes associated with the product under development.

- MOU between the program manager and the independent assessment group (Only if independent assessment is to be executed)

- ILA coordination requirements

- Draft RAP

## 2.2 Integrated Product Team (IPT) Training

### 2.2.1 IPT Training, Inputs:

Completion of the Planning process element results in a program manager approved POA&M for execution of the risk assessment, and an agreement between the coordinator and the program manager that IPT training is required.  This process element may be omitted if the IPT has received training previously.

### 2.2.2 IPT Training, Description:

IPT Training ensures the team is performing the assessment in a repeatable manner with common definitions and understanding of the documentation. It further identifies the expected program reporting requirements based on the high-level requirement documentation. The coordinator will provide training of the assigned risk assessment team. This training will encompass the process defined in this handbook, to include:

- Key Terms and Definitions

- Process Inputs (project specific)

- Process Elements

- Function of each element

- Execution of each element

- Interrelationships

- Process Flow

- Expected Outputs

- Tools

### 2.2.3 IPT Training, Outputs:

IPT has obtained sufficient knowledge of the risk assessment process to perform risk assessment.

## 2.3 Risk Assessment

### 2.3.1 Risk Assessment, Inputs:

The risk assessment is initiated once the top-level requirements, required documents, resources, funding for the efforts, locations and meeting logistics considerations are identified with all issues resolved.

### 2.3.2 Risk Assessment, Description:

The risk assessment is executed via a technical review forum whereby the cognizant development team(s) (either government or contractor) provide briefings associated with each product.  These briefings should address all product elements as well as all critical process elements that are required for success of the program.  A generic meeting agenda outline is provided in appendix B.  The generic agenda should be tailored based on known areas of concern, acquisition phase and/or the requirements of the program under assessment. Each briefing should address as a minimum:

- Current Identified Risks and Risk Mitigation activities

- Schedule For Product Development

- Process documents (e.g. risk management plan, software development plan, reliability development plan, etc.)

- WBS and SOW Work Packages associated with achievement of the requirement

- Traceability of SOW and technical specification of ORD requirements

- Metrics used to monitor progress

- Staffing profiles and relation to schedule

- Results of analysis, simulations, demonstrations, and tests performed to date with respect to technical requirements

- Plans for acquisition of resources such as facilities, spares, publications, etc to support the acquisition phase

The risk assessment is an iterative staged approach that starts with a stand alone assessment of technical items and their consequence, that is the technical risk item is identified and analyzed in the context of the schedule and cost implications to determine the likelihood of occurrence.  Although the assessment initiates with a technical assessment, schedule and cost assessments are also performed with one aspect reviewing the implications of technical risks and another review purely on the merits/reasonableness of cost and schedule development techniques/processes.  This 3 dimensional aspect of risk (cost-schedule-technical) is required for risk managers to:

- Determine risk mitigation alternatives.

- Identify risk tracking metrics

- Develop and evaluation of risk mitigation strategies.

Later chapters within this guide identify the detailed methodology that should be used in risk assessment.

Risk has been defined in the acquisition context as:

… the potential loss to critical requirements (cost, schedule, or technical).

Risk Management must be performed if funding and effort are being expended to accomplish some end result. The risk is therefore traceable to some requirement, goal or objective and can apply to any of the program categories of cost-schedule-technical.  The basic premise of all risk assessments identified within this guide is based on the aforementioned philosophy.  An understanding of risk traceability is therefore paramount in all applications of this risk assessment process.  The following paragraphs provide a brief synopsis of the definition of risk traceability and the implications within this risk assessment process.

The planning process element will provide agreement as to what are the high-level requirement documents for the project. In a classic acquisition program this would be:

- Technical Requirements – ORD

- Cost, Schedule Requirements – APBA

These documents constitute the program managers’ contract with DoD management and are available at program initiation. At later stages in the program the Specification, Contract, and other more detailed information will be available but these documents should also traceable to the ORD and APBA.

In lieu of standard acquisition documentation such as the ORD and APBA, the Program Manager will provide the coordinator documents which contain the high level requirements for program cost-schedule-technical. These documents will form the basis for risk identification and evaluation.

These high-level requirement documents form the backbone of requirement traceability.  In other words, if a requirement or work package is not traceable to a high-level requirement, then risk is needlessly induced into the program and therefore must be identified and brought to the program managers' attention.

Risks will be identified for technical requirements based on the analysis method discussed in chapter 3. WBS items associated with attaining each technical requirement, goal or objective should be isolated for evaluation. Analysis tools (DoD 4245.7-M "Transition From Production To Development Templates", NAVSO P-6071 "Best Practices", NACPAT and NAVSO P-3686 "Top Eleven Ways To Manage Technical Risk", and additional factors) are effective in accomplishing this task. Risks are then traced to program technical requirement(s). Then consequence screening will be accomplished as discussed below and an integrated (with cost and schedule) likelihood will be determined.

Critical Process Screening

This approach is used to identify and analyze program technical risks by assessing the amount of variance between the contractor's design, test and production processes and industry Best Practices.  NAVAIR recognizes the Program Management, Systems Engineering and Risk Management as Critical Processes.  Success of any risk reduction efforts associated with this technique will depend on the contractor's ability and willingness to make a concerted effort to replace any deficient engineering practices and procedures with industry Best Practices.  One of the primary benefits of this approach is that it addresses pervasive and subtle sources of risk in most DoD acquisition programs and uses fundamental engineering principles and proven procedures to reduce technical risks.  The program baseline being used by the contractor should be determined by evaluating actual contractor performance, as opposed to stated policy.  This program baseline should then be compared to a baseline of those industry-wide processes and practices that are critical to the program.  The variances between the two baselines are indications of the technical process risk present in the program.

Likelihood and Consequence Screening

Likelihood and consequence screening are the analysis portion of the assessment on the identified items.  This is a frequently used method of identifying risks requiring management and mitigation.  A standard likelihood and consequence screening is desired to achieve common reporting.  Consequence and likelihood screening are based on the static representation provided through use of the 5X5 risk cube discussed in chapter 6.  This snapshot of the risk, the output of the risk assessment can further be utilized for dynamic and mitigation display associated with the overall risk management process.  Recommended dynamic and mitigation presentation formats are provided in chapter 6.

Characteristics of the program such as ACAT level, phase/milestone decision point or simply PM's desires may impose a need for the output from the cost risk assessment to be a cumulative probability distribution of total cost.  On these occasions likelihood and consequence screening will have to provide likelihoods and consequences quantified beyond the numeric categories associated with the 5x5 risk cube/static risk reporting model.

For example, rather than simply identifying a risk as having a likelihood score of 3 with a consequence score of 2, likelihood must be expressed as a probability ranging from 0.0 - 1.0 and consequence must be expressed in units that can be translated into cost.  These efforts will of course be subjective in nature so the assistance of an experienced cost risk analyst may prove helpful.

Consequence Screening

Consequence screening is accomplished independent of the likelihood.  For program requirements (critical technical from the ORD and APBA cost-schedule) the consequence of not realizing is a 5 "Unacceptable".  As a critical requirement failure to obtain these values results in failure of the program.  Changing a requirement may be a mitigation approach, and would require that a full risk assessment be accomplished as a result of the modification of a major program requirement for program goals and objectives the consequence is determined by the team.  The consequence of not obtaining is not related to the cause or likelihood.  The technical risks that have been identified are already tied to a requirement based on the identification process.  These items are then assessed for likelihood.

Likelihood Screening

Likelihood screening is accomplished in an integrated manner. First an initial assessment is made based on the risk itself. This likelihood is then evaluated in the context of the cost and schedule. Sufficient cost and schedule may result in the likelihood remaining the same. There may also be sufficient time and funding available to even mitigate the likelihood in the initial plan or there are insufficient funds and schedule available such that the likelihood is assigned a higher value. This is done by analysis of the team. The likelihood for all risks identified for program requirements are then used to determine the overall likelihood of risk to the requirement. The team would then be able to identify those watch items necessary for risk management to achieve program requirements and develop appropriate mitigation plans and/or metrics. Risk traceability to program requirements now allows for standard reporting as discussed in the ascending process elements.

Final Risk List review

Once the risk list is generated with the appropriate likelihood and consequence screening factors applied, the entire risk assessment team and IPT risk review board should review all risks to assure:

- General understanding of each risk and risk causes

- Duplicate risks are deleted

- Concurrence on the risk likelihood and consequence

- Risk mitigation alternatives are understood and are well documented

- Risks are traced to high-level program requirements

- "High" risk items are addressed via potential risk mitigation strategies and /or the requirement for management attention outside of the program

### 2.3.3 Risk Assessment, Outputs:

A list of risks along with the associated likelihood and consequences are finalized at the conclusion of the risk assessment.  These risks are addressed versus the higher level program requirements.

## 2.4 Risk Reporting

### 2.4.1 Risk Reporting, Inputs:

Risks have been identified via the risk assessment process and likelihood and consequences of the identified risks have concurrence from the program team.  The program manager and risk assessment team understands criteria for presentation to management.

### 2.4.2 Risk Reporting, Description:

The process is designed to provide a standard reporting method. Internal team monitoring and tracking is still a requirement but is left to the team to manage. Reporting should be as indicated in Chapter 6 of this handbook. The likelihood and consequence values will be reported for the program requirements (cost-schedule-technical requirements) outside the Program Manager level. These are the values that define the teams program and represent the program factors of interest to higher level decision makers. It provides the proper context for the risk management plan for upper level management. This information can be represented in a static (risk cube) form already common to most risk management processes, or in a dynamic form as indicated in chapter 6. Additionally mitigation plans can be presented in the waterfall form for those watch items effecting the reporting risk areas.

Risks must be presented in a clear, concise, and standardized format so that senior personnel responsible for making programmatic and technical decisions are not burdened with large amounts of non-standardized data, yet at the same time have enough information to make programmatic decisions.  The report format should be comprehensive enough to give an overall assessment, be supported by enough technical detail and include recommended corrective actions. In addition, the following provides some basics in reporting or “rolling up” risk data for senior personnel in a position to assist the program in reducing risk:

- Use of a standard form  to report and process risks at the Program Risk Assessment Board (PRAB) - Examples in appendix D

- Government and contractor reports should utilize the same form/format and terminology

- Reports should summarize high and moderate risks and recommended actions

- A “watch list,” which tracks risks and mitigation activities should be included as part of the report.  The watch list is normally updated monthly and should include the top ten (or more as applicable) risk items prioritized by exposure and leverage

- Reports should also include, as a minimum;

- Number of risk items resolved to date

- Number of new risk items since last report

- Number of unresolved risk items

- Unresolved risk items on the critical path

### 2.4.3 Risk Reporting, Outputs:

Identified risks are reported to upper management in a consistent and understandable form.

# Chapter 3: Technical Risk Assessment

## 3.0 Technical Risk Assessment Introduction

Technical risk is usually associated with the evolution of a new design to provide a greater level of performance than previously demonstrated, or the same or lesser performance subject to new or more intense constraints.  The nature and causes of technical risks vary from program to program.  Most technical risks evolve as a result of the demand for ever greater performance from new systems and equipment.  The ever-present requirement to minimize or maximize physical properties of systems and equipment further adds to the risks associated with higher technical thresholds.

Although managing risks for all aspects of a program is critical, technical risk is perhaps the most important area of risk consideration because technical risk and the degree to which processes can be controlled, is a significant driver of all other program risks.  This chapter forms the initial step in the risk assessment process that will be incorporated in and included in the schedule and cost risk assessment processes identified in later chapters of this document.

Many of the "ilities" such as operability, producibility, supportability, maintainability, and reliability, must be addressed in systems acquisition.  Each can be viewed as additional design requirements placed on designers attempting to evolve an efficient design capable of the desired performance level.  The aforementioned view is not correct in that a system must possess these characteristics in order to be both suitable and effective when fielded.  As such, each of these design requirements can be a source of technical risk.

The technical risk assessment process identified in this chapter will assist in the identification and evaluation of technical risks associated with system products and processes.  The technical risk assessment process will result in a clear picture of the program technical foundation and will also provide inputs into the schedule and cost risk assessment processes discussed later in this handbook.  The top level depiction of the technical risk assessment process is shown in Figure 2.

Figure 2: Technical Risk Assessment Process

## 3.1 Identify High Level Technical Thresholds

### 3.1.1 Identify High Level Technical Thresholds, Input:

High level program technical thresholds such as those in the ORD or APBA as directed by the Program Manager and/or cognizant product team lead.

### 3.1.2 Identify High Level Technical Thresholds, Description:

This process element identifies the technical thresholds, goals and objectives of the product line program. These categories for program effort and funding form the traceability basis for risk assessment. The high level technical performance that will be obtained must be identified as a requirement, goal, or objective. This distinction will permit the team to then determine the consequence associated with item. Examples of requirements would be ORD Key Performance Parameters  (KPPs) or "Shall" statements.  If an item is categorized as a requirement, then the consequence of failure is a classic “5”, "Unacceptable" on the static risk cube. The risk assessment team determines consequences of not obtaining goals and objectives as well. Items identified through the remaining technical assessment will be directly traceable to one of these high level thresholds, goals or objectives. These also form the basis for reporting requirements.

### 3.1.3 Identify High Level Technical Thresholds, Output:

Listing of technical thresholds, goals and objectives with associated consequence of failure.

## 3.2 Analogy Review

### 3.2.1 Analogy Review, Input:

Select or develop a Baseline Comparison System (BCS) that very closely approximates the characteristics of the new program/project/system, and uses very similar developmental and acquisition processes.

### 3.2.2 Analogy Review, Description:

Optimally the system engineer and IPT should be involved in performance of this technique.  The system developer could also perform this technique since the developer would, in most cases, posses the most experience with similar systems. This paradigm is most useful to support other primary risk assessment techniques (WBS, process, product risk assessments) when systems engineering, system integration issues, and software development are minimal. It is most applicable to “like” products developed by “like” processes, where like = very, very similar. This technique analyzes similar systems to use lessons learned from similar development efforts.  It is essential that  "like" systems be compared to the system under assessment in a manner than would not lead to erroneous conclusions on the part of the assessment team.

Problems associated with similar systems should be identified and analyzed to determine applicability to the program under assessment.  Problems on similar programs should be treated as potential risks on future programs.

### 3.2.3 Analogy Review, Output:

Risks that are derived from lessons learned on similar or like product lines. Provides technical items that need to be evaluated in the context of the program WBS and integrated with cost and schedule risk information to determine risk to high level thresholds.

## 3.3 Bottoms Up Work Breakdown Structure (WBS)/Statement of Work (SOW) Review

### 3.3.1 Bottoms Up WBS/SOW Review, Input:

- System WBS provided by the Program Manager

- Statement of Work Describing Tasks Associated With Each WBS Element

- High Level Thresholds

- Risk identified during analogy review

- Existing Program Risk Database

### 3.3.2 Bottoms Up WBS/SOW Review, Description:

This technique should be performed by a joint industry-government IPT, Program Managers and systems engineers. A WBS displays and defines the product(s) to be developed and/or produced and the related elements of work to be accomplished. The information assessed will be a WBS, which can be used for workload scheduling, Earned Value cost and schedule prediction (prediction of BCWP, BCWS), and for an engineering (bottom-up) estimate of both cost and schedule. As the acquisition progresses through phases, a more detailed WBS should be required to assess risk. For optimum results, a 5 level WBS is required to fully illuminate risks at phase 2 (EMD) and later. An accurate, credible, executable WBS is an absolute prerequisite to usable cost, schedule, and technical risk assessments. Without a rigorous WBS, programmatic risk assessment is highly problematic, and would undoubtedly yield inconclusive results.

##### Pre-assessment activities:

Provide the risk assessment team with, or access to the following:

- ORD

- Specification

- WBS

- Statement of Work

- Requirement Traceability Matrix

- Risks Identified During Analogy Review

- Existing program Risks

Assessment Activities:

This assessment technique is used to identify and analyze risk associated with the products/elements of the systems.  It will also enable visibility into the processes that will be implemented in the development of the system.  The process element will be utilized along with the ascending process element (Analyze Processes) to completely analyze the work associated with the element as well as the best practice associated with the processes utilized in development of the element.  The "Additional Factors" element of this process will also provide areas of potential risk.

WBS/SOW Comprehensiveness/Suitability Assessment Method:

1. Evaluate comprehensiveness of the product WBS/SOW. Each top-level task should correspond to a clearly defined activity or product, or both. The acquisition team should be able to evaluate the WBS/SOW scope for risk at this level. Deeper levels (levels II, III, IV, and V) may require technical expertise, expert opinions, or industry clarification. Specifically review the product WBS/SOW to see that top-level tasks are further decomposed within the lower-level structure.

2. Technical members of the IPT should review the product system thresholds, goals and objectives identified as discussed above to determine if the WBS/SOW addresses those requirements in sufficient detail.  As stated previously, the intent of the WBS/SOW is to develop a product hierarchy for development of the system and it provides the groundwork for schedule development and cost estimation.  During development of the WBS/SOW, risk is not usually documented or highlighted.  This assessment will permit the risks associated with each WBS/SOW element/work package to be highlighted and reviewed by the entire team.  The engineering requirements should be reflected within the WBS/SOW.  In summary, key elements to review include:

- Content of the WBS:

- Tiered structure (3-to-5 level WBS), at a minimum, for risk evaluation

- Top tiers reflect requirement implementation from System Engineering functional allocation process; hardware and software tasks scoped

- Hardware, software and system integration effort scoped

- Test and evaluation support scoped, if appropriate

- Lower tiers address increasing technical, managerial, process detail

- Effort (Person-Months) and duration (Months) of sub-tasks is consistent with higher-tiered tasks, and consistent with programmatic goals

- Progress estimation is based on past performance

- WBS/SOW is capable of technologically and managerially implementing ORD, MNS requirements

- Redundant tasks  identified

- Critical or key tasks are identified so that major system design drivers are known

- Desired and mandatory requirements are segregated; rate and prioritize risks.

- Review in general to determine if there is a potential for surprises later in the program. Need surprises (risks) to be identified and quantified (cost-schedule-technical)

- WBS, which has not been derived in accordance with MIL-STD-881B or equivalent, requires a detailed process presentation that identifies adequate requirement traceability. If requirement traceability cannot be demonstrated with the WBS, risk cannot be properly identified and bounded.

3.  Identify WBS/SOW elements associated with each identified requirement, goal or objective identified in 3.1, “Identification of High-Level Technical Requirements”.  This is typically obtained from the requirement traceability matrix.

4.  Determine suitability of WBS/SOW elements and identify missing elements based on IPT knowledge base.

5.  Identify risks associated with each WBS/SOW element or missing element based on experience of the assessment team or lessons learned from other programs. As stated previously, the WBS/SOW was developed in response to development of a product and did not initially include (in most cases) the corresponding risk associated with each element.  The risk assessment gives the developer a chance to openly discuss risks associated with the system products under development.  Assure each risk is associated with a program high level requirement.  For example, the risk to the high level requirement may be due to advanced technology, too short of a schedule, or limited funds associated with completion of the work task. Identify processes associated with each WBS/SOW element.  As each element is assessed, identify those products within the system architecture which are new technology (new developments) for which there are no legacy systems for comparison.

6. Assess processes in conjunction with the next step in the process (Analyze Processes).

7. Identify risks derived from the basic knowledge base of the assessors.

8. Review the items to "Watch Out For" associated with each process (Items are listed in NAVSO P-3686 "Top Eleven Ways To Manage Technical Risk" for each critical process).

### 3.3.3 Bottoms Up WBS/SOW Review, Output:

- Risks associated with each WBS/SOW element identified and documented

- Risks associated with absent work packages identified

- Resolution of risks derived by the analogy review of similar system

- List of "New Technology" Related items

## 3.4 Critical Technical Processes Review

### 3.4.1 Critical Technical Processes Review, Input:

- Critical technical processes identified from WBS/SOW in previous process elements

- Critical technical processes identified during "Planning" element of this process

### 3.4.2 Critical Technical Processes Review, Description:

The "Analyze Processes" process element refers to a risk identification technique for technical risks associated with contractor's critical processes.  This technique utilizes fundamental engineering principles and proven procedures to identify risks.  This technique is most applicable during the early stages of product development (phases 0 through II). Critical technical process risks are identified by assessing design, test and production processes against industry best practices, with the degree of variance determining the level of risk. These critical process risks are generally not tailored for individual WBS elements.  The first knowledge source one should utilize in planning for process related risks assessments is the knowledge base resident in the Research & Engineering and Logistics level II and III competencies. Other tools that are recommended for this process follow:

Naval Aviation Critical Process Assessment Tool (NACPAT):

The tool captures criteria for risk assessments as well as questions, which could assist in evaluating a process against the given criteria. The NACPAT exists for 18 critical process areas. The NAVAIR Critical Process Assessment Tool (NACPAT) is a framework to help IPT members assess risk by functional area within each acquisition phase. See the URL for NACPAT information: http://home.navair.navy.mil/nacpat/.

Apply the NACPAT to the critical process areas to determine deviation from "best practices" for the Navy. A list of the critical processes addressed by NACPAT follows:

- Program Management

- System Engineering

- Risk Management

- Quality Assurance

- Manufacturing

- Configuration Management

- Design Engineering

- Survivability

- Safety

- Mass Properties

- Parts,  Materials, Packaging

- Human factors

- T&E

- ILS

- EMI/EMC

NAVSO P-3686 "Top Eleven Ways To Manage Technical Risk"

This document offers a single source of concise explanations and clear descriptions of steps one can take to establish and implement core technical risk management functions.  It contains baseline information, explanations, and best practices that contribute to a well founded technical risk management program – invaluable to program managers overwhelmed by the magnitude of information and guidance available on the broad subject of risk management today.  Each chapter addresses specific technical risk areas.”

The publication, in PDF format, is available on the ASN(RD&A)ABM homepage at http://www.abm.rda.hq.navy.mil/bprisk.cfm.

DoD 4245.7-M, "Transition from Development to Production"

The DoD guide "Transition from Development to Production" provides a structure for identifying risk in the transition from a program's development to production phases.  The structure is geared toward development programs but could be used with any acquisition program with modification.  The structure identifies a series of templates for each of the development contractor's critical engineering processes.  The templates include potential areas of risk for each area.

Assistant Secretary of the Navy for Research, Development, and Acquisition (ASN RD&A)

Interoperability & Integration (I&I) Risk Identification. The ASN RD&A has initiated a process whereby the RDA Chief of Naval Engineering Office (Cheng) will participate in Navy wide programs that have a significant Interoperability & Integration (I&I) component, especially in the areas of Theater Air and Missile defense, C4ISR, and Time Critical Strike.  These programs will be assessed via question based fact finding sessions.  The questions are resident in the Technical Risk and Mitigation System (TRIMS) and will aide in the identification and assessment of risks across programs and PEOs.  It is significant to note that the reporting scheme associated with the TRIMS tool (generated by TRIMS) is different than that prescribed in this guide and is mandatory at milestone decision reviews where the program is under I&I risk review.  The TRIMS tool is part of the Program Managers Workstation (PMWS), and can be downloaded at no cost.  The PMWS is located at (http://www.bmpcoe.org/pmws/index.html)

NAVAIR Specific Models The Reliability and Maintainability (R&M) branch of the Naval Air Systems Command Systems Engineering Branch has developed a set of questions for use in assessing R&M process risks.  This tool is available from AIR-4.1.6.

The Software Center of Excellence (SCE) has modified the Air Force Software Development Capability Evaluation (SDCE) model via incorporation in a software driven tool.  This tool is cited as the software development process evaluation tool and is available through the SCE - AIR-4.1.11.

### 3.4.3 Critical Technical Processes Review, Output:

Process risk factors identified for WBS elements and SOW work packages that are linked to high level program thresholds.

## 3.5 Additional Risk Factors

### 3.5.1 Additional Risk Factors, Input:

During risk planning, it may also be determined that the IPT needs additional expertise in a new technology area. For instance, if a nanotechnology system is being developed, a SME with nanotechnology experience should be added to the existing IPT to address these particular issues.

- Past Performance of the developer

- Technology

- Architecture

- Design

- Operational Environment including threat

- Systems Engineering

- Maintenance, Logistics, and configuration management

- Program Management

### 3.5.2 Additional Risk Factors, Description:

Identify additional factors that might be specific to the product that are not included above and ensure expertise exists to evaluate. Evaluation will be performed on the WBS/SOW elements for the additional factors listed above and identified as specific to the product. Each WBS element will be evaluated for the factors and identify if (i.e.) new technology is being used. This evaluation will identify risk factors in these areas that are tied to a WBS/SOW element and traceable to a high level requirement.  Additional factors in the most simplistic sense, is the knowledge and lessons learned of the risk assessment team.  This process element permits open use of knowledge and experience.

### 3.5.3 Additional Risk Factors, Output:

Technical risk factors identified for WBS/SOW elements that are linked to the high level thresholds.

## 3.6 Develop Technical Risk List

### 3.6.1 Develop Technical Risk List, Input:

Technical risks derived from analogy review, WBS, critical technical process, and "Additional Factors" assessments.

### 3.6.2 Develop Technical Risk List, Description:

The risk list is a tool  (a concise list) of risk factors. The risk list enumerates (lists) all risks, which merit probability screening and are linked through WBS elements to requirement, goal and objective consequences. The risk factors are explicitly traceable to technical thresholds (KPPs or spec). A formal team risk review board will validate the risks.

### 3.6.3 Develop Technical Risk List, Output:

Technical Risk List of process and technical factors that are linked to program thresholds, goals and objectives via WBS/SOW elements

## 3.7 Technical Risk Likelihood/Consequence Screening

### 3.7.1 Technical Risk Likelihood/Consequence Screening, Input:

Technical risk list from previous process element.

### 3.7.2 Technical Risk Likelihood/Consequence Screening, Description:

The technical risk list contains risks that are linked to program thresholds, goals and objectives with their associated consequences. This step identifies the likelihood of that risk based solely on technical merit. This process element requires extreme knowledge and the capability for forethought by the assessment team. Since the likelihood of an event's occurrence is typically intricate to risk identification, this process may be exercised during the risk identification phase, thus permitting integration of risk identification and likelihood screening. As discussed earlier in this document, agreements as to the consequence of not achieving a technical requirement, goal, cost bogie, or other high level requirement identified by the program manager have already been performed.

Characteristics of the program such as ACAT level, phase/milestone decision point or simply PM's desires may impose a need for the output from the cost risk assessment to be a cumulative probability distribution of total cost.  On these occasions likelihood and consequence screening will have to provide likelihoods and consequences quantified beyond the numeric categories associated with the 5x5 risk cube/static risk reporting model.

For example, rather than simply identifying a risk as having a likelihood score of 3 with a consequence score of 2, likelihood must be expressed as a probability ranging from 0.0 - 1.0 and consequence must be expressed in units that can be translated into cost.  These efforts will of course be subjective in nature so the assistance of an experienced cost risk analyst may prove helpful.

The following tables can be utilized to execute likelihood/consequence screening:

| Likelihood Screening |
| --- |
| Level | Likelihood | Probability of Occurrence |
| 1 | Not Likely | ~10% |
| 2 | Low Likelihood | ~30% |
| 3 | Likely | ~50% |
| 4 | Highly Likely | ~70% |
| 5 | Near Certainty | ~90% |

Note:  Likelihood is addressed independent of consequence. The "5 " rating indicates to management activities outside of the PEOs that the program does not have resources to mitigate the risk and assistance, outside of the program, is required.

| Consequence Screening |
| --- |
| Level | Technical | Schedule | Cost |
| 1 | Minimal or no impact | Minimal or no impact | Minimal or no impact |
| 2 | Minor technical/supportability shortfall, no impact to KPPs, OPEVAL or COIs | Additional activities required, able to meet key dates. Slip < * month(s) | Budget increase or unite production cost increases < ** (1% of Budget) |
| 3 | Moderate technical/supportability shortfall may cause Part or Pri II or III deficiencies | Minor schedule slip, no impact to key milestones. Slip < * month(s) of critical path. Sub-system slip > * month(s). | Budget increase or unit production cost increase < ** (5% of Budget) |
| 4 | Major technical/supportability technical shortfall may cause Part or Pri I deficiencies | Program critical path affected, all schedule float associated with key milestone exhausted Slip < * months | Budget increase or unit production cost increase < ** (10% of Budget) |
| 5 | Cannot meet KPP or Key Supportability threshold | Cannot meet key program milestones Slip > * months | Exceeds APBA threshold > ** (10% of Budget) |

Note: All consequences relate to high level thresholds identified by the program manager.  Consequence of not achieving a high level requirement such as an ORD KPP or APB monetary or milestone threshold is a maximum consequence rating of "5", "Unacceptable".

* - Tailor for program in month(s)

** - Tailor for program in whole dollars

When applying the consequence screening technique identified above, it is essential to clearly define quantitative values for all of the subjective terms.  For example, the minor schedule slip item should be quantified in terms such as "3 month slip in items not on critical path", and the budget items should be quantified in terms of actual cost, for example budget increase of < 10% should be defined in terms of actual number such as $100K for a $1M program.

### 3.7.3 Technical Risk Likelihood/Consequence Screening, Output:

Technical risk list with likelihood of risk occurrence determined with associated consequence derived from the link to high level program requirements, goals or objectives.

## 3.8 Determine Risk Mitigation Alternatives

### 3.8.1 Determine Risk Mitigation Alternatives, Input:

- Decision from program manager on risk level required for risk mitigation alternative development

- Risk list

### 3.8.2 Determine Risk Mitigation Alternatives, Description:

Development of risk mitigation alternatives is the responsibility of the technical expertise on the program as well as the risk assessment team.  This element does not reflect the "decision" to pursue a given risk mitigation alternative, since the ultimate decision authority is relinquished to the authority of the program manager.  The process element addresses the need to develop a plan for likelihood reduction of the identified risk.  This process element is iterative and will undoubtedly require a great deal of research and analysis in some cases before a useful list of alternatives is generated. There are numerous techniques for risk mitigation development, but the basic philosophy for risk mitigation development addresses the following areas:

- Risk Avoidance - Elimination the source of the risk and replace with a lower risk solution

- Risk Transfer - Reallocation of the risk from one part of the system to another, or relocation of risks between the government and prime contractor or within government agencies

- Risk Control - Manages the risk in a manner that reduces the likelihood of occurrence and/or minimizes the risk's effect on the program

- Risk Assumption - Acknowledgement of the existence of a particular risk situation and a conscious decision to accept the associated level of risk without engaging in any special efforts to control it.

### 3.8.3 Determine Risk Mitigation Alternatives, Output:

- Risk mitigation alternatives for each risk (risk level provided by the program manager).  For risk control and/or assumption metrics will be identified for risk management purposes.  Metrics should be tied to either technical measures or schedule and cost values to facilitate program management.  Risk avoidance and/or transfer requires a level of re-planning that will usually facilitate a reassessment.

- The overall approval of a Risk Mitigation Plan is at the Program Managers level.  This will ensure that a mitigation plan for one area doesn’t have a counter productive effect on one or more other areas with in a program.

# Chapter 4: Schedule Risk Assessment Process

## 4.0 Schedule Risk Assessment Introduction

The schedule assessment process provides a means to determine program level schedule risk as a function of risk associated with the various activities that compose the program.  The schedule risks identified in this chapter are based on the technical risks derived during the technical risk assessment process within this handbook, comparison to analogous programs, and utilization of look-up tables for new technology efforts.  The analogous programs provide historical assessments of the estimates provided for the work to be accomplished.  Since new technology efforts provide schedule uncertainty in that the product has never been developed before, look-up tables provide a schedule reasonableness check as the program evolves through development.  The schedule risk assessment process is depicted in Figure 3.

Figure 3: Schedule Risk Assessment Process

## 4.1 Identify High Level Schedule Requirements

### 4.1.1 Identify High Level Schedule Requirements, Inputs:

High level schedule requirements

### 4.1.2 Identify High Level Schedule Requirements, Description:

In order to trace schedule events to program requirements the high level schedule requirements (e.g. milestones) should be identified.  This process element requires high level documentation to substantiate program schedule events/activities.

### 4.1.3 Identify High Level Schedule Requirements, Outputs:

High level schedule requirements

## 4.2 Analogy Review

### 4.2.1 Analogy Review, Input:

- BCS that very closely approximates the characteristics of the system, subsystems, or components, and uses very similar developmental and acquisition processes.

- High level schedule related requirements, e.g. milestone dates

### 4.2.2 Analogy Review, Description:

Optimally the system engineer and IPT should be involved in performance of this technique.  In most cases, the system developer could also perform this technique since the developer would posses the most experience with similar development efforts. This technique also leverages the lessons learned and expertise of the program team.

Critical path activities will be evaluated against analogous efforts. All activities/tasks will be evaluated for suitable scheduling to support the required effort. Activities may be identified here that have no previously identified technical risk but have schedule risk only. The team must determine the likelihood for schedule only risks at this point as well. Additionally items identified as technical risk should be evaluated for the schedule impact on the identified risk likelihood (i.e. more than sufficient slack may mitigate the technical risk identified, conversely risk likelihood may increase as a result of insufficient schedule). Utilization of new or COTS technologies will be further evaluated in the next step.

The risk assessment team will assess each of the schedule elements for which there is analogous information available.  Action items may also be assigned for completion of the effort offline in an attempt to obtain the most accurate information available.

### 4.2.3 Analogy Review, Output:

- Schedule risks based on comparison to similar system, subsystem, or component developments with likelihood, traceable through critical paths to either a high level technical or schedule consequence

- Technical risk list with likelihood modified by schedule impacts for analogous review

## 4.3 Apply Technical Assessment Results

### 4.3.1 Apply Technical Assessment Results, Input:

- Technical risks identified during WBS, process, and "Additional Factors" assessments

- High level schedule related requirements, e.g. milestone dates

### 4.3.2 Apply Technical Assessment Results, Description:

The technical assessment results will include risks identified due to insufficient time for completion of an effort. These technical risks have a direct correlation to the schedule risk assessment.  Since there is usually an end product required at a given point in time there is always a development risk.  Obviously, the development risk has a direct correlation to the difficulty of the development as well as the limitations on time for development.  Therefore, for most Navy programs, since there is a product completion or delivery date, there is an associated schedule risk.  If there was not a delivery date and the product had an unlimited development/delivery time, there would be no schedule risk.

The results of the technical risk assessment should be analyzed for inclusion in the overall program schedule risk assessment.

### 4.3.3 Apply Technical Assessment Results, Output:

Schedule risks based on technical risk assessment are included in schedule risk assessment.

## 4.4 Risk Readiness for New Technology/Commercial of the Self (COTS)

### 4.4.1 Risk Readiness for New Technology/COTS, Input:

- New Technology or COTS equipment identified during WBS assessment

- High level schedule related requirements, e.g. milestone dates

### 4.4.2 Risk Readiness for New Technology/COTS, Description:

For new technology and COTS components and devices no analogous program is readily available, consequently with no historical data upon which to evaluate schedule impact to technical risk a "Risk vs. Readiness" approach is used to assess the planned development.

Determine a point in program for readiness reference. Evaluate identified new technology or COTS risk from tables in appendix E to determine what the readiness state should be and assess against the actual readiness state. Utilize formula in appendix E with table derived values to determine risk due to readiness level and convert as shown to likelihood impact on new technology or COTS risk linked to high level performance requirement.

### 4.4.3 Risk Readiness for New Technology/COTS, Output:

Technical risk list with likelihood modified by readiness impacts for new technology and COTS.

## 4.5 Document Schedule Risk

### 4.5.1 Document Schedule Risk, Input:

Schedule risks resulting from execution of previous process elements

### 4.5.2 Document Schedule Risk, Description:

Compile a list of schedule risks identified in previous process steps with traceability to high level schedule and technical requirements. Assure all technical risk list items are evaluated and adjusted for schedule assessment with traceability to high level technical risk.

Characteristics of the program such as ACAT level, phase/milestone decision point or simply PM's desires may impose a need for the output from the cost risk assessment to be a cumulative probability distribution of total cost.  On these occasions likelihood and consequence screening will have to provide likelihoods and consequences quantified beyond the numeric categories associated with the 5x5 risk cube/static risk reporting model.

For example, rather than simply identifying a risk as having a likelihood score of 3 with a consequence score of 2, likelihood must be expressed as a probability ranging from 0.0 - 1.0 and consequence must be expressed in units that can be translated into cost.  These efforts will of course be subjective in nature so the assistance of an experienced cost risk analyst may prove helpful.

### 4.5.3 Document Schedule Risk, Output:

- Schedule risk list

- Modified technical risk list

# Chapter 5: Cost Risk Assessment Process

## 5.0 Cost Risk Introduction

The cost risk assessment quantifies risk associated with technical and schedule challenges. It also includes cost estimating risk, i.e., uncertainty associated with the cost estimating methodologies used to derive the initial program cost estimate.  Thus, cost risk is the quantification of technical, schedule, and cost estimating uncertainty.  The critical inputs for the cost risk assessment are the technical and schedule assessments.

The cost risk assessment aggregates cost risk for each of the WBS/SOW elements of the program into a total program risk cost.  The total cost estimate with cost risk, often referred to as the risk-adjusted program cost estimate, is usually expressed as a cumulative probability distribution.  The distribution shows the probability that the program can be completed for a specific dollar value or less, or what level of funding would be required to have a given probability of completing the program within cost.

The cost risk assessment process is depicted in figure 4.

Figure 4: Cost Risk Assessment Process

## 5.1 Define Scope and Purpose

### 5.1.1 Define Scope and Purpose, Input:

The following is a list of items used to define the scope and purpose of the cost risk assessment: type of program (ACAT level, new/upgrade, acquisition), how cost estimate is to be used (preliminary rough order-of-magnitude (ROM) estimate, Milestone review, baseline, rebaseline, budget, etc.), scope of estimate (life cycle, particular program phase(s)), cost and budgetary requirement, and required documentation (APBA, PMA memo, Cost Analysis Requirements Description (CARD)).

### 5.1.2 Define Scope and Purpose, Description:

The cost risk assessment is predicated on assessments of the program’s technical and schedule challenges and cost estimating methods. The detail (and accuracy) of the cost risk assessment will depend on its scope and purpose.  If the estimate and risk assessment support a Milestone review, baseline estimate or budget, the cost risk assessment will be performed in more detail and with more accuracy than it would be for a ROM estimate to support a trade study.  The level of detail and accuracy will also depend on which acquisition phase the program is in.  Obviously, there will be less detail and less accuracy at Concept & Technology Development than at Production and Deployment.

### 5.1.3 Define Scope and Purpose, Output:

The output from this process step will be top level descriptions of the acquisition effort, scope and intent of the cost risk assessment, and level of effort (detail, accuracy) required to perform the cost risk assessment.

## 5.2 Identify and Gather Data

### 5.2.1 Identify and Gather Data, Input:

The data required for cost risk assessment includes a detailed program description; relevant programmatic information and planning information at a level of detail commensurate with the current acquisition phase.  The MNS, ORD, APBA, CARD, or technical and programmatic baselines are needed too fully understand the program.  In addition, concept exploration studies, WBS, activity network(s), work package listings, parametric and bottoms-up cost models, financial constraints (budgetary, management reserve), and any relevant data on historical analogous program costs are useful.

The technical and schedule assessments described in chapters 3 and 4 are critical inputs to the cost risk assessment.  The more rigorous cost risk methodologies require that these assessments be quantitative in nature (probabilities and consequences) and capable of being mapped to the cost/work breakdown structure of the cost estimate.

##### Typical assessment questions.  Answers to the following questions may assist in identifying required information:

- Is a cost (or budget) not-to-exceed value for this acquisition available?  Is it documented? Is the audit trail for it available, or is it a note taken during the PMA Interview?

- Is the phasing of funds appropriate for the planned program execution?

- Are the data (or documentation) at hand sufficient to analyze and assess the cost risk for this acquisition for this phase?  If previous cost analysis work has been done on this program, is its accuracy sufficient to use as a baseline for this current effort?

- If the program is in the Program Definition and Risk Reduction (PDRR)/System Development and Demonstration phase or subsequent phases, does an accurate, credible WBS exist?  Is it derived from MIL-HDBK-881B?  Has it resulted in an activity network, and an accurate, credible Work Package (WP) set?  Can costs be discretely estimated and risks assessed based on this WP set?

- Have previous parametric cost models been run on this effort?  Does an engineering estimate (bottoms up) exist?

- Does the programmatic data provide sufficient detail to allow accurate assessments?

### 5.2.2 Identify and Gather Data, Description:

The sources of data required for the cost risk assessment are identified and the information/data are gathered.  Most of the information should be available in the program office.  Historical costs and cost growth data for analogous programs may be available in the Cost Department’s databases and Selected Acquisition Reports (SAR).

### 5.2.3 Identify and Gather Data, Output:

The output from this process step is all the information required to conduct the cost risk assessment.

## 5.3 Determine Potential Cost Risk Methodologies

### 5.3.1 Determine Potential Cost Risk Methodologies, Input:

The cost risk technique will be selected based on available information and purpose of the estimate.  The level of accuracy (detail) required for the cost risk assessment is determined by acquisition phase (more coarse-grained for earlier phases), purpose and scope of the cost estimate and risk assessment, and availability of source data identified in 5.2, “Identification and Gathering of Data.”

Typical assessment questions.  Answers to the following questions may assist in selecting a cost risk methodology:

- Does sufficient data exist to perform the cost risk assessment for this acquisition phase?  For the life cycle?

- Do the required tools exist for the analyses?  Is the skillset available for data and statistical analyses?  Is the analyst conversant and articulate in statistical procedures?

- If in earlier acquisition phases, can the cost be bounded within budget?  Does the documentation show an engineering estimate similar in value to the parametric estimate?

- If in the PDRR (System Development and Demonstration) phase or subsequent phases, does the documentation support an accurate, credible engineering estimate?

- Does the acquisition have a historical precedent within the same supplier organization?  Are there EVMS data available to substantiate the cost estimates?

- Will the cost risk estimation methodology support the PMA’s goals?  Is he or she aware of the limitations?

- Is this a risk averse acquisition?

Can the technical and schedule risk assessments be mapped to the baseline cost estimate?  Is the WBS used for the technical/schedule assessments consistent with the cost/work breakdown structure in the program cost estimate?

### 5.3.2 Determine Potential Cost Risk Methodologies, Description:

The various cost risk methodologies include analogous program cost growth comparisons, subject matter expert reviews, Method of Moments, Monte Carlo simulations, cost sensitivities of risk drivers, and other techniques.  A methodology should be chosen prudently, based on available data and PMA requirements.  Prediction accuracy has been shown to be a function of the time required to perform the cost risk assessment.  The Monte Carlo technique produces fairly accurate estimates in a reasonable amount of time.

### 5.3.3 Determine Potential Cost Risk Methodologies, Output:

The output from this process step is a cost risk methodology to be used for the cost risk assessment.

## 5.4 Analyze Data

### 5.4.1 Analyze Data, Input:

Data identified in 5.2, “Identification and Gathering of Data,” are analyzed in this step.  These data include: technical description, programmatic information, baseline cost estimate, baseline cost estimate methodologies, and cost risk methodologies.  In addition, an appropriate cost risk model/tool is needed.

Typical assessment questions.  Answers to the following questions may assist in analyzing data:

- Given the data available, can the scope of the assessment as determined during the PMA Interview be met?  Are more data required for the cost risk assessment?

- Can the cost estimator identify his/her confidence in the methodology used in preparing the baseline cost estimate?

- Is there anything lacking in either the technical assessment or schedule assessment inputs?

- Can the technical and schedule assessments be mapped to the cost elements in the cost estimate?

### 5.4.2 Analyze Data, Description:

The data are analyzed for applicability and relevance to the cost risk assessment’s scope and goals.  If sufficient data were not collected earlier, they should be researched and collected at this step.  All data are organized, normalized and prepared for use in the cost risk assessment.  Depending on the methodology chosen, this may include mapping of the technical and schedule risk assessments WBSs to the cost/work breakdown structure of the baseline cost estimate, and/or assessments of the cost analysts’ confidence in their models.

### 5.4.3 Analyze Data, Output:

The output from this process step is data that are organized, normalized, and made ready for the cost risk estimate.

## 5.5 Accomplish Cost Risk Estimate and Crosschecks

### 5.5.1 Accomplish Cost Risk Estimate and Crosschecks, Input:

Input required to accomplish the cost risk estimate and crosschecks includes: the chosen methodology from 5.3, “Determination of Potential Cost Risk Methodologies,” and the data collected and analyzed in 5.2,“Identification and Gathering of Data” and 5.4 “Analyze Data.”  Critical data include: the initial program or baseline cost estimate; an assessment of confidence in the cost estimate methodologies; and the technical and schedule risk assessments.  Crosschecks are made with historical program cost growth data.  If the Monte Carlo simulation method is used, an appropriate tool (e.g., Crystal Ball or @Risk) is needed.

### 5.5.2 Accomplish Cost Risk Estimate and Crosschecks, Description:

After the initial program/baseline cost estimate is complete and the technical/schedule assessments made, the cost risk is assessed.  The cost risk estimate is accomplished using the input noted above in 5.5.1 “Accomplish Cost Risk Estimate and Crosschecks.”  Of the potential cost risk methodologies noted in 5.3 “Determine Potential Cost Risk Methodologies,” the Monte Carlo technique produces fairly accurate estimates in a reasonable amount of time.  It produces a risk distribution around the program/baseline cost estimate based on technical, schedule, and cost estimating uncertainty—if input from the technical and schedule risk assessments are quantitative in nature.  An alternative method is to compare results of sensitivity analyses of the key cost risk drivers identified in the technical and schedule assessments to the analyst’s and subject matter experts’ scoring of the risks involved in the program.

Crosschecks are accomplished by comparing the cost risk estimate to cost growth experienced on similar NAVAIR programs.

### 5.5.3 Accomplish Cost Risk Estimate and Crosschecks, Output:

The output from this process step is a risk-adjusted program/baseline cost estimate.  It includes the initial program cost estimate plus the cost risk estimate based on risks identified in the technical, schedule, and cost estimating (methodology) assessments.  The risk-adjusted cost estimate can be expressed at various levels of confidence.  Use of the fifty- percent confidence level is typical in DoD cost estimating.

Crosschecks or comparisons of the risk-adjusted program cost estimate with cost growth experienced on similar NAVAIR programs are made.

## 5.6 Review Estimate with Risk and Present

### 5.6.1 Review Estimate with Risk and Present, Input:

The risk-adjusted cost estimate and cost growth experienced on similar NAVAIR programs are inputs to this process step.

### 5.6.2 Review Estimate with Risk and Present, Description:

The cost risk analysis including the overall approach, use of technical and schedule risk assessments, cost estimating risk assessment, cost risk methodology, and crosscheck/comparison to historical programs are reviewed by the IPT, refined, and presented to management.

### 5.6.3 Review Estimate with Risk and Present, Output:

The output from this process step is the risk-adjusted cost estimate.

## 5.7 Document Cost Risk Estimate and Integrate with TA and SA

### 5.7.1 Document Cost Risk Estimate and Integrate with TA and SA, Input:

Documentation includes the details of the technical and schedule risk assessments the approach for the cost risk assessment, and the risk-adjusted program cost estimate.  Background including the scope and purpose of the risk assessment and a description of the program are included.

Typical assessment questions.  Answers to the following questions may assist in documenting the cost risk estimate and performing an integrated risk assessment:

- How may technical risk and/or schedule risk be traded off for cost?  Is this feasible for this program?

- Is this acquisition CAIV driven (cost predominates)?  Is it “SAIV” (schedule is most important) driven?  Is it both CAIV and SAIV?  What can yield?

- How may these intricate risk interdependencies be best articulated to management?

- Given that the IPT is aware of the PMA’s goals (from the earlier PMA Interview), what is the recommendation to management?

### 5.7.2 Document Cost Risk Estimate and Integrate with TA and SA, Description:

The technical, schedule, and cost risk assessments are judged together.  Various programmatic, external issues may drive the relative risk weighting.  For example, if the acquisition is subject to the principles of cost as an independent variable (CAIV), then either schedule or technical issues may have to yield by way of a management decision.  Similarly, if the acquisition is schedule driven, then either technical issues or cost must yield (since schedule is fixed).  The task of the risk assessment team, at this point, is to root these issues out and prepare to present the risk interdependencies to management for decision.

### 5.7.3 Document Cost Risk Estimate and Integrate with TA and SA, Output

The output from this process step includes details of the Integrated Risk Assessment that are documented in narrative and/or briefing format and presented to management.

# Chapter 6: Risk Reporting

## 6.0 Risk Reporting Introduction

Reports are used to convey information to decision-makers and program team members on the status of risk and the effectiveness of risk handling techniques.  Risk related reports can be presented in a variety of ways, ranging from informal verbal reports to formal summary type reports presented at milestone reviews.  The level of detail presented will most assuredly depend on the audience.  The focus of this chapter is to provide standard reporting format and ground-rules for information included in risk reporting.

Risk analysis and reporting is best understood in the context of time. To analyze the risk and risk trend, we need to know what the risk was yesterday, what the risk is today, and what the risk is expected to be tomorrow.

The static risk chart shows what the current risk level is “Today”. The dynamic risk chart shows the risk’s trend “Yesterday”. The risk mitigation chart shows the risk mitigation plan “Tomorrow”.  Using these three graphical methods together will provide the IPT Lead, Program Manager, and ultimately the PEO/MDA a better depiction of risk magnitude, risk trend, and risk management effectiveness.  The reporting process is shown in figure 5.

Figure 5 - Risk Assessment Reporting Process

## 6.1 Static Risk Reporting

### 6.1.1 Static Risk Reporting, Inputs:

- High level program requirements

- Cost, schedule and technical risk assessment results

### 6.1.2 Static Risk Reporting, Description:

Static risk reporting will provide a depiction of present risk status.  The reporting scheme is based on a 5x5 cube presentation and incorporates a low (green), moderate (yellow), and high (red) risk color scheme by plotting risk likelihood and consequence.  The reporting scheme provides a "Quick Look" review of items of interest or that may require further management attention/oversight.  The Static Risk Reporting Model is given in figure 6.

The static risk depiction should display only the risk to high level requirements obtained from the program manager.  Information to support the risk to high level requirements should be presented on separate reports or explained on separate viewgraphs.  These supporting reports should use the format defined in Chapter 3.

#### Static Risk Reporting Model

Product Risk Evaluation and Reporting Guide Sheet

| Level | Likelihood | Probability of Occurrence |
| --- | --- | --- |
| 1 | Not Likely | ~10% |
| 2 | Low Likelihood | ~30% |
| 3 | Likely | ~50% |
| 4 | Highly Likely | ~70% |
| 5 | Near Certainty | ~90%. |

| Level | Technical | Schedule | Cost |
| --- | --- | --- | --- |
| 1 | Minimal or no impact | Minimal or no impact | Minimal or no impact |
| 2 | Minor technical/supportability shortfall, no impact to KPPs, OPEVAL or COIs | Additional activities required, able to meet key dates. Slip < * month(s) | Budget increase or unite production cost increases < ** (1% of Budget) |
| 3 | Moderate technical/supportability shortfall may cause Part or Pri II or III deficiencies | Minor schedule slip, no impact to key milestones. Slip < * month(s) of critical path. Sub-system slip > * month(s) | Budget increase or unit production cost increase < ** (5% of Budget) |
| 4 | Major technical/supportability technical shortfall may cause Part or Pri I deficiencies | Program critical path affected, all schedule float associated with key milestone exhausted Slip < * months | Budget increase or unit production cost increase < ** (10% of Budget) |
| 5 | Cannot meet KPP or Key Supportability threshold | Cannot meet key program milestones Slip > * months | Exceeds APBA threshold > ** (10% of Budget) |

Figure 6: Static Risk Reporting Model

### 6.1.3 Static Risk Reporting, Output:

Figure 7, depiction is in accordance with the aforementioned format to identify risk and a reporting format to include mitigation plans.

#### Figure 7: Static Risk Reporting Output

## 6.2 Dynamic Risk Reporting

### 6.2.1 Dynamic Risk Reporting, Input:

- Previous static risk information

- Current static risk reports

### 6.2.2 Dynamic Risk Reporting, Description:

Dynamic risk reporting will provide a depiction of present and past risk status.  The report provides a historical trend perspective of risks for management.  The report provides the evolution of a risk.

The dynamic risk report should be developed with consequence and likelihood on the x and y axis respectively.  The dynamic risk report should display only the risk to high level requirements obtained from the program manager. Each data point on the dynamic risk chart represents the information in one risk cube from previous or present static risk reports. Each dynamic risk chart can depict about 5 risks, without becoming too cluttered. Although it is recommended that no more than 5 historical points are included, it would be reasonable to include more data points due to specific requests from management. Note that KPPs always have a consequence (of non-attainment) of "5", unacceptable". Information to support the risk to high level requirements can be presented on separate reports or explained on separate viewgraphs.

### 6.2.3 Dynamic Risk Reporting, Output:

Report depicting historical trend of risks.  The figure 8 depicts that likelihood can be changed for high level program requirements while the consequence of failure remains the same.  The depiction also indicates how goals can be handled differently for reporting purposes.

Figure 8: Dynamic Risk Depiction

## 6.3 Program Risk Mitigation Waterfall Chart

### 6.3.1 Program Risk Mitigation Waterfall Chart, Inputs:

- Risk mitigation activities

- Risk mitigation activity schedule

- Program Milestone dates

### 6.3.2 Program Risk Mitigation Waterfall Chart, Description:

#### Managers not only need to know risks but also need to know plans for risk likelihood reduction and the status of those plans.  The risk mitigation waterfall chart is designed to provide that communication.  Simply identifying risk is not an end result but ultimately implementing activities (if required) to reduce the probability of occurrence is also advisable.

#### The risk mitigation waterfall chart should be developed with time (including FYs, CYs, or milestone reviews as appropriate) and risk likelihood on the x and y axis respectively.  The risk mitigation activities should then be depicted on the chart via bars.  The bars are colored to represent activities completed and white representing activities yet to be accomplished. The risk mitigation planning chart is a waterfall depiction of the activities, which compose the plan to mitigate the unacceptable risks (details in risk mitigation plan), and the expected result (risk lowering). One mitigation chart per risk is necessary. Note that for KPPs, you may only mitigate likelihood (not consequence).

### 6.3.3 Program Risk Mitigation Waterfall Chart, Output:

An example, of a Risk mitigation plan depicting likelihood reduction via planned/executed activities, can be seen in figure 9.

Figure 9: Mitigation Waterfall Chart

# Appendix A

Product Risk Evaluation and Reporting Guide Sheet

| Level | Likelihood | Probability of Occurrence |
| --- | --- | --- |
| 1 | Not Likely | ~10% |
| 2 | Low Likelihood | ~30% |
| 3 | Likely | ~50% |
| 4 | Highly Likely | ~70% |
| 5 | Near Certainty | ~90%. |

| Level | Technical | Schedule | Cost |
| --- | --- | --- | --- |
| 1 | Minimal or no impact | Minimal or no impact | Minimal or no impact |
| 2 | Minor technical shortfall, no impact to high level technical requirements | Additional activities required, able to meet key dates.Slip <__ month(s) | Budget increase or unite production cost increases <__(1% of Budget) |
| 3 | Moderate technical shortfall but workaround available which will eliminate impact to high level technical requirements | Minor schedule slip, no impact to key milestones. Slip < __month(s) of critical path. Sub-system slip > __ month(s). | Budget increase or unit production cost increase < __(5% of Budget) |
| 4 | Unacceptable, workarounds available which will eliminate impact to high level technical requirement | Program critical path affected, all schedule float associated with key milestone exhausted Slip < months | Budget increase or unit production cost increase < __(10% of Budget) |
| 5 | Unacceptable, no alternative exist | Cannot achieve key program milestones | Budget increase or unit production cost increases > __(10% of Budget) |

# Appendix B

Technical Risk Assessment Agenda

Agenda Items

- Program Overview

  - Key Performance Parameters (KPPs)

  - Schedule

- Team Organization

  - Government

  - Contractor

- System Overview

  - System Requirements

  - Constraints

- Configuration Item Breakout

  - Major Physical Interfaces

  - Major Functional Interfaces

- Process Overview

  - Program Management

  - Configuration Management

  - Systems Engineering and Trades

  - Logistics, Integrated Logistics Analysis Status

- Requirements Management

  - Risk Management

  - Software Management, Software Metrics

  - Test Planning (Lab, Ground, Flight; DT, OT)

  - Major Facilities/Tools

- Configuration Item (CI) Review (review the below topics for each hardware and software CI)

  - CI Design Status Versus Allocated Requirement

  - Performance (KPPs and Derived Requirements)

  - Interoperability

  - Reliability, FMECA

  - Maintainability

  - Supportability

  - Producibility/Manufacturing Engineering/Qualifying Process

  - Constraints (Weight/Balance/Volume/Power/etc.)

  - Physical and Functional Interface Requirements

  - Environmental Affects

  - EMI/EMC

  - Man-Machine Interface

  - System Safety Assessment

  - Parts/Materials Selection

  - Built-in Test, Fault Isolation

  - Development Test Status, Operational Test Status

  - Logistics

    - LSA

    - Maintenance Plans

    - Manpower/Personnel

    - Support and Test Equipment

    - Training

    - Kitting Provisions

    - Fleet Introduction

    - Spares

    - Publications/Technical Documentation

- Production Risk Assessment

- OT Risk Assessment

PROPOSED GOVERNMENT REVIEW BOARD

| Name | Code | Function |
| --- | --- | --- |

REQUEST FOR ACTION CHIT

| RFA INITIATOR | TYPE: (SRR (PDR (CDR (Other: | ASSIGNMENT: (RFA (RFI (Minutes/Action |
| --- | --- | --- |
|  | SUBJECT/TITLE: | SUBSYSTEM PANEL: | REQUEST NO: |
|  | REFERENCED DOC: |
|  | SPECIFIC PROBLEM OR CONCERN: |
|  | RECOMMENDED ACTION: |
|  | RECOMMENDED CATEGORY: | RECOMMENDED URGENCY/DATE: |
|  | INITIATOR’S NAME: IPT: | ACTIVITY/CODE/PHONE: | DATE: |
| IPT RESPONSE | PROPOSED ACTION: |
|  | PROPOSED SCHEDULE: |
|  | RECOMMENDED CATEGORY: | RECOMMENDED URGENCY/DATE: |
|  | ENGINEER’S NAME: | FUNCTION/DEPT/PHONE: | DATE: |
| EXECUTIVE SESSION | EXECUTIVE REVIEW AND DECISION: |
|  | ASSIGNED CATEGORY: | ASSIGNED URGENCY/DATE: |
|  | IMPACT: |
|  | PROGRAM REPRESENTATIVE: DATE: | CONTRACTOR REPRESENTATIVE: DATE: |
|  | DRB DIRECTOR: DATE: |

# Appendix C

{{INSERT PROGRAM TITLE}} RISK RE-BASELINE

"RISK ASSESSMENT PLAN"

Insert Team LOGO

DISTRIBUTION STATEMENT A.  Approved for public release; distribution is unlimited.

FOREWORD

#### 1. This plan shall be used for the execution of a limited duration {{INSERT PROGRAM TITLE}} program technical risk assessment.

2.  Beneficial comments (recommendations, additions, and deletions) and any pertinent data, which may be of use in improving this document, should be addressed to: {{Insert Name & E-Mail Address of Risk Assessment Coordinator}}

TABLE OF CONTENTS

1.0 INTRODUCTION	4

2.0 PROGRAM SUMMARY	4

3.0 RISK RELATED DEFINITIONS	4

4.0  RISK MANAGEMENT STATUS AND STRATEGY	5

5.0 RISK ASSESSMENT ORGANIZATION	5

6.0 RISK Assessment PROCEDURES	7

7.0 {{INSERT PROGRAM TITLE}} Risk Evaluation Process	10

8.0 {{INSERT PROGRAM TITLE}} TECHNICAL Risk Documentation Requirements	10

9.0 Formal Brief	12

RISK ASSESSMENT PLAN FOR THE {{PROGRAM TITLE}} RISK RE-BASELINE

1.0 INTRODUCTION

### 1.1 Purpose and Objective.

This Risk Assessment Plan (RAP) presents the process for executing a comprehensive and proactive risk assessment. A technical risk assessment is a program management tool to identify events that might adversely impact the program, thereby increasing the likelihood of success.  This RAP describes a process that will:

	Serve as a basis for identifying alternatives to achieve project product and schedule goals

	Assist in making decisions on project execution,

	Provide risk information for project reporting requirements, and

	Provide a program risk baseline that will provide the basis for monitoring the health of the project as it proceeds.

This RAP describes methods for assessing (identifying and analyzing) risks.  It prescribes the risk identification, evaluation, documenting and reporting processes to be followed.

2.0 PROGRAM SUMMARY

### 2.1 Description.

{{Insert Description of Program}}

3.0 RISK RELATED DEFINITIONS

### 3.1 Risk Management.

Risk Management is the act or practice of controlling risk. It includes risk planning, assessing risk areas, developing risk-handling options, monitoring risks to determine how risks have changed, and documenting the overall risk management program.

### 3.2 Risk.

Risk is a measure of the inability to achieve overall program objectives within defined schedule and technical constraints and has two components: (1) the probability of failing to achieve a particular outcome and (2) the consequences of failing to achieve that outcome.

### 3.3 Schedule Risk.

The risk associated with the adequacy of the time estimated and allocated for the execution of the program.  Two risk areas bearing on schedule risk are: the risk that the schedule estimates and objectives are realistic and reasonable; and the risk that program execution will fall short of the schedule objectives as a result of failure to mitigate risks.

### 3.4 Risk Rating.

This is the value that is given to a risk event (or the project overall) based on the analysis of the likelihood/probability and consequences of the event.  Section 6.2 gives guidance on determining likelihood and consequences and defines the criteria.

4.0 RISK MANAGEMENT STATUS AND STRATEGY

### 4.1 Risk Management Status.

The {{INSERT PROGRAM TITLE}} program has implemented a program risk assessment board (PRAB) process whereby risks are identified and analyzed by the IPT and then transitioned to the PRAB for further review and mitigation planning. The risk assessment results which were identified as part of the {{INSERT PROGRAM TITLE}} specific risk management process as of {{Insert date of last assessment or risk management board meeting}} are located on the {{INSERT PROGRAM TITLE & Web-site/server where risk information is located}}

### 4.2 Risk Management Strategy.

The {{INSERT PROGRAM TITLE}} risk management strategy is to handle program risks before they become problems and cause serious project impacts.  This strategy influences the project execution approach, and therefore is being used as a tool to re-baseline the program in a fashion that addresses risk.  The {{INSERT PROGRAM TITLE}} program team will continuously and proactively assess technical risk areas to identify and analyze specific risks, and will develop options to mitigate all risks designated as moderate and high.  The {{INSERT PROGRAM TITLE}} program manager will also identify the resources required to implement the developed risk-handling options.  The program manager, through coordination with the {{INSERT PROGRAM TITLE}} integrated product team (IPT) and within the constraints of the {{INSERT PROGRAM TITLE}} PRAB Process, will review and approve the risk mitigation options.  Once approved, the options will be incorporated into the program master schedule.  The program manager, via coordination with the IPT, will monitor the effectiveness of the selected handling options, and adjust the risk handling approach as necessary.

5.0 RISK ASSESSMENT ORGANIZATION

### 5.1 Responsibilities.

### 5.1.1 Risk Assessment Coordinator (RAC).

The RAC is the overall coordinator of the {{INSERT PROGRAM TITLE}} technical risk assessment and is responsible for:

- Maintaining this Risk Assessment Plan

- Coordination with the {{INSERT PROGRAM TITLE}} program manager, {{INSERT PROGRAM TITLE}} IPT, and the NAVAIR competencies to identify product and functional leads for the assessment

- Development and maintenance of an overall {{INSERT PROGRAM TITLE}} technical risk assessment plan of action and milestones (POA&M)

- Coordinating risk assessment results with the program manager

- Coordinate preparation of  risk briefings, reports, and documents required for the final assessment out-brief

- Participate as part of the {{INSERT PROGRAM TITLE}} Leadership IPT

5.1.2 {{INSERT PROGRAM TITLE}} Technical Risk Assessment IPT Leads.

The technical risk assessment IPT structure is depicted in figure I.

Figure I: Technical Risk Assessment IPT Technical Review Team Leader (TRTL) Organization

### 5.1.2.1 IPT Technical Review Team Leader (TRTL).

The IPT TRTL is the coordinator of the {{INSERT PROGRAM TITLE}} technical risk assessment in designated subject matter areas and is responsible for:

- Evaluating the technical and schedule risk of the product/process under team cognizance

- Coordination with the {{INSERT PROGRAM TITLE}} program manager, {{INSERT PROGRAM TITLE}} IPT, {{Insert System Developer}}, functional teams, and the NAVAIR competencies to populate teams for the assessment

- Development of a POA&M for the technical risk assessment execution for the product/process under team cognizance

- Coordinating risk assessment results with the RAC

- Coordinate preparation of  risk briefings, reports, and documents required for the final assessment out-brief

- Up front planning of fact finding meetings to include development and dispersal of meeting agenda and meeting preparation instructions to include documentation and process information review requirements, etc.

- Development of risk "fact finding" questions to be utilized during the meeting

- Chair/execute technical risk fact finding meetings

- Provide status and updates to Executive IPT

- Provide out-brief at the conclusion of the technical risk assessment

6.0 RISK Assessment PROCEDURES

The {{INSERT PROGRAM TITLE}} risk re-baseline will use a structured risk identification and evaluation approach consisting of three elements; planning, assessment, reporting.  These elements and the general procedures to be used for each of them are described in subsequent paragraphs of this section.

### 6.1 Risk Planning.

Risk planning is essential for the execution of a successful risk assessment program. This RAP serves as the basis for all detailed risk planning for the duration of the assessment. The {{INSERT PROGRAM TITLE}} Technical Risk Assessment Execution Schedule follows:

### 6.2 Risk Assessment.

The risk assessment process includes the identification of critical risk events/processes, the analyses of these events/processes to determine the likelihood of occurrence and consequences of the risks.  The following paragraphs describe the process to be followed in assessing risks.

### 6.2.1 Risk Identification.

The technical review team (TRT) will review all aspects of the project requirements to determine the critical events that would prevent the project from achieving its objectives.  The team will apply knowledge, best judgment, information sources identified by the "Draft" NAVAIR Risk Handbook, and lessons learned from similar programs to identify risk "fact finding" questions. The TRT should follow the following general procedures as a guide in identifying risk events:

### 6.2.1.1 Review Program Requirements.

The program documents that form the basis of the {{INSERT PROGRAM TITLE}} technical risk assessment include:

- Schedule - Dated {{Insert Program Master Schedule}}

- Operational Requirements Document (ORD) - {{Insert Reference Information}}

- Statement of Work (SOW) - {{Insert Reference Information}}

- {{INSERT PROGRAM TITLE}} TEMP - {{Insert Reference Information}}

Note: All of the aforementioned documents are available on the {{INSERT PROGRAM TITLE}} Web site https://pma-299-0.navair.navy.mil/index.html) except those, which are classified.  The classified documents, i.e. ORD, will be available at {{INSERT PROGRAM TITLE}} program office.  Requests for document review should be coordinated with {{Insert name of phone number of POC for classified information review}}.

### 6.2.1.2 Identify Technical Risks

The teams will identify technical risk in a face-to-face meeting forum whereby a question based fact finding process is invoked.  The process is relatively informal but will require team discipline to execute.  The technical assessment will address risk associated with the design concept and the development processes.

### 6.2.1.3 Review WBS/SOW Work Packages.

The WBS/SOW will be reviewed to determine if identified risks are worsened by the current tasking via assessment of:

- Scope

- Earned value

- Schedule

- Staffing

7.0 {{INSERT PROGRAM TITLE}} Risk Evaluation Process

All risks will be evaluated (likelihood & Consequence Screening) in accordance with the criteria set forth in the {{INSERT PROGRAM TITLE}} risk evaluation process.  The risk evaluation process is provided in appendix A.

8.0 {{INSERT PROGRAM TITLE}} TECHNICAL Risk Documentation Requirements

### 8.1 Risk Database Information.

The following risk information shall be collected and recorded in Microsoft Excel format by each risk assessment IPT. The information will be due at the time of the scheduled IPT formal out-brief. The excel spreadsheet provides a compatible format for entry of the risk specific data into the {{INSERT PROGRAM TITLE}} Program Risk Database.

Table I: Risk Information To Be Collected Via Excel Spreadsheet

| Risk Database Column Title | Description of Entry |
| --- | --- |
| Risk # | Number of risk for risk assessment IPT tracking purposes ({{INSERT PROGRAM TITLE}} PRAB will generate tracking number once the risk is incorporated into the database) |
| Title | Descriptive Title of the risk to be identified. The title should be self explanatory in nature and provide sufficient information to enable the risk to be transitioned to the appropriate {{INSERT PROGRAM TITLE}} IPT discipline. |
| Technical Risk Description | Provide a detailed description of the risk (ASSURE TRACEABILITY TO HIGH LEVEL REQUIREMENT (S)). The risk should be stated per the following example: "If the acoustic rack cooling flow is not high enough, ...." or "If SAC doesn't deliver the aircraft ICDs, then ....." |
| Schedule Risk Description | Provide a detailed description of the risk (ASSURE TRACEABILITY TO HIGH LEVEL REQUIREMENT (S)). |
| Cost Risk Description | Provide a detailed description of the risk (ASSURE TRACEABILITY TO HIGH LEVEL REQUIREMENT (S)). |
| Status | All risks identified during the {{INSERT PROGRAM TITLE}} risk re-baseline effort will have a status of "Open" |
| Cause of Risk | Describe the cause or reason for the risk. For example, the cause associated with a risk of low rack cooling flow might be that the duct flow area is potentially insufficient. |
| Failure Mode | Identify the program (ORD KPP and APB schedule milestones) and the product level impacts of the realized risk. An example might include non achievement of ESM Detection KPP, delay to MSIII decision, or noncompliance with performance specification paragraph XXXX. |
| Likelihood | Determine based on {{INSERT PROGRAM TITLE}} Risk Evaluation Criteria (Appendix A). |
| Technical Consequence | Determine based on {{INSERT PROGRAM TITLE}} Risk Evaluation Criteria (Appendix A). |
| Schedule Consequence | Determine based on {{INSERT PROGRAM TITLE}} Risk Evaluation Criteria (Appendix A). |
| Cost Consequence | Determine based on {{INSERT PROGRAM TITLE}} Risk Evaluation Criteria (Appendix A). |
| Initiated By | List the I individual who identified the risk |
| Date Identified | List the date the risk was documented |
| Initiator Phone Number | List the phone number of the individual who identified the risk |
| Program Area | Identify whether the risk is categorized as a performance, schedule, or cost risk |

### 8.2 Work Package Information

Results of identified deficiencies associated with the {{INSERT PROGRAM TITLE}} SOW for {{Program Phase}} work packages in areas deficient in appropriate work scope, schedule, or staffing. Also determine the need for additional work packages in order to reduce an identified risk.   This information will be documented in the IPT formal out-brief.  The formal brief format will be discussed in subsequent sections of this document.

9.0 Formal Brief

A formal brief will be required by each IPT at the conclusion of the risk assessment effort.  The brief will provide {{Insert name of Program Manager}} ({{INSERT PROGRAM TITLE}} Program Manager) with visibility into the process execution as well as the status of the {{INSERT PROGRAM TITLE}} program as it relates to technical, schedule, and cost (executability) risks.  The brief will also address recommended SOW updates/modifications/deletions as well as any other risk mitigation alternatives.  The format for the formal brief is included in appendix B.

# Appendix D

{Insert Program Name} Risk Summary Work Sheet

Risk Title _______________________________ Risk # _______ Updated _______

Submission to PRAB: Date ____________ Initiator ____________________________________ Phone #__________ Risk Type (Check one) ____Technical ____Schedule ____Cost Description of Risk ____________________________________________ Assessed Risk Likelihood #____/Consequence # ____

| PRAB Disposition Date _____________ ___Accepted-Recommended Metrics ______ Accepted Assessed Risk L/C ___Reassessed Risk Likelihood #______/Consequence # ______ ___Mitigate Metrics _____________________________________________________ ___Transfer to___________________________________________________________ ___Avoid Consequence if Risk is Realized - ____Technical ____Schedule _____Cost (Risk Failure Mode in relation to ORD/APB requirement) | Risk Phase (Check one) ____ EMD II ____ TECHEVAL ____ LRIP ____ OPEVAL ____ Other _____ |
| --- | --- |
| Suggested Risk Likelihood Reduction Plan |
| Action/Event | Date | Success/Metrics Criteria | Risk Level if Successful | Comments |
|  | Scheduled | Actual |  | C | L |  |

# Appendix E

Risk vs. Readiness

Risk versus readiness is utilized when no analogous review can be conducted due to the nature of the technology, effort or experience level of the developer. Risk versus readiness allows the risk assessor to evaluate the technology or effort in the context of where the program needs to be in relation to where the program is. This is a monitoring assessment technique tied to program milestones that will identify when mitigation needs to be performed by the risk manager.

The risk versus readiness approach is based on identification of where the program should be (based on milestones) and a table lookup of the technical status, both real and required. Deltas in the snapshot status and the program milestone required status are realized as a schedule risk modifier to the technical risk. This applies to both the development of new technology to support requirements as well a utilization of Commercial off-the-shelf (COTS) components. The COTS aspect utilizes a graduation from state of the art to true in-service availability and environmentally qualified.

This is a systematic approach to identify, assess and control the schedule impacts to technical readiness and risk issues of the acquisition process. Assessments of readiness and risk by program experts are combined in a mathematical value representing a percent readiness for new or COTS technology elements. The current status of these elements are evaluated with respect to their readiness to meet the acquisition phases shown in figure 1.

Figure 1-Acquisition Phase Readiness

The phases and the number line associated with Figure 1 can be utilized with the following table data to evaluate the schedule impact (or readiness aspect) of the technical risks elements identified by the risk assessment/management team. The elements can be evaluated utilizing the following factors for identification and assessment of readiness.

Comparison of current state to program success criteria

- Technology

- Design Maturity

- Manufacturing

The readiness level value for where you should be is derived from the number line and acquisition phase in figure 1. The current state is selected from the appropriate readiness table. Risk criteria tables are included that address not only schedule, but technical and cost evaluation criteria. The technical evaluation criteria can be utilized to validate the technical evaluation determined likelihood and the cost is included for information purposes only at this time.

The current state is derived from the following tables. The technical state modifiers are selected from the readiness table based on the current state and a nominal risk value for calculation purposes is selected from the appropriate risk table.

| Readiness | Technology Evaluation Criteria | Level Value |
| --- | --- | --- |
| V-Low | Conceptual Principle | 0 |
| Low | Basic Principle Observed and Reported | 1 |
| Low | Conceptual Design Formulated | 2 |
| Low | Concept Tested Analytically or Experimentally | 3 |
| Medium | Critical function or Characteristic Demonstrated | 4 |
| Medium | Component or Breadboard Tested in Relevant Environment | 5 |
| High | Prototype or Engineering Model Tested in Relevant Environment | 6 |
| High | Engineering Model Tested in Actual Environment | 7 |
| V-High | Operational Deployment | 8 |

| Risk | Technology Risk Evaluation Criteria | Level Value |
| --- | --- | --- |
| Low | Technology has been used on other systems Alternatives and other workarounds are available Parallel Development Programs are Possible Critical Path and Downstream Milestones not affected | 1 |
| Medium | Technology exists but has not been in a system Alternatives and workarounds are possible but not developed Resources and schedule for parallel development are marginal Critical path and downstream milestones affected Subelement slip requires workaround | 1.5 |
| High | Technology must be developed Alternatives and workarounds do not exist Parallel development programs not possible Significant critical path impact, serious impact to milestones | 2 |

| Readiness | Design Maturity Evaluation Criteria | Level Value |
| --- | --- | --- |
| V-Low | Design Undocumented | 0 |
| Low | Design Formulated at Conceptual Level | 1 |
| Low | Mass Properties, Aero Data and Design Traceable to Requirements | 2 |
| Low | PDR Suitable Design | 3 |
| Medium | Engineering Mock-Up Constructed | 4 |
| Medium | Brassboard Full-Scale Engineering Model | 5 |
| High | Prototype Design Flown | 6 |
| High | Engineering Model Tested in Actual Environment, Qual Complete | 7 |
| V-High | LRIP Produced and Flown | 8 |

| Risk | Design Maturity Risk Evaluation Criteria | Level Value |
| --- | --- | --- |
| Low | Similar design flown at or beyond conditions for proposed design. Design techniques required within proven theory and practice for all major components and subcomponents. Engineering design and safety margins realizable without compromising operational performance Critical path and downstream milestones not affected | 1 |
| Medium | State of the art design techniques required Engineering design and safety margins relaxed to prevent compromise of operational performance Design manageable without fully integrated CAD/CAM Critical path and downstream milestones affected Subelement slip requires workaround | 1.5 |
| High | Test confirmation not possible with available facilities Integrated CAD/CAM required for design complexity Simulation experience or supporting data bases do not span the design operating conditions Significant critical path impact, serious impact to milestones | 2 |

| Readiness | Manufacturing Evaluation Criteria | Level Value |
| --- | --- | --- |
| V-Low | Manufacturing Concepts | 0 |
| Low | Early Materials Trade Studies and Requirements Analyzed | 1 |
| Low | Definition and Process Development Complete | 2 |
| Low | Pilot Product Demonstrated | 3 |
| Medium | Manufacturing Flows, Producibility, Process Capability Analyzed | 4 |
| Medium | Production Facility Designed | 5 |
| High | LRIP | 6 |
| High | Multiple Production Facilities in Operation | 7 |
| V-High | Surge and Mobilization Capability Exists | 8 |

| Risk | Manufacturing Risk Evaluation Criteria | Level Value |
| --- | --- | --- |
| Low | Current production facilities in operation and operating below capacity Trained manpower available, supply exceeds demand Materials/Components available Critical Path and Downstream Milestones not affected | 1 |
| Medium | New facilities required to meet demand, capital investment available Trained manpower in short supply Materials/components in short supply Critical path and downstream milestones affected Subelement slip requires workaround | 1.5 |
| High | Pilot production has not been demonstrated, demand justifies capital investment required Trained manpower not available, must train new personnel Materials/components not available, must find new supply Significant critical path impact, serious impact to milestones | 2 |

The values for:

Required – from number line evaluation of program requirement

Current – derived from table of actual state

Risk – derived from table based on actual state

Are then entered into the following formula for calculation:

The calculated value will be between 1.0 and –1.0. A negative value represents a high risk. Other values can be converted to the five likelihood blocks of the standard risk cube as follows.

| Risk/Readiness Calculation | Risk Cube Likelihood |
| --- | --- |
| 0.0 –0.20 | 5 |
| 0.21-0.40 | 4 |
| 0.41-0.60 | 3 |
| 0.61-0.80 | 2 |
| 0.81-1.00 | 1 |

In this way the schedule (current and actual) for non-analogous development can have the identified technical risk evaluated for the readiness state.

# Text boxes

Planning

IPT

Training

Risk Assessment

Risk Reporting

Performed Simultaneously

Identify High Level Technical Requirements

Analogy Review

Bottoms-Up WBS Review

Critical Technical Process Review

Determine Risk Mitigation Alternatives

Additional Factors Analysis

Develop Technical Risk List

Technical Risk Screening

Identify High Level Schedule Requirements

Analogy Review

Apply Technical Assessment Results

Apply Risk/Readiness to New Technology

Document Schedule Risk

Define Scope & Purpose

Identify & Gather Data

Determine Potential Cost Risk Methodologies

Analyze Data

Accomplish Cost Risk Estimate & Crosschecks

Review Estimate with Risk & Present

Document Cost Risk & Integrate with TA and SA

High Level Risk Reporting

Static Risk Reporting

Program Risk Mitigation Waterfall Chart

Dynamic Risk Reporting

5

#### Likelihood

1

2

3

4

1

2

3

4

5

Likelihood

Consequence

##### Consequence

Risk:

Mitigation:

Risk:

Mitigation:

Risk:

Mitigation:

5

4

3

2

1

1

2

3

4

5

9/99

3/00

9/99

12/99

12/99

3/00

1            2           3          4        5

CONSEQUENCE

(KPP EXAMPLE)

(GOAL EXAMPLE)

LIKELIHOOD

1		2		3		4        5

RISK LIKELIHOOD

1             2           3           4           5

MITIGATION PLAN for RISK LIKELIHOOD

PD&RR              EMD                    LRIP        PROD

CY 99		00		01		02		03

TIME/PHASE

Completed     Planned

Activity #1

Activity #2

Activity #3

Activity #4

Activity #5

MS II

MS III

CDR

1

2

3

4

5

1

2

3

4

5

#### Likelihood

Likelihood

Consequence

##### Consequence

Executive IPT

Insert Appropriate POC

Software IPT

Insert Appropriate POC

Air Vehicle IPT

Insert Appropriate POC

Weapons/SAS Offensive IPT

Insert Appropriate POC

Radar IPT

Insert Appropriate POC

Core Avionics IPT

Insert Appropriate POC

Acoustic IPT

Insert Appropriate POC

Mission Support IPT

Insert Appropriate POC

Program Management IPT

Insert Appropriate POC

Training IPT

Insert Appropriate POC

Systems Engineering IPT

Insert Appropriate POC

Month 5    6    7    8    9       12  13  14 15  16         19  20  21  22  23      26  27  28  1    2          5  6

Execution Schedule

Program Management

Systems Engineering

Air Vehicle

Software

Weapons/SAS Offensive IPT

Mission Support

Acoustics

Core Avionics

Radar

Training

Cost

Review

Formal Reviews

Report

Note: Red Bar Denotes No Schedule Submitted at the time of this printing

Review Program Requirements

Identify Technical Risks Based on The Current System Concept, Acquisition Approach and Processes

Review WBS/SOW Work Packages

1

2

3

4

5

1

2

3

4

5

Likelihood

11

2

3

4

5

11

2

3

4

5

Likelihood

Consequence

Consequence

Technology Opportunities & User Needs

FOC

0

1

2

3

4

5

6

7

8

IOC

Concept &

Technology

Development

Operations

&

Support

IOT&E

FRP

Production & Deployment

System Development & Demonstration

A

B

C

(

)

(

)

)

,

(

Risk/

Readiness

= 1

Projected Value of Readiness/Risk for a Single Element at a Future Milestone

Minimum

Risk Value in Table

Minimum

Readiness

Value at

Milestone

- Lower of:

Minimum

Readiness

Value at

Milestone

Assessed

Readiness Level

Minimum

Risk

Value in

Table

Minimum

Readiness

Value at

Milestone