COMPLIANCE IS MANDATORY

| Responsible Office: |  | 500/Applied Engineering and Technology Directorate |
| --- | --- | --- |
| Title: | DESIGN DEVELOPMENT |  |

# Preface

P.1     PURPOSE

This procedure establishes the process for providing design input, for generating design output, for performing design verification, and for handling design changes that occur as the result of design verification and/or product validation.

P.2     APPLICABILITY

This procedure applies to the development of all Goddard Space Flight Center (GSFC) products and processes covered by the scope of the GSFC Management System.

P.3     AUTHORITY

NPD 1280.1, NASA Management System Policy

P.4     APPLICABLE DOCUMENTS

GPR 1310.1, Customer Commitments and Review

GPR 1410.2, Configuration Management

GPR 1710.1, Corrective and Preventive Action

GPR 5330.1, Product Processing, Inspection, and Test

GPR 7123.1, Systems Engineering

GPR 8070.2, Identification and Application of Statistical Techniques

GPR 8700.1, Design Planning and Interface Management

GPR 8700.3, Design Validation

GPR 8700.4, Integrated Independent Reviews

GPR 8700.6, Engineering Peer Reviews

500-PG-3410.2.1, Basic Adhesive Bonding Certification

500-PG-8700.2.5, Engineering Drawing Requirements Manual

500-PG-8700.2.7, Design of Space Flight Field Programmable Gate Arrays

500-PG-8700.2.8, Field Programmable Gate Array Development Methodology

540-PG-8072.1.2, Mechanical Fastener Torque Guidelines

541-PG-8072.1.2, Goddard Space Flight Center Fastener Integrity Requirements

P.5     CANCELLATION

GPR 8700.2E, Design Development

P.6     SAFETY

Safety is an important consideration that shall be addressed in all phases of design development with particular emphasis on the identification and mitigation of all safety issues associated with design verification.

P.7     TRAINING

None.

P.8     RECORDS

| Record Title | Record Custodian | Retention |
| --- | --- | --- |
| Work Order Authorization (WOA) or equivalent for software, Completed | Product Manager (PM) | * NRRS 8/103 Engineering test and evaluation data. Temporary. Destroy between 5 and 30 years after program/project termination. |
| Design Verification Test Reports and/or Summaries | Product Design Lead (PDL) | * NRRS 8/103 |

*NRRS - NASA Records Retention Schedules (NPR 1441.1)

P.9     MEASUREMENT/VERIFICATION

The Responsible Office for this directive shall ensure that internal and external third party audit findings related to effective design development are used to assess the directive's effectiveness.

Procedures

In this document, a requirement is identified by “shall,” a good practice by “should,” permission by “may” or “can,” expectation by “will,” and descriptive material by “is”.

1.  Design Input

The Product Design Lead (PDL) shall convene the Product Design Team (PDT) to review the customer requirements (generated through implementation of GPR 1310.1 and/or other means) and the design plan (see GPR 8700.1), review the scope of the product design, document derived requirements as design input, and develop detailed product designs as appropriate.

1.1  For design input related to implementation of basic adhesive bonding and/or primary structural bonding, the PDL shall include the requirement that certified bonding personnel are to be used per 500-PG-3410.2.1.

1.2  The PDL shall use 500-PG-8700.2.7 and 500-PG-8700.2.8 for design and development of Field Programmable Gate Arrays.

1.3  Where mechanical fasteners are used in designs, the PDL shall adhere to 540-PG-8072.1.2 and

541-PG-8072.1.2.

1.4  The PDL shall identify critical design elements, and key characteristics that must be controlled, based on customer requirements and systems engineering processes defined in GPR 7123.1, as appropriate.

1.5  When developing detailed product designs, the PDL shall determine if statistical techniques will be utilized as part of the design process and, if so, document such techniques per GPR 8070.2.

1.6  As a result of design verification or product validation (and subsequent corrective action per GPR 1710.1), additional design development activities may be required.  In these cases, the PDL shall update the design plan documentation generated by GPR 8700.1.

2.  Design Output

The PDT shall document the design output in terms that can be verified against design requirements.  Design output consists of drawings, specifications, and/or procedures necessary to manufacture and/or operate the product.  This includes acceptance criteria for product validation as well as specific requirements for safe and proper functioning of the product.

2.1  Design output documentation shall include specific actions to be taken to address critical design items and to ensure that key characteristics are controlled per requirements, with plans for verification and validation as needed.

2.2  The PDL shall ensure engineering drawings are produced per 500-PG-8700.2.5.

2.3  Design output shall be used to refine the Product Validation Plan (see GPR 8700.1 and GPR 8700.3).

3.  Design Verification

The process of design verification includes, but is not limited to, drawing checking, finite element analysis, breadboard/prototype tests, software code walk-throughs, electronic design tool simulations, mathematical simulations, and engineering peer reviews (See GPR 8700.6).

3.1  The PDT shall perform design verification activities per the design plan (see GPR 8700.1).

3.2  The Work Order Authorization (WOA, Form 4-30), or equivalent for software, shall be used to document all functional and environmental tests for design verification and, where applicable, the WOA may be used to document other design verification activities (See GPR 5330.1).

4.  Product Configuration Control

The PDT shall ensure that design changes are controlled and documented in accordance with the applicable configuration control procedures as described in GPR 1410.2.  If the design fails to meet requirements, the PDL shall recommend and implement design changes per these procedures.

5.  Design Review Support

The PDL/PDT shall prepare and present documentation for design reviews (see GPR 8700.4 and GPR 8700.6), as required by the design plan (See GPR 8700.1).

#### 6.  Design Release

The PDL shall document the successful completion of design development and verification, and release the design for final product fabrication (and subsequent validation per GPR 8700.3) in accordance with the design plan (see GPR 8700.1) and customer requirements (see GPR 1310.1).

Design Development Flowchart

Records

Customer Requirements from GPR 1310.1

Corrective Action per GPR 1710.1

2.

Generate design output

Start

Design Plan from GPR 8700.1

Does the design meet the requirements?

6.

Release design for product fabrication

Yes

No

4.

Change design per configuration control procedures

3.

Perform design verification activities

5.

Support design reviews

1.

Gather/Generate design inputs

Appendix A: Definitions

A.1  Critical Item – An item that has a major impact on the realization and use of the product or system to be developed.  Items are critical if they have a significant effect on the safety, performance, form, fit, function, producibility, testability, or lifetime of the product.  They include, but are not limited to, mission critical items and safety critical items.

A.2  Key Characteristic – A feature or attribute that has significant impact or effect on the performance, form, fit, function, producibility, testability, or lifetime of the product when it varies.  Each key characteristic typically needs to be controlled or managed.  Examples include use of dimensional tolerances, mass budgets, and electronic noise budgets.

A.3  Product Design Lead (PDL) – The manager or leader with overall responsibility for managing the design activity, managing the technical and organizational interfaces identified during design planning, and where required, forming and leading the Product Design Team (PDT).  PDL refers to flight project managers, mission managers, instrument managers, subsystem technical managers, integrated product development team leaders, lead engineers, etc.

A.4  Product Manager (PM) – The manager or leader with overall responsibility for a product.  PM usually refers to the project manager or instrument manager.

A.5  Validation – Proof that the product accomplishes the intended purpose.  (The “product” may be the operations concept, the requirements, the architecture/design, the mission plan, and/or other end-item deliverable.)  May be determined by test, analysis, and demonstration.  Generally accomplished through trade studies and performance analysis by Phase B and through testing in Phase D.

A.6  Verification – Proof that the design is compliant with requirements and specifications.  May be determined by test, analysis, and inspection.

Appendix B: Acronyms

PDL – Product Design Lead

PDT – Product Design Team

PM – Product Manager

WOA – Work Order Authorization

CHANGE HISTORY LOG

| Revision | Date | Description of Changes |
| --- | --- | --- |
| Baseline | 8/12/98 |  |
| A | 10/6/98 | Header and footer format changes. New title for GPG 1310.1 reference. Indicated responsibility for maintenance of quality records. |
| B | 05/07/99 | Clarified Purpose. Corrected reference list to include GPG 1710.1. Added definition for validation. Added requirements to update product design plans and to consider use of statistical methods in step 2.1. Divided step 2.2 into 2.2 (design output) and 2.3 (design verification). Moved requirement to create a validation plan to GPG 8700.1. Clarified PDL’s responsibilities regarding design changes in step 2.4.2. Modified quality records requirements. Modified flow chart to support the text. |
| C | 05/04/00 | Added GPG 1410.2 as a reference. Modified Quality Records requirements to include completed WOA’s, with the Product Manager as custodian, to be consistent with GPG 5330.1. Deleted definitions of Configuration Baseline, Configuration Control Board, Configuration Documents, and Configuration Items. Removed all configuration management requirements and referenced GPG 1410.2. |
| D | 01/05/05 | As directed during the FY04 Center Rules Review, the Responsible Office modified this document to remove requirements that were no longer needed and to clearly distinguish requirements from supporting information. Administrative changes were made throughout to correct responsible organization names and codes, and to retitle Goddard Procedures and Guidelines (GPG) to Goddard Procedural Requirements (GPR). All changes were reviewed and approved by the Goddard Quality Management System Council (QMSC). |
| D | 05/13/05 | Expiration date was extended to July 5, 2005 per the attached memo signed by Mr. Weiler. |
| D | 07/11/05 | Expiration date was extended to September 6, 2005 per the attached memo signed by Mr. Weiler. |
| E | 07/29/2005 | Added Safety, Training, Metrics, and Definitions paragraphs to the Preface per the current GPR format. Updated definitions of "verification" and "validation" to align with NPR 7120.5. Updated paragraph numbering throughout, including paragraph references on the flowchart. Included reference to GPR 8700.6, Engineering Peer Reviews as part of the design verification process. |
| F | 11/15/2011 | Revised format per GPR 1410.1. Formatted the procedure such that each “shall statement” has its own paragraph or sub-paragraph number. Added requirements to address critical items, key characteristics, and associated actions (per AS9100) to paragraphs 1 and 2. Added references to Systems Engineering (GPR 7123.1), Basic Adhesive Bonding Requirements (500-PG-3410.2.1), Engineering Drawing Requirements Manual (500-PG-8700.2.5), Design of Space Flight Field Programmable Gate Arrays (500-PG-8700.2.7), Field Programmable Gate Array Development Methodology (500-PG-8700.2.8), Mechanical Fastener Torque Guidelines (540-PG-8072.1.2), and Goddard Space Flight Center Fastener Integrity Requirements (541-PG-8072.1.2) to paragraphs 1 and 2. Updated retention schedules in P.8 per NPR 1441.1D. |